# swFOCE Repair Work Sept 2015

## Cable Terminations

Terminate both ends of the (2) new 30m cables with MINK16-CCP connectors

Test both 30m cables using existing quikFOCE can

Pot all four ends of the (2) 30m cables

### Prior to Sept 10th Cruise

x - Verify George has all of the Subconn dummies he needs for housings recovery

### Sept 10th

R/V Paragon – Recover 15m cables (2) and 52m cable

Bring Jose along

Dummy off bulkhead connections (5)

CN (3)

MEH #1 (1)

MEH #2 (1)

### Post Sept 10th Cruise

Re-Terminate the bad end of the 52m cable

Test 52m cable

Pot new connector on 52m cable

## KFA Power Can

Once the (2) 30m cables and (1) 52m cable have been tested,

Remove all of the electronics from the quikFOCE can

Install 300Vdc:12Vdc Micro Vicor

Use existing J-Box cable from dpFOCE

Test Power Can (loaded condition)

## Motors

Fabricate (2) Y-Whips (use for testing)

Test Elmo+motor on bench

Test Elmo+motor on bench with Sensor Node

Test Elmo+motor on bench with Sensor Node and Gateway Node

Fabricate oil filled cabling assembly (utilizing the 2 Y-whips)

Test entire cable+Elmo+motor dry

Test entire cable+Elmo+motor in the test tank

## Second Deployment (Last Half of Sept)

Deploy (2) 30m and (1) 52m cables

Install KFA Power Can on Micronode

Test power/communications from shore while housings are on the R/V Paragon

Deploy new motor assemblies the same day?

## September 2015

Sun		Mon		Tue		Wed		Thur		Fri		Sat

| 30 | 31 | 1 | 2 | 3 | 4 Off Friday | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| 6 | 7 Labor Day | 8 | 9 | 10 R/V Paragon | 11 | 12 |
| 13 | 14 | 15 | 16 | 17 Chad OffShore | 18 Off Friday Chad OffShore | 19 Chad OffShore |
| 20 Chad OffShore | 21 Chad OffShore | 22 Chad OffShore | 23 Chad OffShore | 24 Chad OffShore | 25 Chad OffShore | 26 Chad OffShore |
| 27 Chad OffShore | 28 Chad OffShore | 29 Chad OffShore | 30 Chad OffShore |  |  |  |