KFA/quikFOCE Deployment Tuesday May 20th



Shore (HMS Pumphouse): Jim Montgomery & Bob Herlien

R/V Paragon: Jared Figurski, Chad Kecy, & Tom Marion

Divers: George Matsumoto, Kerry Nichols, Jessica Moye, Jamie Dunckley, Paul Leary, Steve Litvin, Nyssa Silbiger


Monday May 19th
Afternoon: MOB the R/V Paragon (if possible)
		KFA Central Node + cables
		swFOCE chamber
		quikFOCE system
		Tool Box 
		Asstd accessories		


Tuesday May 20th
8:30 AM: Paragon departs Moss Landing
9:15 AM: Paragon arrives at KFA site
		We will call divers when we’re almost there, they will meet us in the whaler
9:30 AM: Dive #1 (Recover the KFA Micronode+tether to Paragon)
10:00AM: Dive #2 (Deploy swFOCE chamber)

	Specific work plan (10:00am-~12:00pm)
	
Receive KFA micronode tether from divers
	Verify with Jim that no power is applied
	Remove endcap
	Unplug Ethernet
	Cut internal power cables and tape off
	Call Jim – perform megger test on isolated tether
	When megger test is done, terminate power leads with connectors
	Plug in Ethernet cables to OE converters
	Plug in internal power leads
	Call Jim 
		Energize KFA
		Measure at SeaConn conn
		Energize swFOCE
		Measure at SeaConn conn
		Power down KFA
		Power down swFOCE
		Connect 2m cable between micronode & central node
		Connect 30m cable between micronode & quikFOCE
		Energize KFA
		Energize swFOCE
		Verify KFA power usage (~200mA @ 325Vdc)
		Verify quikFOCE power usage (~35mA @ 400Vdc)
	 	Perform Ethernet connectivity test of swFOCE (Bob)
		Perform Ethernet connectivity test of KFA (Bob)
		Power down KFA
		Power down swFOCE
	Disconnect 2m & 30m cables from micronode
	Seal up micronode (with desiccant)
	Mount micronode onto central node
	Connect 2m & 30m cables (tie wrap excess cables in final configuration)
	Connect line to KFA CN/micronode
	Dip KFA into water
	Call Jim
		Energize KFA & swFOCE
		Monitor for ground faults (~10min)
		Power down KFA & swFOCE
	Call divers
		
~12:00PM: Dive #3 (Deploy KFA & quikFOCE system)

	

~1:00PM
	Wait for divers to get back in the whaler
	Shore: Power up KFA & swFOCE
[bookmark: _GoBack]		Monitor for ground faults (60 minutes)
		System check of quikFOCE
			Verify comms/operation of all instruments
	
	Paragon: Head back to Moss Landing












