KFA/quikFOCE Deployment Tuesday May 20th

Shore (HMS Pumphouse): Jim Montgomery & Bob Herlien

R/V Paragon: Jared Figurski, Chad Kecy, & Tom Marion

Divers: George Matsumoto, Kerry Nichols, Jessica Moye, Jamie Dunckley, Paul Leary, Steve Litvin, Nyssa Silbiger

Monday May 19th

Afternoon: MOB the R/V Paragon (if possible)

KFA Central Node + cables

swFOCE chamber

quikFOCE system

Tool Box

Asstd accessories

Tuesday May 20th

8:30 AM: Paragon departs Moss Landing

9:15 AM: Paragon arrives at KFA site

We will call divers when we’re almost there, they will meet us in the whaler

9:30 AM: Dive #1 (Recover the KFA Micronode+tether to Paragon)

10:00AM: Dive #2 (Deploy swFOCE chamber)

Specific work plan (10:00am-~12:00pm)

Receive KFA micronode tether from divers

Verify with Jim that no power is applied

Remove endcap

Unplug Ethernet

Cut internal power cables and tape off

Call Jim – perform megger test on isolated tether

When megger test is done, terminate power leads with connectors

Plug in Ethernet cables to OE converters

Plug in internal power leads

Call Jim

Energize KFA

Measure at SeaConn conn

Energize swFOCE

Measure at SeaConn conn

Power down KFA

Power down swFOCE

Connect 2m cable between micronode & central node

Connect 30m cable between micronode & quikFOCE

Energize KFA

Energize swFOCE

Verify KFA power usage (~200mA @ 325Vdc)

Verify quikFOCE power usage (~35mA @ 400Vdc)

Perform Ethernet connectivity test of swFOCE (Bob)

Perform Ethernet connectivity test of KFA (Bob)

Power down KFA

Power down swFOCE

Disconnect 2m & 30m cables from micronode

Seal up micronode (with desiccant)

Mount micronode onto central node

Connect 2m & 30m cables (tie wrap excess cables in final configuration)

Connect line to KFA CN/micronode

Dip KFA into water

Call Jim

Energize KFA & swFOCE

Monitor for ground faults (~10min)

Power down KFA & swFOCE

Call divers

~12:00PM: Dive #3 (Deploy KFA & quikFOCE system)

~1:00PM

Wait for divers to get back in the whaler

Shore: Power up KFA & swFOCE

Monitor for ground faults (60 minutes)

System check of quikFOCE

Verify comms/operation of all instruments

Paragon: Head back to Moss Landing