Electrical tasks for the shallow water version of FOCE.

1. Design the input power circuits.

This includes the main power cable to the Hopkins observatory, inrush limiting, ground fault monitoring, voltage and current monitoring, and DC-DC conversion.

2. Interface to all science and engineering instruments.

I will need to compile a list of all necessary instruments, including optional external sensors and cameras which may be needed. This will help define the power and communication requirements. Included in this is the new inductive power coupling connectors (how many on frame?)

3. Make an overall block diagram of the system.

This includes all external and internal electronics and instruments.  The number of junction boxes and interconnection cables will be decided on at this point.

4. Design and test the new chassis system.

A backplane system is being designed which will make future upgrades/additions much easier.

5. Design and test the new power input circuits.

New power input boards will need to be developed. We will be running off of 300Vdc input. Need a compiled list of instruments to know which DC voltages we will need.

6. Integrate and test the individual electrical subsystems.

Lots of new hardware will be added to the shallow water version.

Estimation for EE time needed for shallow water system for 2011:

Power System				176hrs

Design				40hrs

Fab + populate boards 		40hrs

Test boards			16hrs

Software			80hrs

Chassis system			816hrs

Low voltage load switch		176hrs

Design			40hrs

Fab + populate boards	40hrs

Test boards		16hrs

Software		80hrs

High voltage load switch		176hrs

Design			40hrs

Fab + populate boards	40hrs

Test boards		16hrs

Software		80hrs

Ground fault detection board	176hrs

Design			40hrs

Fab + populate boards	40hrs

Test boards		16hrs

Software		80hrs

Power Supply Board		96hrs

Test boards		16hrs

Software		80hrs

CPU Board			96hrs

Test boards		16hrs

Software		80hrs

Environmental board		96hrs

Test boards		16hrs

Software		80hrs

Integration				240hrs

External manifold wiring		40hrs

External cable design/manuf	80hrs

Junction box wiring		40hrs

Int electronics housing wiring	80hrs

System Level Testing			240hrs

Each instr power+comms	24hrs (x10?)

Total number of EE hours:		1472hrs

Possible instruments:

pH probes (x6)

CTD (x2)

Nortek velocimeter

RDI ADCP

Turbidity measurement

Spectrometer

Fluorescence measurement

Camera(s)

Light(s)

Pan and Tilt?

Pumps (x2?)

Motors (x2?) – for thrusters

Internal Electronics:

Ethernet switch (Netgear)

Video server (Axis)

Serial server (Digi)

PC/104 stack

Power supply

CPU

Octal serial board (x2)

Hard drive

Chassis System

Power Supply

CPU

Environmental board

Ground fault detection board

Low Voltage Load Switcher (# TBD)

High Voltage Load Switcher (# TBD)

Input Power Conversion

Inrush limiter

Individual DC-DC boards

Number of them required and DC voltages TBD

Thermal cooling for converters