Teleconference notes  1/25/2016

Thanks to all for your help in planning our mobile microscope-cytometer workshop!

Attendees: Schmitz, Klimov, Sosik, Chavez, Scholin, Ryan, O’Reilly

Action items

Provide comparison of existing instruments to steering commitee - O’Reilly, Klimov

- Detailed science use cases, specifying sampling requirements (depth, frequency, particle size, etc)

  - West Coast HABs - Ryan

  - Export - Chavez

  - Open ocean - ???

  - Template to insure consistency/comparability - O’Reilly, Klimov

- Contact Kudela about steering committee - O’Reilly

- Identify potential contributions of proposed developer attendees

- Set up poll for next telecon (3 weeks is too late) - O’Reilly

Detailed notes

Today’s telecon goals - annotated. Please comment on errors and omissions.

0. Finalize workshop date: week of 30 May through 3 June (duration TBD): This date is OK with steering committee.

1. Workshop goals - e.g. discover specific science applications, available vehicle and instrument technologies, opportunities

Sosik: most science attendees are aware of specific use case details - don’t dwell on these at workshop.

Scholin: Need specific use cases to set requirements for developers.

Schmitz: Yes, science applications/requirements not yet obvious for JRF.

RESOLVED: Science steering committee members will generate use cases before the workshop.

2. How to structure discussion of applications versus technology

Consensus: minimize presentations, maximize discussions. Don’t ask developers to give presentations without awareness of science applications.

Ryan: Tech developers should somehow summarize their instrument capabilities.

O’Reilly, Klimov: Could provide instrument capability form to developers to fill out before workshop - then discuss at workshop in context of use cases.

Scholin, Sosik: Want to identify specific problems that need to be solved.

Sosik, Schmitz: Useful to present overview comparison of different tech - leverage Klimov-O’Reilly results for this. Provide online beforehand.

Sosik, Chavez: Would like to see tech expert overview of certain key technologies; microfluidics, informatics, onboard processing, cameras-microscopes, miniature/low-power electronics, battery technology - experts needn’t specialize in microscopy/cytometry.

O’Reilly, Scholin: Several MBARI engineers can attend - Hobson and Zhang (AUVs), Roman and Maughan (onboard processing)

3. Workshop duration, size, attendees

- Budget not to exceed $20K

- Domestic travel <$1400, Europe ~$1800, Asia ~$2200, several local attendees

Current attendee list would cost about $20K.

Consensus: Current list size (~25) is manageable size for workshop goal - don’t get much bigger though.

Sosik: Need to describe what is expected from each developer attendee. Don’t send developer invitations until this is done.

Sosik, Scholin: preparation by all attendees ahead of workshop is critical. Need to identify limitations of current approaches in order to close gaps.

Scientist homework: develop use cases, with details on particle size ranges, depths, endurance, etc.

Developer homework: Identify instrument/tech capabilities, limits (size, power, counting rates, state-of-the-art, what’s on the horizon, etc)

4. Workshop product - report, implementation, avenues, etc.

Not specifically discussed

------------------------------------------------

Thomas C. O'Reilly
Monterey Bay Aquarium Research Institute
7700 Sandholdt Road
Moss Landing, CA 95039
831-775-1766
oreilly@mbari.org
http://www.mbari.org
"The machine does not isolate us from the great mysteries of nature, 
but plunges us more deeply into them."

    - ANTOINE DE SAINT-EXUPERY
      "Wind, Sand, and Stars" (1939)