## Budget
Item | Cost | Notes | Actual Spending
Iridium SBD comms | 18900 | From our discussions plan for 210 days of Wave Glider operations $90/day | 25000
Iridium Rudics comms | 8500 | Based on totals from previous years | 5000
LR Piloting | 20000 | Plan for 80 days of LR piloting @ $250 per day | 8000
Intervention Emergency Recovery | 4000 | Will be supplemented by funds saved during vehicle downtime
Insurance | N/A | We are assuming this is covered by DMO vehicle insurance?
Spare parts/sensors
Spare Xeos emergency tracker | 2300 | Quote from LR | 2397.86
Spare Wetlabs Eco Puck | 9000 | Estimated | 9198
SBE GPCTD + DO | 17500 | Estimated
Airmar (weather station) | 1600 | Quote from LR
Powered radar deflector | 3100 | Quote from LR ended up purchasing 3 mast due to tinys collision | 10863
Licor |  |  | 5300
Sensor Calibrations
SBE GPCTD + DO | 1500 | Estimated | 1090
Wetlabs ECOPUCK | 1000 | Estimated | 795
Vemco VR2C |  |  | 5442.5
LR Dev time |  |  | 5000
Misc parts/tools/cables | 5000 | Estimated | 13427.09
remaining
Total | 92400 | ~12k added to budget on03NOV2016 not included here | 91513.45 | 886.55