## Sheet1
Ship Name | Project ID | Project Title | Project Manager | Funding Source | Days | Transit Days | Proposed Date | Alternate Date | Equipment | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
Wave Glider Requests
Wave Glider | 300082 | DMO Support - Wave Glider | Grech, Chris | MBARI | 8 | 0 | 2017-01-02 | 2017-01-03 | Engineering test days |  | Less than 20nm |  |  | Flexible | Testing of the Wave Glider off the Paragon
Wave Glider | 704106 | LRAUV Fault Detection | Zhang, Yanwu / Belligham Jim | MBARI | 6 | 0 | 2017-02-01 | 2017-03-01 | Wave Glider-SV3 Sparky |  | Less than 20nm
Wave Glider | 901009 | CANON | Chavez, Francisco | MBARI | 50 | 0 | 2017-01-01 | 2017-01-10 |  |  | Less than 20nm |  |  | These are not consecutive but to be used to support CANON campaigns in early May and October.
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-01-15 | 2017-01-18 |  |  | Less than 20nm |  |  | Need to monitor BIN and BEDS
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-02-15 | 2017-02-18 |  |  | Less than 20nm |  |  | Need to monitor BIN and BEDS
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-03-15 | 2017-03-17 |  |  | Less than 20nm |  |  | The schedule on middle March for this Wave glider trip is especially important because we need to localize the BEDS and other equipment to assist in their recoveries
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-06-01 | 2017-06-03 |  |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BEDS through the year
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-07-01 | 2017-07-03 |  |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BIN until end of March, and BEDS through the year
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-09-01 | 2017-09-01 |  |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BIN until end of March, and BEDS through the year
Wave Glider | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-11-01 | 2017-11-03 |  |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BIN until end of March, and BEDS through the year
Wave Glider | 901112 | Change in MB and CA Current | Pennington, Tim | MBARI | 50 | 0 | 2017-01-01 | 2016-01-02 | CTD, CTD 12hr |  | Between 20nm & 50nm |  |  | 16 days, one each 3 weeks in concert with MBTS cruises. 34 additional days for other activities.
Wave Glider | 901513 | Adaptive Sampling by Autonomous Underwater Vehicles | Zhang, Yanwu | MBARI | 6 | 0 | 2017-02-01 | 2017-03-01 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Either wave glider can be used for front tracking tests. (Will only use one wave glider.) | Chris Wahl will take charge of the wave glider operations.
Wave Glider | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 4 | 8 | 2017-01-10 | 2017-01-17 | Wave Glider-SV3 Sparky |  | Greater than 50nm | Sta. M; 34 50 9N, 123 00 9W | Sta. M; 34 50 9N, 123 00 9W |  | communicate with Rover and SES.
Wave Glider | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 4 | 8 | 2017-03-04 | 2017-03-06 | Wave Glider-SV3 Sparky |  | Greater than 50nm | Sta. M; 34 50 9N, 123 00 9W | Sta. M; 34 50 9N, 123 00 9W | Rendezvous with Western Flyer | communicate with Rover and SES.
Wave Glider | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 4 | 8 | 2017-07-14 | 2017-07-24 | Wave Glider-SV3 Sparky |  | Greater than 50nm | Sta. M; 34 50 9N, 123 00 9W | Sta. M; 34 50 9N, 123 00 9W |  | communicate with Rover and SES.
Wave Glider | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 4 | 8 | 2017-09-09 | 2017-09-15 | Wave Glider-SV3 Sparky |  | Greater than 50nm | Sta. M; 34 50 9N, 123 00 9W | Sta. M; 34 50 9N, 123 00 9W |  | communicate with Rover and SES.
Wave Glider | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 4 | 8 | 2017-11-01 | 2017-11-08 | Wave Glider-SV3 Sparky |  | Greater than 50nm | Sta. M; 34 50 9N, 123 00 9W | Sta. M; 34 50 9N, 123 00 9W | Rendezvous with Western Flyer | communicate with Rover and SES.
Wave Glider | 901717 | Long Range AUV Ops Support | Hobson, Brett | MBARI | 5 | 0 | 2017-01-01 | 2017-01-02 |  |  | Less than 20nm
|  |  |  | Totals | 152 | 40 | 192
Paragon Requests
Paragon | 300057 | Mooring Maintenance | Dawe, Craig | MBARI | 12 | 0 | 2017-01-01 | 2017-01-02 | CTD winch |  | Less than 20nm |  |  | Requesting approximately 12 days throughout the year for maintenance runs. Scheduling hard to predict. | 4 days of SCUBA diving, the remainder are topside mooring visits
Paragon | 300082 | DMO Support - Wave Glider | Grech, Chris | MBARI | 8 | 0 | 2017-01-01 | 2017-01-02 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky | wave glider ops | Less than 20nm |  |  |  | Testing days for wave glider
Paragon | 704106 | LRAUV Fault Detection | Zhang, Yanwu / Belligham Jim | MBARI | 1 | 0 | 2017-02-01 | 2017-03-01 | Wave Glider-SV3 Sparky |  | Less than 20nm |  |  |  | For testing wave glider front tracking. Brian Kieft will be the pilot, and Tom O'Reilly will be onboard to help with launch and recovery. Their labor is already included in the proposal.
Paragon | 901009 | CANON | Chavez, Francisco | MBARI | 30 | 0 | 2017-01-01 | 2017-01-10 | CTD winch | No equipment needed | Less than 20nm |  |  | These are not consecutive but to be used for deployment recovery of floats, AUVs and wave gliders
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-01-15 | 2017-01-18 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Need to monitor BIN and BEDS
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-02-01 | 2017-02-03 | AUV - Mapping | USBL pole | Less than 20nm |  |  | Schedule is not rigid and depends on the occurrence of events on the Canyon and whether BEDS come to the surface. "AUV-Mapping" not necessary but selected to be able to do the ship day entry in the web interface for scheduling
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-02-15 | 2017-02-18 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Need to monitor BIN and BEDS
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-03-15 | 2017-03-17 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | The schedule on middle March for this Wave glider trip is especially important because we need to localize the BEDS and other equipment to assist in their recoveries
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-06-01 | 2017-06-03 | AUV - Mapping | USBL pole | Less than 20nm |  |  | Schedule is not rigid and depends on the occurrence of events on the Canyon and whether BEDS come to the surface. "AUV-Mapping" not necessary but selected to be able to do the ship day entry in the web interface for scheduling
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-06-01 | 2017-06-03 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BEDS through the year
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-07-01 | 2017-07-03 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BIN until end of March, and BEDS through the year
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-07-15 | 2017-07-18 | AUV - Mapping | USBL pole | Less than 20nm |  |  | Schedule is not rigid and depends on the occurrence of events on the Canyon and whether BEDS come to the surface. "AUV-Mapping" not necessary but selected to be able to do the ship day entry in the web interface for scheduling
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-08-01 | 2017-08-03 | AUV - Mapping | USBL pole | Less than 20nm |  |  | Schedule is not rigid and depends on the occurrence of events on the Canyon and whether BEDS come to the surface. "AUV-Mapping" not necessary but selected to be able to do the ship day entry in the web interface for scheduling
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-09-01 | 2017-09-03 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BIN until end of March, and BEDS through the year
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-10-01 | 2017-10-03 | AUV - Mapping | USBL pole | Less than 20nm |  |  | Schedule is not rigid and depends on the occurrence of events on the Canyon and whether BEDS come to the surface. "AUV-Mapping" not necessary but selected to be able to do the ship day entry in the web interface for scheduling
Paragon | 901023 | Continental Margin Process | Gwiazda, Roberto | MBARI | 1 | 0 | 2017-11-01 | 2017-11-03 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Schedule is not rigid. Need to monitor BIN until end of March, and BEDS through the year
Paragon | 901103 | Biodiversity and Biooptics | Haddock, Steve | MBARI | 6 | 0 | 2017-01-01 | 2017-01-01 | CTD winch |  | Less than 20nm |  |  |  | for blue water SCUBA diving
Paragon | 901107 | SeeStar Imaging System | Kecy, Chad | MBARI | 1 | 0 | 2016-10-01 | 2016-10-02 | CTD winch | Using divers | Less than 20nm |  |  |  | We will be deploying the SeeStar III system for testing in a shallow location (TBD) during the latter half of the year - Fall or Winter.
Paragon | 901112 | Change in MB and CA Current | Pennington, Tim | MBARI | 25 | 0 | 2017-01-01 | 2017-01-02 | AUV - CTD |  | Between 20nm & 50nm |  |  | 16 days to support Dorado/Gulper and Tethys/Sipper deployments on MBTS days 9 additional days to support Wave Glider and other activities
Paragon | 901200 | AMP | Matsumoto, George | MBARI | 1 | 0 | 2017-07-11 | 2017-07-18 | None |  | Less than 20nm
Paragon | 901200 | AMP | Matsumoto, George | MBARI | 2 | 0 | 2017-01-25 | 2017-02-08 | None |  | Less than 20nm
Paragon | 901200 | AMP | Matsumoto, George | MBARI | 2 | 0 | 2017-07-25 | 2017-08-01 | ROV | DO not need a ROV, not sure how that even got onto the form. No equipment needed | Between 20nm & 50nm |  |  | four days; two 2-day trips. For Albacore collections between July-October depending on water temperatures and albacore presence.
Paragon | 901200 | AMP | Matsumoto, George | MBARI | 2 | 0 | 2017-09-12 | 2017-09-19 | AUV - Other | no equipment needed. Form requires selection of one of the above | Between 20nm & 50nm |  |  | four days; two 2-day trips. For Albacore collections between July-October depending on water temperatures and albacore presence.
Paragon | 901200 | AMP | Matsumoto, George | MBARI | 2 | 0 | 2017-10-17 | 2017-11-14 | None |  | Less than 20nm
Paragon | 901206 | Coastal Profiling Float | Massion, Gene | MBARI | 20 | 0 | 2017-01-03 | 2017-02-15 | CTD winch | Not really required but we have to check something | Less than 20nm |  |  | We are requesting 20 days spread roughly over the entire year.
Paragon | 901405 | Wave Energy Conversion Oceanographic Applications | Hamilton, Andy | MBARI | 1 | 0 | 2017-05-01 | 2017-06-01 | CTD winch | Only Diver support needed, CTD winch specified only to satisfy web entry, not needed. | Less than 20nm |  |  | Scheduling is flexible and would in fact consist of two half days ideally. | These days are used for diver support. Scheduling is flexible and date is approximate.
Paragon | 901405 | Wave Energy Conversion Oceanographic Applications | Hamilton, Andy | MBARI | 2 | 0 | 2017-11-01 | 2017-12-01 | CTD winch | Only Diver support needed, CTD winch specified only to satisfy web entry, not needed. | Less than 20nm |  |  | Scheduling is flexible and would in fact consist of four half days ideally. | Scheduling is flexible and would in fact consist of four half days ideally.
Paragon | 901513 | Adaptive Sampling by Autonomous Underwater Vehicles | Zhang, Yanwu | MBARI | 1 | 0 | 2017-02-01 | 2017-03-01 | Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Either wave glider can be used for front tracking tests. (Will only use one wave glider.) | Brian Kieft will be the pilot. Tom O'Reilly will be onboard to help with launch and recovery.
Paragon | 901606 | Park and Fly AUV for Long-term Abyssal Surveys | Smith, Ken | MBARI | 10 | 0 | 2017-10-07 | 2017-10-12 | AUV - Other | Iceberg AUV | Less than 20nm |  |  | Tow-out for homing trials offshore MBARI
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-01-10 | 2017-01-17 | Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | deploy wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-01-22 | 2017-01-29 | None |  | Less than 20nm |  |  | recover wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-03-04 | 2017-03-06 | Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | deploy wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-03-15 | 2017-03-18 | None |  | Less than 20nm |  |  | recover wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-07-14 | 2017-07-24 | Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | deploy wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-07-26 | 2017-08-02 | None |  | Less than 20nm |  |  | recover wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-09-09 | 2017-09-15 | Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | deploy wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-09-21 | 2017-09-27 | None |  | Less than 20nm |  |  | recover wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-11-01 | 2017-11-08 | Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | deploy wave glider
Paragon | 901618 | Pelagic-Benthic Coupling | Huffard, Christine | MBARI | 1 | 0 | 2017-11-13 | 2016-11-20 | None |  | Less than 20nm |  |  | recover wave glider
Paragon | 901700 | Acoustical Ocean Ecology | Waluk, Chad | MBARI | 20 | 0 | 2017-01-01 | 2017-01-02 | CTD winch | Pole mounted acoustics, Auto-profiling CTD, + | Less than 20nm |  |  |  | Science to be scattered throughout the year in 2-3 day episodes
Paragon | 901704 | Next Generation Observation Lander | Kecy, Chad | MBARI | 5 | 0 | 2016-07-01 | 2016-07-02 | CTD winch | Lowering new system via winch | Less than 20nm |  |  | Our days don't have to be consecutive, just during the month of July. | We will be lowering the Multi-Purpose Benthic Observation System down on the Paragon.
Paragon | 901713 | Nearshore FOCE | Walz, Peter | MBARI | 4 | 0 | 2017-01-01 | 2017-01-02 | CTD winch |  | Less than 20nm |  |  | Spread through year as required for project | Some diving - Hopkins Marine Station FOCE location
Paragon | 901716 | MBA Plastics in the Food Web | Choy, Anela | MBARI | 3 | 0 | 2017-05-01 | 2017-06-01 | CTD winch |  | Less than 20nm |  |  |  | Jared Figurski as Chief operator
Paragon | 901716 | MBA Plastics in the Food Web | Choy, Anela | MBARI | 3 | 0 | 2017-11-01 | 2017-12-01 | CTD winch |  | Less than 20nm |  |  |  | Jared Figurski as Chief operator
Paragon | 901717 | Long Range AUV Ops Support | Hobson, Brett | MBARI | 55 | 0 | 2017-01-01 | 2017-01-02 | LRAUV LARS |  | Less than 20nm
Paragon | 901721 | Wave Glider Hot Spot Support | OReilly, Tom | MBARI | 5 | 0 | 2017-09-01 | 2017-09-02 | AUV - Other, LRAUV LARS, Wave Glider-SV3 Tiny, Wave Glider-SV3 Sparky |  | Less than 20nm |  |  | Total five Paragon days in 2017 in Q3, to launch/recover 2 LRAUVs and Wave Glider Hot spot 10 days total for two LRAUVs 10 days Wave Glider Hot Spot | Launch Hot Spot and two LRAUVs for acoustic data transfer demonstration