## Budget 250 Hrs
2018 Preliminary Budget for Project 370000 (assuming 260 total Wave Glider days at sea)
Item | Cost | Notes
Iridium SBD comms | 31200 | From our discussions plan for 260 days of Wave Glider operations $120/day
Iridium Rudics comms | 8000 | Based on totals from previous years
LR mission setup | 12000 | LR mission setup required for 4 missions $3000 per
LR Piloting | 20000 | Plan for 80 days of LR piloting @ $250 per day
Intervention Emergency Recovery | 4000 | Will be supplemented by funds saved during vehicle downtime
Insurance | 7882 | Number from Mike Kelly, assuming payment is about the same as 2016
Conference Travel | 3000 | International travel for Euro Glider conference
Spare parts/sensors
SBE GPCTD + DO | 17500 | From 2015 quote
Two replacement Umbilicals | 74000 | from 2017 quote recommended replacment after 2 years at sea, should we buy a second so that we have a new spare?
replacement wing springs | 780 | from 2017 quote recommended replacment after 2 years at sea
thrudder bushing repalcement | 1000 | from 2017 quote recommended replacment after 2 years at sea
replacement battery set | 1800 | recommended replacment after 2 years at sea
glider replacement frame | 3200 | damaged, I think it should be replaced
airmar | 1600 | keep failing we need spares
Sensor Calibrations
SBE GPCTD + DO | 6000 | $1500 X 4, from 2015 quote
Wetlabs ECOPUCK | 2000 | $1000 x 2, from 2015 quote
Misc parts/tools/cables | 6000 | Estimated
Total | 199962

## Actual Spending 250 Hrs
2018 actual spending |  |  |  | Actual | Difference
Item | Cost | Notes
Iridium SBD comms | 31200 | From our discussions plan for 260 days of Wave Glider operations $120/day |  | 36000 | -4800
Iridium Rudics comms | 8000 | Based on totals from previous years |  | 7200 | 800
LR mission setup | 12000 | LR mission setup required for 4 missions $3000 per |  | 0 | 12000
LR Piloting | 20000 | Plan for 80 days of LR piloting @ $250 per day |  | 0 | 20000
Intervention Emergency Recovery | 4000 | Will be supplemented by funds saved during vehicle downtime |  | 297.5 | 3702.5
Insurance | 7882 | Number from Mike Kelly, assuming payment is about the same as 2016 |  | 0 | 7882
Conference Travel | 3000 | International travel for Euro Glider conference |  | 0 | 3000
|  |  |  | 0 | 0
Spare parts/sensors |  |  |  |  | 0
SBE GPCTD + DO | 17500 | From 2015 quote, can steal gpctd from OA SV2 to cover |  | 0 | 17500
Two replacement Umbilicals | 74000 | planned for 2 new umbilicals, changed to v200 glider upgrade (includes umbilical) for both our SV3 vechiles |  | 97175 | -23175
replacement wing springs | 780 | from 2017 quote recommended replacment after 2 years at sea |  | 0 | 780
thrudder bushing repalcement | 1000 | from 2017 quote recommended replacment after 2 years at sea |  | 0 | 1000
replacement battery set | 1800 | recommended replacment after 2 years at sea |  | 1811.39 | -11.39
glider replacement frame | 3200 | damaged, I think it should be replaced |  | 0 | 3200
airmar | 1600 | keep failing we need spares |  | 0 | 1600
Spare thrudder upgrade to v200 | 0 |  |  | 4629.38 | -4629.38
0
Sensor Calibrations |  |  |  |  | 0
SBE GPCTD + DO | 6000 | $1500 X 4, from 2015 quote |  | 3130 | 2870
Wetlabs ECOPUCK | 2000 | $1000 x 2, from 2015 quote |  | 865 | 1135
0
Misc parts/tools/cables | 6000 | Estimated |  | 19825.08 | -13825.08
Total | 199962
|  |  | Total 2018 spending |  | Total diff | check sum
|  |  |  | 170933.35 | 29028.65 | 199962