## Wave Glider
2018 Ship/Equipment Requests
Oct 13, 2017 4:49:48 PM
Ship with RC hours | Project L1 - Name | Days | Transit Days | Proposed Date | Alternate Date | ROV & Crew | Transducer pole | Wave Glider Tiny | Wave Glider Sparky | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
Paragon | 300082 - DMO Support - Wave Glider | 8 | 0 |  |  |  |  | Yes | Yes | [5 empty] | Testing
Paragon | 901618 - Pelagic-Benthic Coupling | 1 | 0 |  |  |  |  | Yes |  |  | Less than 20nm | launch wave glider |  | Wave glider goes to Station M for 12 days
Paragon | 901618 - Pelagic-Benthic Coupling | 1 | 0 |  |  |  |  | Yes |  |  | Less than 20nm | launch wave glider |  | Wave glider goes to Station M for 12 days, coordinate with Smith lab flyer cruise
Paragon | 901618 - Pelagic-Benthic Coupling | 2 | 0 |  |  |  |  | Yes |  |  | Less than 20nm | recover wave glider
Paragon | 901513 - Targeted Sampling by AUVs | 1 | 0 |  |  |  |  | Yes
Paragon | 901608 - WG Sensor Payld Box & Tow | 3 | 0 |  |  |  |  | Yes
Paragon | 901817 - Marine Biogeochemistry Program | 4 | 0 | [5 empty] | Yes |  | Less than 20nm
Western Flyer | 901618 - Pelagic-Benthic Coupling | 8 | 2 |  | 10/10/2018 | ROV - Western Flyer | Yes | Yes |  | Winch, cold room, Ambient SW tables, suction samplers + carousel, benthic tool sled, Niskin bottles, Push cores, chain cutter, T-20 | Greater than 50nm | Rover position | approx 34N 122W
Western Flyer | 901618 - Pelagic-Benthic Coupling | 5 | 2 |  | 5/1/2018 | ROV - Western Flyer | Yes | Yes |  | Winch, cold room, Ambient SW tables, suction samplers + carousel, benthic tool sled, Niskin bottles, Push cores, chain cutter, T-20 | Greater than 50nm | Rover position | approx 34N 122W
| 901009 - CANON | 25 | 0 |  | 5/21/2018 |  |  | Yes | [6 empty] | Wave Glider deployments must be concurrent with Western Flyer ship time,
| 901009 - CANON | 25 | 0 |  | 9/3/2018 |  |  | Yes | [6 empty] | Wave Glider deployments must be concurrent with Western Flyer ship time,
| 901112 - Change in MB & CA Current | 50 | 0 |  |  |  |  | Yes | [5 empty] | On MBTS and other days
| Totals | 133