## RV Western Flyer
Level | Days | Transit Days | Proposed Date | Alternate Date | CTD 12hr | CTD 24hr | Mini - ROV | Mooring | ROV & Crew | Van_Chemical | Van_RAD | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
300060 - DMO Sppt-Pargn LABOR ONLY | 5 | 0 | 1/1/2019 | 7/1/2019 | [11 empty] | wave glider testing
300082 - DMO Support - Wave Glider | 5 | 0 | 2/1/2019 | 2/3/2019 | [11 empty] | wave glider testing
901809 - Deep Sea Bioinspiration | 8 | 0 | 8/26/2019 |  |  |  | Yes |  | Yes

## Paragon
Level | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV Crew | CTD winch | LRAUV | LRAUV LARS | Transducer pole | Wave Glider Tiny | Wave Glider Sparky | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
300082 - DMO Support - Wave Glider | 5 | 0 | 7/1/2019 | [7 empty] | Yes | Yes | [5 empty] | wave glider testing
901513 - Targeted Sampling by AUVs | 1 | 0 | [8 empty] | Yes | [6 empty] | Pilot: Brian Kieft
901608 - WG Sensor Payld Box & Tow | 5 | 0 | [8 empty] | Yes | [5 empty] | Would be good to have Jared and Chris to help work out towbody deployment | Engineering tests of the Towbody
901618 - Pelagic-Benthic Coupling | 1 | 0 | 3/25/2019 | 3/26/2019 | [6 empty] | Yes |  |  | Greater than 50nm | To Station M and Back | To Station M and Back | LAUNCH WAVE-GLIDER for 20-day deployment to Sta. M to communicate with Rover and SES. Rendezvous during Western Flyer cruise in Spring 2019. | WAVE GLIDER OUT FOR 20 days
901618 - Pelagic-Benthic Coupling | 1 | 0 | 4/15/2019 | 4/16/2019 | [6 empty] | Yes |  |  | Greater than 50nm | To Station M and Back | To Station M and Back | RECOVER WAVE-GLIDER from 20-day deployment to Sta. M to communicate with Rover and SES. Rendezvous during Western Flyer cruise in Spring 2019. | NOTE- all days on this request are anticipated to take only 0.5 days
901618 - Pelagic-Benthic Coupling | 1 | 0 | 7/1/2019 | 7/8/2019 | [6 empty] | Yes |  |  | Greater than 50nm | To Station M and Back | To Station M and Back | LAUNCH WAVE-GLIDER for 20-day deployment to Sta. M to communicate with Rover and SES. | WAVE GLIDER OUT FOR 20 days
901618 - Pelagic-Benthic Coupling | 1 | 0 | 7/22/2019 | 7/29/2019 | [6 empty] | Yes |  |  | Greater than 50nm | To Station M and Back | To Station M and Back | RECOVER WAVE-GLIDER from 20-day deployment to Sta. M to communicate with Rover and SES.
901618 - Pelagic-Benthic Coupling | 1 | 0 | 9/23/2019 | 10/7/2019 | [6 empty] | Yes |  |  | Greater than 50nm | To Station M and Back | To Station M and Back | LAUNCH WAVE-GLIDER for 20-day deployment to Sta. M to communicate with Rover and SES. Rendezvous during Western Flyer cruise in Fall 2019. | WAVE GLIDER OUT FOR 20 days
901618 - Pelagic-Benthic Coupling | 1 | 0 | 9/30/2019 | 10/21/2019 | [6 empty] | Yes |  |  | Greater than 50nm | To Station M and Back | To Station M and Back | RECOVER WAVE-GLIDER from 20-day deployment to Sta. M to communicate with Rover and SES. Rendezvous during Western Flyer cruises in Fall 2019.
901700 - 2017 Acoustical Ocean Eco | 6 | 0 | [9 empty] | Yes |  | Less than 20nm |  |  | Bracketing Ventana deployments
901800 - LRAUV Payload & Support | 4 | 0 | [5 empty] | Yes | Yes |  | Yes
901803 - Carbon Wave Glider Develo | 10 | 0 | 11/18/2019 | [8 empty] | Yes |  | Less than 20nm |  |  | Likely near end of 2019. | I've budgeted 10 days in the event that we are ready for multiple short deployments.
901817 - Marine Biogeochemistry Pr | 3 | 0 | 2/11/2019 | 2/18/2019 | [7 empty] | Yes |  | Less than 20nm |  |  | These are estimated dates. Actual dates will depend on CPF readiness and location.
901817 - Marine Biogeochemistry Pr | 3 | 0 | 4/8/2019 | 4/15/2019 | [7 empty] | Yes |  | Less than 20nm |  |  | These are estimated dates. Actual dates will depend on CPF readiness and location.
901817 - Marine Biogeochemistry Pr | 3 | 0 | 6/10/2019 | 6/17/2019 | [7 empty] | Yes |  | Less than 20nm |  |  | These are estimated dates. Actual dates will depend on CPF readiness and location.

## External Ship Equipment Only
Level | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV - Mapping | AUV - Mapping 2 | AUV - Other | AUV Crew | CTD 12hr | CTD 24hr | LRAUV | Mini - ROV | Wave Glider Tiny | Wave Glider Sparky | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
901009 - CANON | 60 | 0 | 6/1/2019 | [8 empty] | Yes |  | Yes | Yes | [5 empty] | dates are arbitrary, but mus coincide with RC and WF dates in June/Oct.
901009 - CANON | 60 | 0 | 10/1/2019 | [8 empty] | Yes |  | Yes | Yes
901023 - Continental Margin Proces | 7 | 0 | [12 empty] | Yes
901112 - Change in MB & CA Current | 8 | 0 | 1/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 2/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 3/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 4/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 5/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 6/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 7/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 8 | 0 | 8/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 9 | 0 | 9/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 9 | 0 | 10/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 9 | 0 | 11/1/2019 | [8 empty] | Yes |  | Yes
901112 - Change in MB & CA Current | 9 | 0 | 12/1/2019 | [8 empty] | Yes |  | Yes
100

## 2019 Wave Glider request summar
Project Number | Project Name | 2019 Wave Glider days requested | Requested dates | Comments
n/a | DMO Sonardyne Colab | 12 | Monthly | Monthly data downloads of Sonardayne AZA at MARS
300082 | 300082 DMO Support Wave Glider | 5 | n/a | Dates flexible, DMO testing
901009 | 901009 CANON | 60 | 6/1/2019 to 6/30/2019 | Month long deployment of 2 Wave Gliders coordinated with WF cruise
901009 | 901009 CANON | 60 | 10/1/2019 to 10/30/2019 | Month long deployment of 2 Wave Gliders coordinated with WF cruise
901023 | 901023 Continental Margins | 7 | n/a
901112 | 901112 Monterey Bay Time Series | 60 | Coordinated with RC timeseries cruises | Per conversation with Francisco reduced from 100 days to 60 days, assuming 12 monthly missions of 5 days each
901513 | 901513 Targeted Sampling by Autonomous Vehicles | 6 | n/a
901608 | 901608 Wave Glider Sensor Payload Box and Towbody Engineering | 5 | n/a
901618 | 901618 Pelagic-Benthic Coupling and the Carbon Cycle | 20 | 3/25/2019 to 4/15/2019
901618 | 901618 Pelagic-Benthic Coupling and the Carbon Cycle | 20 | 7/1/2019 to 7/21/2019
901618 | 901618 Pelagic-Benthic Coupling and the Carbon Cycle | 20 | 9/23/2019 to 10/13/2019
901700 | 901700 Acoustical Ocean Ecology | 42 | n/a | Three 14 day deployments are requested
901701 | 901701 Feasibility Study for Developing a Bio-Electric Field Sensor | 5 | n/a
901800 | 901800 LRAUV Payloads | 4 | n/a
901803 | 901803 Carbon Wave Glider Development | 10 | n/a
901817 | 901817 Marine Biogeochemistry Program | 7 | 2/11/2019 to 2/18/2019 | Dates are flexible
901817 | 901817 Marine Biogeochemistry Program | 7 | 4/8/2019 to 4/15/2019 | Dates are flexible
901817 | 901817 Marine Biogeochemistry Program | 7 | 6/10/2019 to 6/17/2019 | Dates are flexible
| 2019 Total Wave Glider requests | 357 | days