## SUMMARY
PLATFORM | Days Available | Days Requested
R/V WESTERN FLYER | 120 | 180
ROV DOC RICKETTS |  | 148
R/V RACHEL CARSON | 120 | 177.5
ROV VENTANA |  | 130
R/V PARAGON |  | 329.5 |  | 26
DORADO MAPPER 1 |  | 8 |  | 9
DORADO MAPPER 2 |  | 8 |  | 51
DORADO TRN |  | 4
DORADO i2Map |  | 54
DORADO GULPER |  | 24
CTD 12 HOUR |  | 13
CTD 24 HOUR |  | 24
MINI-ROV |  | 86
WAVEGLIDER |  | 321 | Impacts of Jupiter
LRAUV |  | 255

## RV Western Flyer (hidden)
Level |  | Days | Transit Days | Proposed Date | Alternate Date | CTD 12hr | CTD 24hr | Mini - ROV | Mooring | ROV & Crew | Van_Chemical | Van_RAD | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
TOTAL Days Requested | 0 | 0 | 0 |  |  |  | CTD - 24hr | Mini-ROV |  | ROV
901200 - AMP | Aquarium | 5 | 0 | 3/11/2020 | 3/18/2020 |  |  |  |  | Yes |  |  | MBA Elevator | Greater than 50nm |  |  | exact timing and location TBD. MBA is flexible on the former and is working on permits for shallower collections outside of Monterey Bay
901200 - AMP | Aquarium | 5 | 0 | 12/2/2020 | 12/9/2020 |  |  |  |  | Yes |  |  | MBA Elevator | Greater than 50nm |  |  | exact timing and location TBD. MBA is flexible on the former and is working on permits for shallower collections outside of Monterey Bay
901007 - Benthic Biology & Ecology | Barry | 5 | 0 | 6/15/2020 | 6/22/2020 |  |  |  |  | Yes |  |  |  | Between 20nm & 50nm |  |  | first two weeks of June are not possible | Sur Ridge (or Davidson Sea Mount)
901007 - Benthic Biology & Ecology | Barry | 5 | 0 | 10/5/2020 | 10/12/2020 |  |  |  |  | Yes |  |  |  | Between 20nm & 50nm |  |  | slightly earlier, September 29th on is possible but not Sept 27-28th | Sur Ridge (or Davidson Sea Mount)
901007 - Benthic Biology & Ecology | Barry | 5 | 0 | 12/7/2020 | 12/14/2020 |  |  |  |  | Yes |  |  |  | Between 20nm & 50nm |  |  |  | Sur Ridge
901007 - Benthic Biology & Ecology | Barry | 5 | 0 | 3/2/2020 | 3/9/2020 |  |  |  |  | Yes |  |  |  | Between 20nm & 50nm |  |  | not available last two weeks of Feb and do not want to go earlier (final 2019 cruise is in Mid Dec) | Sur Ridge (or Davidson Sea Mount)
901101 - Ocean Imaging | Caress | 4 | 0 | 2/18/2020 | 2/11/2020 | No | No | No | No | Yes | No | No | Low altitude survey | Less than 20nm | Extravert Cliff | Extravert Cliff | Ideally late February while Giancarlo Troni is visiting | Extravert Cliff
901101 - Ocean Imaging | Caress | 6 | 4 | 8/17/2020 | 8/17/2020 | No | No | No | No | Yes | No | No | Low altitude survey | Greater than 50nm | Axial Seamount | Axial Seamount | Moss Landing to Newport, after Carson NE Pac Mapping AUV expedition | Axial Seamount
901101 - Ocean Imaging | Caress | 8 | 2 | 8/28/2020 | 8/28/2020 | No | No | No | No | Yes | No | No | Low altitude survey | Greater than 50nm | Eel Slump | Eel Slump | Newport to Newport | Eel Slump
901101 - Ocean Imaging | Caress | 3 | 2 | 11/1/2020 | 11/15/2020 | No | No | No | No | Yes | No | No | Low altitude survey | Between 20nm & 50nm | 35d31.46'N 122d38.48'W | 35d31.46'N 122d38.48'W | Must be after Mapping AUV surveys of Octopus Garden | Octopus Garden Davidson Seamount
901009 - CANON | Chavez | 6 | 0 | 5/1/2020 | 5/15/2020 |  | Yes |  |  | YEs
901009 - CANON | Chavez | 6 | 0 | 10/1/2020 | 10/15/2020 |  | Yes |  |  | Yes
901808 - Free-Living & Symbiotic M | Goffredi/Orphan | 7 | 0 | 4/1/2020 | [5 empty] | Yes | [7 empty] | requested for So Cal expedition
901103 - Biodiversity & Biooptics | Haddock | 10 | 0 | 5/3/2020 | 5/11/2020 |  |  |  |  | Yes |  |  |  | Greater than 50nm |  |  | Cruise dates to be coordinated with other PIs
901103 - Biodiversity & Biooptics | Haddock | 7 | 0 | 10/1/2020 | 10/12/2020 |  |  |  |  | Yes |  |  |  | Greater than 50nm | MBARI | MBARI
901809 - Deep Sea Bioinspiration | Katija | 7 | 0 | 8/27/2020 | 8/31/2020 |  |  | Yes
901023 - Continental Margin Proces | Paul | 10 | 0 | 9/8/2020 | 9/15/2020 |  |  |  |  | Yes | Yes |  | vibracore + pushcores | Greater than 50nm | 44.497N 124.033W | 44.497N 124.033W | After Carson AUV mapping Paull legs
901023 - Continental Margin Proces | Paul | 10 | 3 | 9/19/2020 | 9/26/2020 |  |  |  |  | Yes | Yes |  | vibracore + pushcores | Greater than 50nm | 44.497N 124.033W | 36.83N 121.8 W | After Carson AUV mapping Paull legs
901220 - Midwater Ecology | Robison | 7 | 0 | 3/6/2020 |  | No | No | Yes | No | Yes | No | No |  | Between 20nm & 50nm | 36.70000/-122.05000 | 36.70000/-122.05000 |  | mini will be used to conduct shelf break transects for Leitner
901220 - Midwater Ecology | Robison | 7 | 0 | 6/11/2020 |  | No | No | Yes | No | Yes | No | No |  | Between 20nm & 50nm | 36.70000/-122.05000 | 36.70000/-122.05000 |  | mini will be used to conduct shelf break transects for Leitner
901220 - Midwater Ecology | Robison | 7 | 0 | 11/13/2020 |  | No | No | Yes | No | Yes | No | No |  | Between 20nm & 50nm | 36.70000/-122.05000 | 36.70000/-122.05000 |  | mini will be used to conduct shelf break transects for Leitner
901618 - Pelagic-Benthic Coupling | Smith | 5 | 2 | 5/1/2020 | 5/21/2020 |  |  |  | Yes | Yes |  |  |  | Greater than 50nm | Moss Landing | Station M | Rendezvous with Wave Glider | We plan to recover one mooring and deploy three
901618 - Pelagic-Benthic Coupling | Smith | 8 | 2 | 10/12/2020 | 10/1/2020 |  |  |  | Yes | Yes |  |  |  | Greater than 50nm | Moss Landing | Station M | Rendezvous with Wave Glider | We plan to recover and redeploy three moorings
901114 - E&D-Picophytoeukaryotes | Worden | 10 | 0 | 6/20/2020 | 7/20/2020 |  | Yes | No | No | Yes | No | Yes | no | Greater than 50nm | moss landing | moss landing | no
901114 - E&D-Picophytoeukaryotes | Worden | 5 | 0 | 9/20/2020 | 10/20/2020 |  | Yes | No | No | Yes | No | Yes | no | Greater than 50nm | moss landing | moss landing | no
300058 - DMO Spprt-WF -LABOR ONLY |  | 2 | 0 | 1/1/2020 | 2/1/2020 |  |  |  |  | Yes | [6 empty] | for testing
DAYS REQUESTED |  | 180
Days Available |  | 120 |  |  |  |  | 24 | 26 |  | 148
Difference |  | -60

## RV Rachel Carson (hidden)
Level |  | RC Hours | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV - Mapping | AUV - Mapping 2 | AUV - Other | AUV Crew | CTD | Mini - ROV | Mooring | ROV & Crew | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
901200 - AMP | Aquarium | 10 | 1 | 0 | 1/14/2020 | 2/4/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 3/11/2020 | 4/8/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 3/12/2020 | 3/13/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 4/16/2020 | 4/10/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 5/7/2020 | 5/9/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 5/13/2020 | 6/10/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 6/11/2020 | 6/6/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 1 | 1 | 0 | 7/8/2020 | 8/15/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 7/9/2020 | 7/12/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 8/6/2020 | 8/14/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 9/9/2020 | 10/17/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 9/17/2020 | 9/12/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 10/7/2020 | 10/10/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 10/7/2020 | 10/14/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | Makeup for 2021 GOC expedition in 2021
901200 - AMP | Aquarium | 10 | 1 | 0 | 10/8/2020 | 10/11/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | Makeup for 2021 GOC expedition in 2021
901200 - AMP | Aquarium | 10 | 1 | 0 | 10/8/2020 | 10/11/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | Makeup for 2021 GOC expedition in 2021 | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 11/11/2020 | 11/15/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 11/13/2020 | 11/15/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 11/14/2020 | 11/18/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | Makeup for 2021 GOC expedition in 2021 | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 11/18/2020 | 11/21/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 11/19/2020 | 11/22/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | Makeup for 2021 GOC expedition in 2021
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/3/2020 | 12/6/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/4/2020 | 12/5/2020 | [8 empty] | Yes | midwater sled | Between 20nm & 50nm |  |  | Makeup for 2021 GOC expedition in 2021
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/9/2020 | 12/12/2020 | [8 empty] | Yes | Benthic sled | Between 20nm & 50nm |  |  | exact date flexible | Benthic sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/10/2020 | 12/17/2020 | [8 empty] | Yes | benthic sled | Between 20nm & 50nm |  |  | exact date flexible | midwater sled
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/16/2020 | 12/23/2020 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | Contingency dates placed at end of year - MBA filming of sunken whale on day 0, 5, 15, 60, 120, and 180
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/17/2020 | 12/23/2020 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | Contingency dates placed at end of year - MBA filming of sunken whale on day 0, 5, 15, 60, 120, and 180
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/18/2020 | 12/23/2020 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | Contingency dates placed at end of year - MBA filming of sunken whale on day 0, 5, 15, 60, 120, and 180
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/19/2020 | 12/23/2020 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | Contingency dates placed at end of year - MBA filming of sunken whale on day 0, 5, 15, 60, 120, and 180
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/20/2020 | 12/23/2020 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | Contingency dates placed at end of year - MBA filming of sunken whale on day 0, 5, 15, 60, 120, and 180
901200 - AMP | Aquarium | 10 | 1 | 0 | 12/23/2020 | 12/26/2020 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | Contingency dates placed at end of year - MBA filming of sunken whale on day 0, 5, 15, 60, 120, and 180
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 1/15/2020 | 1/14/2020 | [8 empty] | Yes |  |  |  |  | This is start of a BRS deployment - the subsequent is ideally 5-7 days later - flexible in deployment/retrieval any time between 1/7 and 1/23 | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 1/21/2020 | 1/22/2020 | [8 empty] | Yes |  |  |  |  | This is the end of a BRS deployement | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 3/24/2020 | 3/25/2020 | [8 empty] | Yes |  |  |  |  | This is start of a BRS deployment - the subsequent is ideally 5-7 days later - would like to avoid this being to close to our WF cruise in the same month | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 3/30/2020 | 3/31/2020 | [8 empty] | Yes |  |  |  |  | This is the end of a BRS deployement | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 7/7/2020 | 7/14/2020 | [8 empty] | Yes | [5 empty] | benthic collection cruise (likely sponge ridge)
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 8/19/2020 | 8/18/2020 | [8 empty] | Yes |  |  |  |  | This is start of a BRS deployment - the subsequent is ideally 5-7 days later - earlier in August would work but not a deployment/retrieval that overlaps the first week of September | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 8/25/2020 | 8/24/2020 | [8 empty] | Yes |  |  |  |  | This is the end of a BRS deployement | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 11/13/2020 | 11/12/2020 | [8 empty] | Yes |  |  |  |  | This is start of a BRS deployment - the subsequent is ideally 5-7 days later | Within Monterey Bay - BRS
901007 - Benthic Biology & Ecology | Barry | 10 | 1 | 0 | 11/18/2020 | 11/19/2020 | [8 empty] | Yes |  |  |  |  | This is the end of a BRS deployement | Within Monterey Bay - BRS
901101 - Ocean Imaging | Caress | 10 | 1 | 0 | 3/1/2020 | 3/15/2020 | No | Yes | Yes | No | Yes | No | No | No | No |  | Less than 20nm | AUV Patch Test site | AUV Patch Test site | AUV testing and validation | AUV Patch Test site
901101 - Ocean Imaging | Caress | 10 | 1 | 0 | 4/1/2020 | 4/15/2020 | No | Yes | Yes | No | Yes | No | No | No | No |  | Less than 20nm | AUV Patch Test site | AUV Patch Test site | AUV testing and validation | AUV Patch Test site
901101 - Ocean Imaging | Caress | 10 | 1 | 0 | 5/1/2020 | 5/15/2020 | No | Yes | Yes | No | Yes | No | No | No | No |  | Less than 20nm | AUV Patch Test site | AUV Patch Test site | AUV testing and validation | AUV Patch Test site
901101 - Ocean Imaging | Caress | 10 | 1 | 0 | 6/1/2020 | 6/15/2020 | No | Yes | Yes | No | Yes | No | No | No | No |  | Less than 20nm | AUV Patch Test site | AUV Patch Test site | AUV testing and validation | AUV Patch Test site
901101 - Ocean Imaging | Caress | 24 | 3 | 2 | 4/15/2020 | 5/1/2020 |  | Yes | Yes | No | Yes | No | No | No | No | AMT | Between 20nm & 50nm | 35d31.46'N 122d38.48'W | 35d31.46'N 122d38.48'W | Before Western Flyer low altitude surveys requested in November | Octopus Garden Davidson Seamount
901009 - CANON | Chavez | 10 | 2 | 0 | 5/1/2020 | 5/15/2020 |  |  |  | Yes | Yes |  |  |  | Yes | [5 empty] | Carson days to coincide with WF CANON cruises, 'Other' AUV requested is i2MAP
901009 - CANON | Chavez | 10 | 2 | 0 | 10/1/2020 | 10/15/2020 |  |  |  | Yes | Yes |  |  |  | Yes | [5 empty] | Carson days to coincide with WF CANON cruises, 'Other' AUV requested is i2MAP
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 1/6/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 2/3/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 3/2/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 4/6/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 5/4/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 6/1/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 7/6/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 8/3/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 9/7/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 10/5/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 11/2/2020 | [6 empty] | Yes
901112 - Change in MB & CA Current | Chavez | 10 | 1 | 0 | 12/7/2020 | [6 empty] | Yes
300057 - Mooring Maint | Figurski | 10 | 1 | 0 | 8/3/2020 | 7/27/2020 | [7 empty] | Yes |  |  | Less than 20nm | M1 |  | M1 Turnaround - MOB previous day - offload following day
901103 - Biodiversity & Biooptics | Haddock | 10 | 1 | 0 | 4/21/2020 | [9 empty] | Yes |  | Less than 20nm | MBARI | 36.7 -122.05 |  | Midwater collections at Midwater1 site
901103 - Biodiversity & Biooptics | Haddock | 10 | 1 | 0 | 6/8/2020 | [9 empty] | Yes |  | Less than 20nm | MBARI | 36.7 -122.05 |  | Midwater collections at Midwater1 site
901103 - Biodiversity & Biooptics | Haddock | 10 | 1 | 0 | 7/20/2020 | [9 empty] | Yes |  | Less than 20nm | MBARI | 36.7 -122.05 |  | Midwater collections at Midwater1 site
901103 - Biodiversity & Biooptics | Haddock | 10 | 1 | 0 | 9/14/2020 | [9 empty] | Yes |  | Less than 20nm | MBARI | 36.7 -122.05 |  | Midwater collections at Midwater1 site
901103 - Biodiversity & Biooptics | Haddock | 10 | 1 | 0 | 11/16/2020 | [9 empty] | Yes |  | Less than 20nm | MBARI | 36.7 -122.05 | -122.05 | Midwater collections at Midwater1 site
901103 - Biodiversity & Biooptics | Haddock | 10 | 1 | 0 | 12/14/2020 | [9 empty] | Yes |  | Less than 20nm | MBARI | 36.7 -122.05 |  | Midwater collections at Midwater1 site
708141 - MINIONS | Katija | 10 | 1 | 0 | 5/29/2020 | 6/1/2020 | [6 empty] | Yes | [6 empty] | Add to Bioinspiration Lab's (901809) proposed summer dive series
901809 - Deep Sea Bioinspiration | Katija | 10 | 2 | 0 | 3/16/2020 | 3/23/2020 | [6 empty] | Yes | [7 empty] | Mesobot
901809 - Deep Sea Bioinspiration | Katija | 10 | 2 | 0 | 5/27/2020 | 6/1/2020 | [6 empty] | Yes | [7 empty] | Mesobot
901809 - Deep Sea Bioinspiration | Katija | 10 | 2 | 0 | 11/16/2020 | 11/23/2020 | [6 empty] | Yes | [7 empty] | Mesobot
901700 - 2017 Acoustical Ocean Eco | KBB | 10 | 1 | 0 | 3/3/2020 | 3/10/2020 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | 36.71; -122.2 | 36.71; -122.2 | Within +/- 2 weeks of ROV/AUV at Midwater 1 Feb 27, avoid week of 2/17 | i2MAP deployment/ROV video survey at MARS
901700 - 2017 Acoustical Ocean Eco | KBB | 10 | 1 | 0 | 3/4/2020 | 3/11/2020 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | 36.71; -122.2 | 36.71; -122.2 | Following deployment day | i2MAP recovery/ROV video survey
901700 - 2017 Acoustical Ocean Eco | KBB | 10 | 1 | 0 | 5/27/2020 | 5/20/2020 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | 36.71; -122.2 | 36.71; -122.2 | Within +/- 2 weeks of ROV/AUV at Midwater 1 Nov 4 | i2MAP deployment/ROV video survey at MARS
901700 - 2017 Acoustical Ocean Eco | KBB | 10 | 1 | 0 | 5/28/2020 | 5/21/2020 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | 36.71; -122.2 | 36.71; -122.2 | Following deployment day | i2MAP recovery/ROV video survey
901700 - 2017 Acoustical Ocean Eco | KBB | 10 | 1 | 0 | 11/10/2020 | 11/16/2020 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | 36.71; -122.2 | 36.71; -122.2 | Within - 2 weeks of ROV/AUV at Midwater 1 June 3 | i2MAP deployment/ROV video survey at MARS
901700 - 2017 Acoustical Ocean Eco | KBB | 10 | 1 | 0 | 11/11/2020 | 11/17/2020 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | 36.71; -122.2 | 36.71; -122.2 | Following deployment day | i2MAP recovery/ROV video survey
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 2/27/2020 |  |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | Midwater 1 |  | Day 1 of a 2-day series with Midwater Time Series
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 6/3/2020 |  |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | Midwater 1 |  | Day 1 of a 2-day series with Midwater Time Series
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 11/4/2020 |  |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm | Midwater 1 |  | Day 1 of a 2-day series with Midwater Time Series
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 5/19/2020 | 5/26/2020 |  |  |  | YES
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 5/21/2020 | 5/28/2020 |  |  |  | YES
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 10/20/2020 | 10/26/2020 |  |  |  | Yes
901807 - Next Gen Acoust Dorado | KBB | 10 | 1 | 0 | 10/22/2020 | 10/28/2020 |  |  |  | YEs
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 1/8/2020 | 1/15/2020 | [8 empty] | Yes |  |  |  |  | MARS Surveys | Must occur in first 1/4 or early 2nd 1/4. need not be continuous
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 1/22/2020 | 1/15/2020 | [8 empty] | Yes |  |  |  |  | MARS Surveys | Must occur in first 1/4 or early 2nd 1/4. need not be continuous
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 2/5/2020 | 1/15/2020 | [8 empty] | Yes |  |  |  |  | MARS Surveys | Must occur in first 1/4 or early 2nd 1/4. need not be continuous
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 2/19/2020 | 1/15/2020 | [8 empty] | Yes |  |  |  |  | MARS Surveys | Must occur in first 1/4 or early 2nd 1/4. need not be continuous
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 3/11/2020 | 1/15/2020 | [8 empty] | Yes |  |  |  |  | MARS Surveys | Must occur in first 1/4 or early 2nd 1/4. need not be continuous
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 3/25/2020 | 1/15/2020 | [8 empty] | Yes |  |  |  |  | MARS Surveys | Must occur in first 1/4 or early 2nd 1/4. need not be continuous
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 5/13/2020 | 5/20/2020 | [8 empty] | Yes |  |  |  |  | MARS Maintenance
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 8/18/2020 | 8/25/2020 | [8 empty] | Yes |  |  |  |  | MARS Maintenance
701127 - MARS O&M III | MARS | 12 | 1 | 0 | 11/15/2020 | 11/22/2020 | [8 empty] | Yes |  |  |  |  | MARS Maintenance
300079 - DMO Spprt-RC - LABOR ONLY | na | 10 | 2 | 0 | 1/1/2020 | 2/1/2020 | [8 empty] | Yes |  |  |  |  | For testing
901023 - Continental Margin Proces | Paull | 24 | 8 | 3 | 7/15/2020 | 7/22/2020 |  | Yes | Yes |  | Yes |  |  |  | No |  | Greater than 50nm | 36.83N 121.8 W | 44.497N 124.033W | Carson legs need to take place before WF Paull's legs. Hans Thomas needs to participate in all the proposed Carson legs and be able to join afterwards D Caress in his low altitude surveys in the WF
901023 - Continental Margin Proces | Paull | 24 | 8 | 0.5 | 7/24/2020 | 7/31/2020 |  | Yes | Yes |  | Yes |  |  |  | No |  | Greater than 50nm | 44.497N 124.033W | 44.497N 124.033W | Carson legs need to take place before WF Paull's legs. Hans Thomas needs to participate in all the proposed Carson legs and be able to join afterwards D Caress in his low altitude surveys in the WF
901023 - Continental Margin Proces | Paull | 24 | 8 | 3 | 8/3/2020 | 8/10/2020 |  | Yes | Yes |  | Yes |  |  |  | No |  | Greater than 50nm | 44.497N 124.033W | 36.83N 121.8 W | Carson legs need to take place before WF Paull's legs. Hans Thomas needs to participate in all the proposed Carson legs and be able to join afterwards D Caress in his low altitude surveys in the WF
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 1/8/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 2/5/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 4/8/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 5/14/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 7/8/2020 | 7/15/2020 | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 8/7/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 9/18/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 10/21/2020 | 10/28/2020 | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 12/9/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | Robison | 12 | 1 | 0 | 7/24/2020 |  | No | No | No | No | No | No | No | Yes | No |  | Between 20nm & 50nm | 36.54646800/-122.53900800 | 36.54646800/-122.53900800 | Needs to occur after our June WF cruise. Deep MRS mooring recovery (2978 m) | will be the last Deep MRS reco./repl.
901220 - Midwater Ecology | Robison | 12 | 1 | 0 | 9/22/2020 |  | No | No | No | No | No | No | No | Yes | No |  | Between 20nm & 50nm | 36.54646800/-122.53900800 | 36.54646800/-122.53900800 | Needs to occur prior to our Nov WF cruise. Deep MRS mooring deployment | will be the last Deep MRS reco./repl.
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 5/28/2020 |  | No |  | No | No | No | No | Yes | No | No |  | Less than 20nm | 36 42.000/ -122 -3.000 | 36 42.000/ -122 -3.000 | MESOBOT ops in conjunction with Katija (701136)
901220 - Midwater Ecology | Robison | 10 | 1 | 0 | 5/28/2020 |  | No |  | No | No | No | No | Yes | No | No |  | Less than 20nm | 36 42.000/ -122 -3.000 | 36 42.000/ -122 -3.000 | MESOBOT ops in conjunction with Katija (701136)
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 1/7/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 2/4/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 2/28/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | Recover i2Map AUV (no MRS). Deploy ADCP with ROV. Needs to occur prior to WF cruise in March | In conjunction w/KBB (901807)
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 4/7/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 5/13/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 6/4/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | Recover i2Map AUV (no MRS). Deploy ADCP with ROV. Needs to occur prior to WF cruise in June. | In conjunction w/KBB (901807)
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 7/7/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 8/6/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 9/17/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 10/20/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 11/6/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | Recover i2Map AUV (no MRS). Deploy ADCP with ROV. Needs to occur prior to WF cruise in Nov. | In conjunction w/KBB (901807)
901221 - Midwater Time Series | Robison | 10 | 1 | 0 | 12/8/2020 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.70000/-122.05000 | 36.74978300/-122.10698300 | i2Map AUV transects and MRS Deployment with ROV. | Comes first in 2-day series
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 4/6/2020 |  |  |  |  | Yes | Yes | [9 empty] | TRN testing - iceberg AUV (O/A sonars)
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 5/4/2020 |  |  |  |  | Yes | Yes | [9 empty] | TRN testing - iceberg AUV (O/A sonars)
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 6/1/2020 |  |  |  |  | Yes | Yes | [9 empty] | TRN testing - iceberg AUV (O/A sonars)
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 11/2/2020 |  |  |  |  | Yes | Yes | [9 empty] | TRN testing - iceberg AUV (O/A sonars)
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 2/3/2020 | [7 empty] | Yes | [7 empty] | mid-water tracking - coordinating with Kakani on multiday cruise
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 3/2/2020 | [9 empty] | Yes | [5 empty] | benthic surveys
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 7/6/2020 | [7 empty] | Yes | [7 empty] | mid-water tracking - coordinating with Kakani on multiday cruise
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 9/2/2020 | [9 empty] | Yes | [5 empty] | benthic surveys
600034 - Control Tech - Rock | Rock | 10 | 1 | 0 | 10/5/2020 | [7 empty] | Yes | [7 empty] | mid-water tracking - coordinating with Kakani on multiday cruise
901502 - Passive Acoustic Sensing | Ryan | 12 | 1 | 0 | 1/7/2020 | 1/14/2020 | [8 empty] | Yes |  | Less than 20nm | MARS |  |  | recovery of NPS hydrophone
901502 - Passive Acoustic Sensing | Ryan | 12 | 1 | 0 | 3/17/2020 | 3/24/2020 | [8 empty] | Yes |  | Less than 20nm | MARS |  |  | deployment of NPS hydrophone
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 3/2/2020 | 3/9/2020 | [8 empty] | Yes | [5 empty] | Hook up SES to MARS, deploy larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 3/3/2020 | 3/10/2020 | [8 empty] | Yes |  |  |  |  | Schedule one day after previous cruise | Recover larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 4/14/2020 | 4/21/2020 | [8 empty] | Yes | [5 empty] | Deploy larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 4/15/2020 | 4/22/2020 | [8 empty] | Yes |  |  |  |  | Schedule one day after previous cruise | Recover SES from MARS, Recover larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 7/1/2020 | 7/8/2020 | [8 empty] | Yes | [5 empty] | deploy larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 7/2/2020 | 7/9/2020 | [8 empty] | Yes |  |  |  |  | Schedule one day after previous cruise | recover larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 10/28/2020 | 10/29/2020 | [8 empty] | Yes |  |  |  |  | Work around Sta M Flyer cruise | deploy larval pump
901618 - Pelagic-Benthic Coupling | Smith | 12 | 1 | 0 | 10/29/2020 | 10/30/2020 | [8 empty] | Yes |  |  |  |  | Schedule one day after previous cruise. Work around Sta M Flyer cruise | recover larval pump
TOTAL Days Requested | 177.5 |  | 169 | 8.5
Days Available |  |  | 120 |  |  |  |  | Mapper 1 | Mapper 2 | TRN |  | CTD | Mini-ROV |  | ROV
|  |  | -49 |  |  |  |  | 8 | 8 | 4 |  | 13 | 9 |  | 130
i2Map
54

## RV Paragon (hidden)
Level | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV Crew | CTD winch | Transducer pole | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
300057 - Mooring Maint | 12 | 0 | 1/1/2020 | [9 empty] | As needed M1 maintenance trips
300082 - DMO Support - Wave Glider | 5 | 0 | 1/1/2020 | 1/2/2020 | [8 empty] | spread throughout year for testing
300083 - DMO Support - LRAUV | 10 | 0 | 1/1/2020 | 11/30/2020 | [9 empty] | LRAUV testing
600034 - Control Tech - Rock | 2 | 0 | 2/12/2020 | [5 empty] | Makai |  |  |  | 3 vehicle team for one day | From LRAUV Schedule
600034 - Control Tech - Rock | 2 | 0 | 4/15/2020 | [5 empty] | Makai |  |  |  | 3 vehicle team for one day | From LRAUV Schedule
600034 - Control Tech - Rock | 2 | 0 | 6/17/2020 | [5 empty] | Makai |  |  |  | 3 vehicle team for one day | From LRAUV Schedule
600034 - Control Tech - Rock | 2 | 0 | 8/12/2020 | [5 empty] | Makai |  |  |  | 3 vehicle team for one day | From LRAUV Schedule
600034 - Control Tech - Rock | 2 | 0 | 10/14/2020 | [5 empty] | Makai |  |  |  | 3 vehicle team for one day | From LRAUV Schedule
901009 - CANON | 3 | 0 | 5/1/2020 | 5/15/2020 | [8 empty] | Paragon days to coincide with other CANON deployments
901009 - CANON | 2 | 0 | 5/1/2020 | 5/15/2020 | [8 empty] | 6 LRAUVs requested for each CANON experiment. Deployments to coincide with CANON WF cruises | From LRAUV Schedule
901009 - CANON | 2 | 0 | 5/1/2020 | 5/15/2020 | [9 empty] | From LRAUV Schedule
901009 - CANON | 2 | 0 | 5/1/2020 | 5/15/2020 | [9 empty] | From LRAUV Schedule
901009 - CANON | 2 | 0 | 5/1/2020 | 5/15/2020 |  |  |  |  | Wave Glider - |  |  |  | To coincide with other CANON deployments | From Wave Glider Schedule
901009 - CANON | 3 | 0 | 10/1/2020 | 10/15/2020 | [8 empty] | Paragon days to coincide with other CANON deployments
901009 - CANON | 2 | 0 | 10/1/2020 | 10/15/2020 | [9 empty] | From LRAUV Schedule
901009 - CANON | 2 | 0 | 10/1/2020 | 10/15/2020 | [9 empty] | From LRAUV Schedule
901009 - CANON | 2 | 0 | 10/1/2020 | 10/15/2020 | [9 empty] | From LRAUV Schedule
901009 - CANON | 2 | 0 | 10/1/2020 | 10/15/2020 |  |  |  |  | Wave Glider - |  |  |  | To coincide with other CANON deployments | From Wave Glider Schedule
901103 - Biodiversity & Biooptics | 2 | 0 | 1/1/2020 | [5 empty] | Pontus |  |  |  | Dates will be coordinated with Chavez monthly LRAUV missions 901112 | From LRAUV Schedule
901103 - Biodiversity & Biooptics | 2 | 0 | 3/1/2020 | [5 empty] | Pontus |  |  |  | Dates will be coordinated with Chavez monthly LRAUV missions 901112 | From LRAUV Schedule
901103 - Biodiversity & Biooptics | 2 | 0 | 5/1/2020 | [5 empty] | Pontus |  |  |  | Dates will be coordinated with Chavez monthly LRAUV missions 901112 | From LRAUV Schedule
901103 - Biodiversity & Biooptics | 1 | 0 | 5/18/2020 | [6 empty] | Less than 20nm | MBARI |  | Specific date and dive location TBD, depending on weather | Blue-water SCUBA dive in conjuction with MBA
901103 - Biodiversity & Biooptics | 1 | 0 | 6/15/2020 | [6 empty] | Less than 20nm | MBARI |  | Specific date and dive location TBD, depending on weather | Blue-water SCUBA dive in conjuction with MBA
901103 - Biodiversity & Biooptics | 2 | 0 | 7/1/2020 | [5 empty] | Pontus |  |  |  | Dates will be coordinated with Chavez monthly LRAUV missions 901112 | From LRAUV Schedule
901103 - Biodiversity & Biooptics | 1 | 0 | 7/6/2020 | [6 empty] | Less than 20nm | MBARI |  | Specific date and dive location TBD, depending on weather | Blue-water SCUBA dive in conjuction with MBA
901103 - Biodiversity & Biooptics | 2 | 0 | 9/1/2020 | [5 empty] | Pontus |  |  |  | Dates will be coordinated with Chavez monthly LRAUV missions 901112 | From LRAUV Schedule
901103 - Biodiversity & Biooptics | 1 | 0 | 9/22/2020 | [6 empty] | Less than 20nm | MBARI |  | Specific date and dive location TBD, depending on weather | Blue-water SCUBA dive in conjuction with MBA
901103 - Biodiversity & Biooptics | 2 | 0 | 11/1/2020 | [5 empty] | Pontus |  |  |  | Dates will be coordinated with Chavez monthly LRAUV missions 901112 | From LRAUV Schedule
901103 - Biodiversity & Biooptics | 1 | 0 | 11/2/2020 | [6 empty] | Less than 20nm | MBARI |  | Specific date and dive location TBD, depending on weather | Blue-water SCUBA dive in conjuction with MBA
901103 - Biodiversity & Biooptics | 1 | 0 | 12/7/2020 | [6 empty] | Less than 20nm | MBARI |  | Specific date and dive location TBD, depending on weather | Blue-water SCUBA dive in conjuction with MBA
901112 - Change in MB & CA Current | 2 | 0 | 1/6/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 2/3/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 3/2/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 4/1/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 5/4/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 6/1/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 7/6/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 8/3/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 9/7/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 10/1/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 11/2/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 12/1/2020 | [5 empty] | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901112 - Change in MB & CA Current | 2 | 0 | 1/6/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 2/3/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 3/2/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 4/1/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 5/4/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 6/1/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 7/6/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 8/3/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 9/7/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 10/1/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 11/2/2020 |  | Yes
901112 - Change in MB & CA Current | 2 | 0 | 12/1/2020 |  | Yes
901200 - AMP | 2 | 0 | 3/5/2020 | 3/18/2020 | [5 empty] | Less than 20nm |  |  | need diving approval for videographers, LR AUV assistance, and captain
901200 - AMP | 2 | 0 | 4/8/2020 | 7/15/2020 |  |  |  |  | Any |  |  |  | payload flexible, object is to film LRAUV launch, underwater, and recovery. Underwater video by videographer on SCUBA | From LRAUV Schedule
901200 - AMP | 2 | 0 | 7/22/2020 | 8/12/2020 | [5 empty] | Between 20nm & 50nm |  |  | use depends on presence and location of albacore | Jared has expressed an interest in driving if he is available
901200 - AMP | 2 | 0 | 9/16/2020 | 10/7/2020 | [5 empty] | Between 20nm & 50nm |  |  | use depends on presence and location of albacore | Jared has expressed an interest in driving if available
901206 - Coastal Profiling Float | 0.5 | 0 | 2/12/2020
901206 - Coastal Profiling Float | 0.5 | 0 | 3/18/2020
901206 - Coastal Profiling Float | 0.5 | 0 | 4/14/2020
901206 - Coastal Profiling Float | 0.5 | 0 | 5/13/2020
901206 - Coastal Profiling Float | 2 | 0 | 6/1/2020 | 6/15/2020 |  |  |  |  | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901206 - Coastal Profiling Float | 4 | 0 | 6/10/2020 | [9 empty] | 4 individual days spread in June
901206 - Coastal Profiling Float | 0.5 | 0 | 8/18/2020
901206 - Coastal Profiling Float | 0.5 | 0 | 9/16/2020
901206 - Coastal Profiling Float | 2 | 0 | 9/28/2020 | 10/12/2020 |  |  |  |  | Wave Glider - |  |  |  |  | From Wave Glider Schedule
901206 - Coastal Profiling Float | 4 | 0 | 10/13/2020 | [9 empty] | 4 individual days spread in October
901206 - Coastal Profiling Float | 0.5 | 0 | 11/17/2020
901217 - Chemical Sensor Program | 4 | 0 | [11 empty] | dates unspecified
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 3/15/2020 | 3/22/2020
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 4/8/2020 | 4/15/2020
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 5/6/2020 | 5/13/2020
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 11/11/2020 | 11/18/2020
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 12/9/2020 | 12/10/2020
901502 - Passive Acoustic Sensing | 3 | 0 | 8/11/2020 | 8/18/2020 |  |  |  |  | drifting hydrophone
901513 - Targeted Sampling by AUVs | 2 | 0 | 2/4/2020 | [10 empty] | From LRAUV Schedule
901513 - Targeted Sampling by AUVs | 1 | 0 | 3/3/2020
901513 - Targeted Sampling by AUVs | 2 | 0 | 5/5/2020 | [10 empty] | From LRAUV Schedule
901513 - Targeted Sampling by AUVs | 2 | 0 | 8/6/2020 | [10 empty] | From LRAUV Schedule
901618 - Pelagic-Benthic Coupling | 2 | 0 | 1/15/2020 | 1/20/2020 |  |  |  |  | Wave Glider - |  |  |  | Prep Hotspot on shore for Loop and Cross | From Wave Glider Schedule
901618 - Pelagic-Benthic Coupling | 2 | 0 | 3/2/2020 | 3/9/2020 |  |  |  |  | Wave Glider - |  |  |  | To Station M communicate with Rover, | From Wave Glider Schedule
901618 - Pelagic-Benthic Coupling | 2 | 0 | 4/2/2020 | 3/26/2020 |  |  |  |  | Wave Glider - |  |  |  | MARS to communicate with SES at MARS and test loop and cross | From Wave Glider Schedule
901618 - Pelagic-Benthic Coupling | 2 | 0 | 4/27/2020 | 5/11/2020 |  |  |  |  | Wave Glider - |  |  |  | To Station M Communicate with SES, Rover, Rendesvous with Flyer at Station M. Test Loop and Cross | From Wave Glider Schedule
901618 - Pelagic-Benthic Coupling | 2 | 0 | 7/1/2020 | 7/8/2020 |  |  |  |  | Wave Glider - |  |  |  | To Station M Communicate with SES, Rover. | From Wave Glider Schedule
901618 - Pelagic-Benthic Coupling | 2 | 0 | 10/1/2020 | 9/28/2020 |  |  |  |  | Wave Glider - |  |  |  | To Station M Communicate with SES, Rover, Rendesvous with Flyer at Station M. | From Wave Glider Schedule
901700 - 2017 Acoustical Ocean Eco | 15 | 0 | [5 empty] | Yes |  | Less than 20nm |  |  | Periodic throughout year
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Triton |  |  |  | Spread through year, flexible on dates | From LRAUV Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Triton |  |  |  | Spread through year, flexible on dates | From LRAUV Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Triton |  |  |  | Spread through year, flexible on dates | From LRAUV Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Triton |  |  |  | Spread through year, flexible on dates | From LRAUV Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Triton |  |  |  | Spread through year, flexible on dates | From LRAUV Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Triton |  |  |  | Spread through year, flexible on dates | From LRAUV Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Wave Glider -Echosounder |  |  |  | Associated with MARS ROV dive | From Wave Glider Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Wave Glider -Echosounder |  |  |  | Associated with MARS ROV dive | From Wave Glider Schedule
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | [6 empty] | Wave Glider -Echosounder |  |  |  | Associated with MARS ROV dive | From Wave Glider Schedule
901713 - Nearshore FOCE | 5 | 0
901800 - LRAUV Payload & Support | 2 | 0 | 1/13/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 24 | 0 | 2/3/2020 | [10 empty] | Hobson, Kieft and Jones will captain
901800 - LRAUV Payload & Support | 2 | 0 | 2/10/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 3/16/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 4/13/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 4/13/2020 | [5 empty] | Wave Glider -Towbody |  |  |  | LRAUV towbody tow-out testing | From Wave Glider Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 5/11/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 5/11/2020 | [5 empty] | Wave Glider -Towbody |  |  |  | LRAUV towbody tow-out testing | From Wave Glider Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 6/8/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 6/15/2020 | [5 empty] | Wave Glider -Towbody |  |  |  | LRAUV towbody tow-out testing | From Wave Glider Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 7/20/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 8/17/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 9/14/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 9/14/2020 | [5 empty] | Wave Glider -Towbody |  |  |  | LRAUV towbody tow-out testing | From Wave Glider Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 10/12/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 11/9/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800 - LRAUV Payload & Support | 2 | 0 | 12/7/2020 | [5 empty] | Tethys |  |  |  |  | From LRAUV Schedule
901800.98 - Bioacoustic Payload | 2 | 0 | [11 empty] | From LRAUV Schedule
901800.98 - Bioacoustic Payload | 2 | 0 | [11 empty] | From LRAUV Schedule
901800.98 - Bioacoustic Payload | 2 | 0 | [11 empty] | From LRAUV Schedule
901800.98 - Bioacoustic Payload | 2 | 0 | [11 empty] | From LRAUV Schedule
901800.98 - Bioacoustic Payload | 2 | 0 | [11 empty] | From LRAUV Schedule
901803 - Carbon Wave Glider Develo | 2 | 0 | 9/14/2020 | [5 empty] | Wave Glider -Science + DIC-pCO2 instrumentat |  |  |  | Dates flexible | From Wave Glider Schedule
901803 - Carbon Wave Glider Develo | 2 | 0 | 10/12/2020 | [5 empty] | Wave Glider -Science + DIC-pCO2 instrumentat |  |  |  | Dates flexible | From Wave Glider Schedule
901803 - Carbon Wave Glider Develo | 2 | 0 | 11/2/2020 | [5 empty] | Wave Glider -Science + DIC-pCO2 instrumentat |  |  |  | Dates flexible | From Wave Glider Schedule
901803 - Carbon Wave Glider Develo | 5 | 0 | 11/17/2020 |  |  |  | Yes |  |  | Less than 20nm | Moss Landing | TBD within Bay | Flexible dates for 10 outings. | Collect discrete validation samples near carbon wave glider or M1 mooring.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
901817 - Marine Biogeochemistry Pr | 1 | 0 |  |  |  |  | Yes |  |  | Between 20nm & 50nm | Moss Landing | TBD | Dates are dependent on CPF deployments. | Outing to collect water for HPLC, Chla, and POC analysis.
902004 - Planktivore | 2 | 0 | 3/10/2020 | 3/25/2020 |  |  |  |  | Waveglider |  |  |  | Time is flexible and towbody can be combined with other waveglider usage
902004 - Planktivore | 2 | 0 | 3/10/2020 | 3/25/2020 |  |  |  |  | Wave Glider -towbody |  |  |  | Towbody can be a ride along on another deployment | From Wave Glider Schedule
902011 - Jupiter CO2 Collab | 4 | 0 | 2/3/2020
902011 - Jupiter CO2 Collab | 4 | 0 | 3/2/2020
902011 - Jupiter CO2 Collab | 4 | 0 | 4/6/2020
902011 - Jupiter CO2 Collab | 4 | 0 | 5/4/2020
DQ1938 - DHS Acoustics | 5 | 0 | 3/2/2020
AUV-CTD
TOTAL DAYS REQUESTED | 329.5 |  |  |  | 24

## External Ship & Equipment Only (hidden)
Level | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV - Mapping | AUV - Mapping 2 | AUV - Other | AUV Crew | CTD 12hr | CTD 24hr | Mini - ROV | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
600034 - Control Tech - Rock | 5 | 0 | 1/6/2020 | [8 empty] | Yes |  |  |  |  | testing in MBARI test tank | midwater tracking
600034 - Control Tech - Rock | 5 | 0 | 4/6/2020 | [8 empty] | Yes |  |  |  |  | testing in MBARI test tank | vision-based navigation (Aditya)
600034 - Control Tech - Rock | 5 | 0 | 9/7/2020 | [8 empty] | Yes |  |  |  |  | testing in MBARI test tank | wall station-keeping experiments
901103 - Biodiversity & Biooptics | 28 | 0 | 8/1/2020 | [8 empty] | Yes |  | Greater than 50nm | San Diego, CA |  | Exact dates for UNOLS cruise to be determined | NSF-funded UNOLS cruise from San Diego
901200 - AMP | 4 | 2 | 4/8/2020 | 4/15/2020 | [7 empty] | Yes |  |  |  |  | scheduling to depend on MiniROV and Fulmar availability
901200 - AMP | 4 | 2 | 10/7/2020 | 10/21/2020 | [7 empty] | Yes |  |  |  |  | scheduling to depend on MiniROV and Fulmar availability
TOTAL DAYS REQUESTED | [11 empty] | 51

## WaveGlider
Paragon Days | Level | PI | Days | Proposed Date | Alternate Date | Payload | Launch Point | Notes
| 300082 - DMO Support - Wave Glider | deleted | [5 empty] | testing
2 | 901009 - CANON | Chavez | 15 | 5/1/2020 | 5/15/2020 |  | Moss Landing | To coincide with other CANON deployments
2 | 901009 - CANON | Chavez | 15 | 10/1/2020 | 10/15/2020 |  | Moss Landing | To coincide with other CANON deployments
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 1/6/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 2/3/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 3/2/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 4/1/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 5/4/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 6/1/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 7/6/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 8/3/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 9/7/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 10/1/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 11/2/2020 |  |  | Moss Landing
2 | 901112 - Change in MB & CA Current | Chavez | 4 | 12/1/2020 |  |  | Moss Landing
2 | 901206 - Coastal Profiling Float | Johnson/Massion | 30 | 6/1/2020 | 6/15/2020 |  | Moss Landing
2 | 901206 - Coastal Profiling Float | Johnson/Massion | 30 | 9/28/2020 | 10/12/2020 |  | Moss Landing
2 | 901618 - Pelagic-Benthic Coupling | Smith/Huffard | 1 | 1/15/2020 | 1/20/2020 |  | Moss Landing | Prep Hotspot on shore for Loop and Cross
2 | 901618 - Pelagic-Benthic Coupling | Smith/Huffard | 20 | 3/2/2020 | 3/9/2020 |  | Moss Landing | To Station M communicate with Rover,
2 | 901618 - Pelagic-Benthic Coupling | Smith/Huffard | 3 | 4/2/2020 | 3/26/2020 |  | Moss Landing | MARS to communicate with SES at MARS and test loop and cross
2 | 901618 - Pelagic-Benthic Coupling | Smith/Huffard | 20 | 4/27/2020 | 5/11/2020 |  | Moss Landing | To Station M Communicate with SES, Rover, Rendesvous with Flyer at Station M. Test Loop and Cross
2 | 901618 - Pelagic-Benthic Coupling | Smith/Huffard | 20 | 7/1/2020 | 7/8/2020 |  | Moss Landing | To Station M Communicate with SES, Rover.
2 | 901618 - Pelagic-Benthic Coupling | Smith/Huffard | 20 | 10/1/2020 | 9/28/2020 |  | Moss Landing | To Station M Communicate with SES, Rover, Rendesvous with Flyer at Station M.
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 14 |  |  | Echosounder | Moss Landing | Associated with MARS ROV dive
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 14 |  |  | Echosounder | Moss Landing | Associated with MARS ROV dive
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 14 |  |  | Echosounder | Moss Landing | Associated with MARS ROV dive
2 | 901800 - LRAUV Payload & Support | Hobson | 2 | 4/13/2020 |  | Towbody | Moss Landing | LRAUV towbody tow-out testing
2 | 901800 - LRAUV Payload & Support | Hobson | 2 | 5/11/2020 |  | Towbody | Moss Landing | LRAUV towbody tow-out testing
2 | 901800 - LRAUV Payload & Support | Hobson | 2 | 6/15/2020 |  | Towbody | Moss Landing | LRAUV towbody tow-out testing
2 | 901800 - LRAUV Payload & Support | Hobson | 0 | 9/14/2020 |  | Towbody | Moss Landing | LRAUV towbody tow-out testing
2 | 901803 - Carbon Wave Glider Develo | Fassbender/McGill | 5 | 8/10/2020 |  | DIC-pCO2 instrumentation |  | Sensor integration at MBARI
2 | 901803 - Carbon Wave Glider Develo | Fassbender/McGill | 5 | 9/14/2020 |  | Science + DIC-pCO2 instrumentat | Moss Landing | Dates flexible
2 | 901803 - Carbon Wave Glider Develo | Fassbender/McGill | 5 | 10/12/2020 |  | Science + DIC-pCO2 instrumentat | Moss Landing | Dates flexible
2 | 901803 - Carbon Wave Glider Develo | Fassbender/McGill | 21 | 11/2/2020 |  | Science + DIC-pCO2 instrumentat | Moss Landing | Dates flexible
2 | 901809 - Deep Sea Bioinspiration | Katija/Daniels | 5 | 8/24/2020 | 8/31/2020 | track an underwater asset that has a Benthos modem
2 | 901809 - Deep Sea Bioinspiration | Katija/Daniels | 5 | 11/9/2020 | 11/16/2020 | track an underwater asset that has a Benthos modem
2 | 901809.XX - New Capital | delete | 0 | na | na | na | na | na
2 | 901809.XX - New Capital | delete | 0 | na | na | na | na | na
2 | 902004 - Planktivore | Chavez/Maughan | 5 | 3/10/2020 | 3/25/2020 | towbody | Moss Landing | Towbody can be a ride along on another deployment
76 | TOTAL DAYS REQUESTED |  | 321

## LRAUV
Paragon Days | Level | PI | Days | Proposed Date | Alternate Date | Payload | Vehcile | Launch Point | Notes
0 | 300079 - DMO Spprt-RC - LABOR ONLY | deleted | 0 | na |  | na | na | na | testing
0 | 300083 - DMO Support - LRAUV | deleted | 0 | na |  | na | na | na | testing
2 | 600034 - Control Tech - Rock | Rock | 1 | 2/12/2020 |  | TRN | Tethys | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 2/12/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 2/12/2020 |  | TRN | Pontus | Moss Landing | 3 vehicle team for one day
2 | 600034 - Control Tech - Rock | Rock | 1 | 4/15/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 4/15/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 4/15/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
2 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
2 | 600034 - Control Tech - Rock | Rock | 1 | 8/12/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
2 | 600034 - Control Tech - Rock | Rock | 1 | 10/14/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
0 | 600034 - Control Tech - Rock | Rock | 1 | 6/17/2020 |  | TRN | Makai | Moss Landing | 3 vehicle team for one day
2 | 901009 - CANON | Chavez | 8 | 5/1/2020 | 5/15/2020 |  |  | Moss Landing | 6 LRAUVs requested for each CANON experiment. Deployments to coincide with CANON WF cruises
| 901009 - CANON | Chavez | 8 | 5/1/2020 | 5/15/2020 |  |  | Moss Landing
2 | 901009 - CANON | Chavez | 8 | 5/1/2020 | 5/15/2020 |  |  | Moss Landing
| 901009 - CANON | Chavez | 8 | 5/1/2020 | 5/15/2020 |  |  | Moss Landing
2 | 901009 - CANON | Chavez | 8 | 5/1/2020 | 5/15/2020 |  |  | Moss Landing
| 901009 - CANON | Chavez | 8 | 5/1/2020 | 5/15/2020 |  |  | Moss Landing
2 | 901009 - CANON | Chavez | 8 | 10/1/2020 | 10/15/2020 |  |  | Moss Landing
| 901009 - CANON | Chavez | 8 | 10/1/2020 | 10/15/2020 |  |  | Moss Landing
2 | 901009 - CANON | Chavez | 8 | 10/1/2020 | 10/15/2020 |  |  | Moss Landing
| 901009 - CANON | Chavez | 8 | 10/1/2020 | 10/15/2020 |  |  | Moss Landing
2 | 901009 - CANON | Chavez | 8 | 10/1/2020 | 10/15/2020 |  |  | Moss Landing
| 901009 - CANON | Chavez | 8 | 10/1/2020 | 10/15/2020 |  |  | Moss Landing
2 | 901103 - Biodiversity & Biooptics | Haddock/Christianson | 2 | 2020-01-01 |  | UBAT | Pontus | Moss Landing | Dates will be coordinated with Chavez monthly LRAUV missions 901112
2 | 901103 - Biodiversity & Biooptics | Haddock/Christianson | 2 | 2020-03-01 |  | UBAT | Pontus | Moss Landing | Dates will be coordinated with Chavez monthly LRAUV missions 901112
2 | 901103 - Biodiversity & Biooptics | Haddock/Christianson | 2 | 2020-05-01 |  | UBAT | Pontus | Moss Landing | Dates will be coordinated with Chavez monthly LRAUV missions 901112
2 | 901103 - Biodiversity & Biooptics | Haddock/Christianson | 2 | 2020-07-01 |  | UBAT | Pontus | Moss Landing | Dates will be coordinated with Chavez monthly LRAUV missions 901112
2 | 901103 - Biodiversity & Biooptics | Haddock/Christianson | 2 | 2020-09-01 |  | UBAT | Pontus | Moss Landing | Dates will be coordinated with Chavez monthly LRAUV missions 901112
2 | 901103 - Biodiversity & Biooptics | Haddock/Christianson | 2 | 2020-11-01 |  | UBAT | Pontus | Moss Landing | Dates will be coordinated with Chavez monthly LRAUV missions 901112
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 1/1/2020 |  |  | Daphne |  | Dates will be coordinated with Haddock 901103
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 2/1/2020 |  |  | Daphne
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 3/1/2020 |  |  | Daphne |  | Dates will be coordinated with Haddock 901103
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 4/1/2020 |  |  | Daphne
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 5/1/2020 |  |  | Daphne |  | Dates will be coordinated with Haddock 901103
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 6/1/2020 |  |  | Daphne
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 7/1/2020 |  |  | Daphne |  | Dates will be coordinated with Haddock 901103
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 8/1/2020 |  |  | Daphne
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 9/1/2020 |  |  | Daphne |  | Dates will be coordinated with Haddock 901103
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 10/1/2020 |  |  | Daphne
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 11/1/2020 |  |  | Daphne |  | Dates will be coordinated with Haddock 901103
2 | 901112 - Change in MB & CA Current | Chavez | 3 | 12/1/2020 |  |  | Daphne
2 | 901200 - AMP | Matsumoto | 2 | 4/8/2020 | 7/15/2020 |  | Any | Moss Landing | payload flexible, object is to film LRAUV launch, underwater, and recovery. Underwater video by videographer on SCUBA
2 | 901513 - Targeted Sampling by AUVs | Zhang | 2 | 2/4/2020 |  | Standard |  | Moss Landing
2 | 901513 - Targeted Sampling by AUVs | Zhang | 2 | 5/5/2020 |  | Standard |  | Moss Landing
2 | 901513 - Targeted Sampling by AUVs | Zhang | 2 | 8/6/2020 |  | Standard |  | Moss Landing
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 4 |  |  | Echosounder | Triton | Moss Landing | Spread through year, flexible on dates
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 4 |  |  | Echosounder | Triton | Moss Landing | Spread through year, flexible on dates
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 4 |  |  | Echosounder | Triton | Moss Landing | Spread through year, flexible on dates
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 7 |  |  | Echosounder | Triton | Moss Landing | Spread through year, flexible on dates
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 7 |  |  | Echosounder | Triton | Moss Landing | Spread through year, flexible on dates
2 | 901700 - 2017 Acoustical Ocean Eco | KBB/Waluk | 7 |  |  | Echosounder | Triton | Moss Landing | Spread through year, flexible on dates
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 1/13/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 2/10/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 3/16/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 4/13/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 5/11/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 6/8/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 7/20/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 8/17/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 9/14/2020 |  | Tethys Dev | Tethys | Moss Landing
0 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 9/14/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 10/12/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 11/9/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800 - LRAUV Payload & Support | Hobson/Jones | 2 | 12/7/2020 |  | Tethys Dev | Tethys | Moss Landing
2 | 901800.98 - Bioacoustic Payload | Hobson/Jones | 2 |  |  | Bioacoustics |  | Moss Landing
2 | 901800.98 - Bioacoustic Payload | Hobson/Jones | 2 |  |  | Bioacoustics |  | Moss Landing
2 | 901800.98 - Bioacoustic Payload | Hobson/Jones | 4 |  |  | Bioacoustics |  | Moss Landing
2 | 901800.98 - Bioacoustic Payload | Hobson/Jones | 4 |  |  | Bioacoustics |  | Moss Landing
2 | 901800.98 - Bioacoustic Payload | Hobson/Jones | 7 |  |  | Bioacoustics |  | Moss Landing
2 | 901809 - Deep Sea Bioinspiration | Katiga/Daniels | 5 | 8/24/2020 | 8/31/2020
2 | 901809 - Deep Sea Bioinspiration | Katiga/Daniels | 5 | 11/9/2020 | 11/16/2020 |  | Triton
| Sub-total |  | 255
| Tethys |  | -26
116 | TOTAL |  | 229