## Wave Glider
Level | Days | Proposed Date | Alternate Date | Payload | Launch Point | Notes
901009 - CANON | 15 | 5/10/2021 | 5/17/2021
901112 - Change in MB & CA Current | 4 | 1/4/2021
901112 - Change in MB & CA Current | 4 | 2/1/2021
901112 - Change in MB & CA Current | 4 | 3/1/2021
901112 - Change in MB & CA Current | 4 | 4/1/2021
901112 - Change in MB & CA Current | 4 | 5/3/2021
901112 - Change in MB & CA Current | 4 | 6/1/2021
901112 - Change in MB & CA Current | 4 | 7/1/2021
901112 - Change in MB & CA Current | 4 | 8/2/2021
901112 - Change in MB & CA Current | 4 | 9/1/2021
901112 - Change in MB & CA Current | 4 | 10/1/2021
901112 - Change in MB & CA Current | 4 | 11/1/2021
901112 - Change in MB & CA Current | 4 | 12/1/2021
901206 - Coastal Profiling Float | 30 | 4/14/2021
901206 - Coastal Profiling Float | 30 | 10/6/2021
901513 - Targeted Sampling by AUVs | 3 | 3/1/2021 | 3/8/2021 | Hotspot | Moss Landing
901513 - Targeted Sampling by AUVs | 4 | 6/14/2021 | 6/21/2021 | Hotspot | Moss Landing
901618 - Pelagic-Benthic Coupling | 20 | 3/1/2021 | 3/15/2021 | Same as prior trips to Station M | Moss Landing | Requesting Four 20-day deployments to Sta. M in Mar, May, July, Oct 2021 to communicate with Rover and SES, and provide contemporaneous surface data with Western Flyer cruise. Rendezvous during Western Flyer cruise in October 2021. This includes 1 day at station M to conduct Loop and Cross search procedure.
901618 - Pelagic-Benthic Coupling | 20 | 5/3/2021 | 5/17/2021 | Same as prior trips to Station M | Moss Landing
901618 - Pelagic-Benthic Coupling | 20 | 7/1/2021 | 7/15/2021 | Same as prior trips to Station M | Moss Landing
901618 - Pelagic-Benthic Coupling | 20 | 10/1/2021 | 10/15/2021 | Same as prior trips to Station M | Moss Landing
901700 - 2017 Acoustical Ocean Eco | 18 | 2/10/2021 |  | Bioacoustics | Moss Landing | To be coordinated with Midwater Time Series Cruise
901700 - 2017 Acoustical Ocean Eco | 18 | 5/13/2021 |  | Bioacoustics | Moss Landing | To be coordinated with Midwater Time Series Cruise
901700 - 2017 Acoustical Ocean Eco | 18 | 8/12/2021 |  | Bioacoustics | Moss Landing | To be coordinated with Midwater Time Series Cruise
901700 - 2017 Acoustical Ocean Eco | 18 | 11/11/2021 |  | Bioacoustics | Moss Landing | To be coordinated with Midwater Time Series Cruise
901805 - Coastal Biogeochemical Se | 14 | 4/1/2021 |  | pCO2 (Tiny) | Moss Landing | TIming is flexible; will likely be combined with MBTS
901805 - Coastal Biogeochemical Se | 14 | 10/1/2021 |  | pCO2 (Tiny) | Moss Landing | TIming is flexible; will likely be combined with MBTS
901809 - Deep Sea Bioinspiration | 5 | 5/17/2021 | 5/24/2021 |  |  | In conjunction with Paragon, LRAUV and Rachel Carson days
901809 - Deep Sea Bioinspiration | 5 | 10/25/2021 | 10/18/2021 |  |  | In conjunction with Paragon, LRAUV and Rachel Carson days
901913 - Wet Wifi | 2 | 8/4/2021 | 8/2/2021 | OceanComm Modem | Moss Landing | With LRAUV
901913 - Wet Wifi | 3 | 8/10/2021 | 8/11/2021 | OceanComm Modem | Moss Landing | With LRAUV
901913 - Wet Wifi | 5 | 8/26/2021 | 7/27/2021 | OceanComm Modem | Moss Landing | With LRAUV
901913 - Wet Wifi | 7 | 9/15/2021 | 9/16/2021 | OceanComm Moem | Moss Landing | With LRAUV
TOTAL DAYS | 337
Notes:
Aug 28, 2020 10:45:05 AM PDT
Confidential Information. Do not distribute without permission.

## Information about this Sheet
Chris Di Salvo at Monterey Bay Aquarium Research Institute
Sheet | Wave Glider
Level | MBARI
Version | Budget 2021