## 2022_RV Western Flyer
Level | Days | Transit Days | Proposed Date | Alternate Date | CTD 12hr | CTD 24hr | Mini - ROV | Mooring | ROV & Crew | Van_Chemical | Van_RAD | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
901009 - CANON | 5 | 0 | 9/7/2021
901200 - AMP (use 910001.03) | 5 | 0 | 1/10/2022 | 1/17/2022 |  |  |  |  | Yes |  |  | benthic elevator and midwater trawl | Between 20nm & 50nm |  |  |  | telepresence is requested for two days of the five
901112 - Change in MB & CA Current | 3 |  | 2/3/2022 | 2/1/2022 | [9 empty] | Gulf of California |  |  | Specific equipment requests TBD
901714 - Divers & Evo Midwtr Anima | 10 |  | 2/14/2022 | 2/27/2022 |  |  |  |  | Yes |  |  | winch and trash wire for midwater trawl net | Greater than 50nm | La Paz | La Paz | Max 600 km, work planned between La Paz and Guaymas Basin, alternate date would be much more difficult to manage. | I am requesting a 10-day Western Flyer/Doc Ricketts midwater cruise. My project requires both deep ROV and midwater trawl collections, with ROV being the priority. This dive time will also provide ship time access for the following regular MBARI staff: Kakani Katija, Joost Daniels, Astrid Leitner, and Kyra Schlining is requested to participate as well. Also, past interns Vanessa Stenvers, Freya Goetz, and Karen Osborn.
901220 - Midwater Ecology | 10 | 0 | 2/27/2022 |  | No | No | No | No | Yes | No | No |  | Greater than 50nm | 24° 13 N/109° 36 W | 26° 11 N/110° 36 W | Robison leg #3 Gulf of California, begins Cerralvo Bank, extends to Carmen Basin, return. | Four (4) days of Telepresence requested
901103 - Biodiversity & Biooptics | 10 |  | 3/12/2022 | 3/13/2022 |  |  |  |  | Yes |  |  |  | Greater than 50nm | Gulf of California
901007 - Benthic Biology & Ecology | 10 |  | 3/25/2022 | [13 empty] | GOC
901101 - Seafloor Mapping | 10 | 0 | 4/7/2022 | [5 empty] | Yes |  |  | AMT for tide sensor |  |  |  | 2022 MBARI GOC WF Leg 6 | Telepresence desired
901808 - Free-Living & Symbiotic M | 10 |  | 4/20/2022 | [5 empty] | Yes |  |  |  | Greater than 50nm | La Paz | La Paz | Leg previously scheduled for April 20-29, 2022. Would like to keep same time frame.
901112 - Change in MB & CA Current | 3 |  | 5/5/2022 | 5/1/2022 | [9 empty] | Gulf of California |  |  | Specific equipment requests TBD
901200 - AMP (use 910001.03) | 5 | 0 | 6/20/2022 | 7/11/2022 |  |  |  |  | Yes |  |  | benthic elevator and midwater trawl | Between 20nm & 50nm |  |  |  | telepresence is requested for two days of the five
901809 - Deep Sea Bioinspiration | 7 |  | 7/11/2022 | [5 empty] | Yes | [7 empty] | Utilize DeepPIV/EyeRIS hardware, ML-Tracking algorithms, ROVVR, and other experiments with DOIG collaborators.
901007 - Benthic Biology & Ecology | 5 |  | 7/18/2022 | 7/25/2022 |  |  |  |  | Yes |  |  |  | Between 20nm & 50nm |  |  | We have requested these WF dates and a series of 12h Carson days (6) as contingency to access to the WF in summer of 2022- | Telepresence - Sur Ridge and Davidson Seamount
901103 - Biodiversity & Biooptics | 7 |  | 8/3/2022 | 8/9/2022 |  |  |  |  | Yes |  |  |  | Greater than 50nm | 36.1, -124.5 | 35.5, -124.0 | we'd love late summer to be able to also blue water scuba dive | this is a local Monterey Bay area cruise that we can collaborate with MBA on
901805 - Coastal Biogeochemical Se | 5 | 1 | 8/8/2022 | 7/11/2022 |  | Yes |  |  |  |  | Yes | Surface net tow | Greater than 50nm | MBARI | MBARI | Flexible after GoC expedition | Will hold station at 67_90, 67_70, or 67_60 based on SST and Chl surface satellite maps
901220 - Midwater Ecology | 7 | 0 | 8/15/2022 |  | No | No | No | No | Yes | No | No |  | Between 20nm & 50nm | 36.70000/-122.05000 | 36.70000/-122.05000 |  | Two (2) days of Telepresence requested
901618 - Pelagic-Benthic Coupling | 8 | 2 | 9/20/2022 | 9/12/2022 | Yes |  |  | Yes | Yes |  |  | Elevator | Greater than 50nm | Moss Landing | Station M | Rendezvous with Wave Glider, Last cruise before Western Flyer retirement
901220 - Midwater Ecology | 0 | 0 | 11/14/2022 |  | No | No | No | No | Yes | No | No |  | Between 20nm & 50nm | 36.70000/-122.05000 | 36.70000/-122.05000 |  | Two (2) days of Telepresence requested
| 120 | 3
Notes:
Sep 3, 2021 9:43:10 AM PDT
Confidential Information. Do not distribute without permission.

## 2022_RV Rachel Carson
Level | RC Hours | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV - Mapping | AUV - Mapping 2 | AUV - Other | AUV Crew | CTD | Mini - ROV | Mooring | ROV & Crew | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
300057 - Mooring Maint | 10 | 1 | 0 | 7/15/2022 | 8/15/2022 | [7 empty] | Yes |  |  |  | M1
600034 - Control Tech - Rock | 10 | 1 |  | 4/27/2022 | 5/4/2022 | [8 empty] | Yes | [5 empty] | control system testing and ROV TRN with Caress
600034 - Control Tech - Rock | 10 | 1 |  | 4/28/2022 | 4/5/2022 |  | Yes |  |  | Yes | [9 empty] | schedule to be contiguous with Caress AUV days
600034 - Control Tech - Rock | 10 | 1 |  | 8/3/2022 | 8/17/2022 |  | Yes |  |  | Yes | [9 empty] | schedule to be contiguous with Caress AUV days
600034 - Control Tech - Rock | 10 | 1 |  | 8/10/2022 | 8/24/2022 | [8 empty] | Yes | [5 empty] | control system testing and ROV TRN with Caress
600034 - Control Tech - Rock | 10 | 1 |  | 11/2/2022 | 11/23/2022 | [8 empty] | Yes | [5 empty] | control system testing and ROV TRN with Caress
600034 - Control Tech - Rock | 10 | 0 |  | 3/15/2022 | [7 empty] | Yes | [7 empty] | schedule to be contiguous with Katija’s mid-water tracking cruises
600034 - Control Tech - Rock | 10 | 0 |  | 6/15/2022 | [7 empty] | Yes | [7 empty] | schedule to be contiguous with Katija’s mid-water tracking cruises
600034 - Control Tech - Rock | 10 | 0 |  | 9/15/2022 | [7 empty] | Yes | [7 empty] | schedule to be contiguous with Katija’s mid-water tracking cruises
701147 - MARS O&M IV | 12 | 2 |  | 8/16/2022 | 8/23/2022 | [8 empty] | Yes
701147 - MARS O&M IV | 12 | 1 |  | 3/16/2022 | 3/17/2022 | [8 empty] | Yes |  |  |  |  | 12hr day
701147 - MARS O&M IV | 12 | 1 |  | 10/19/2022 | 10/26/2022 | [8 empty] | Yes
901007 - Benthic Biology & Ecology | 10 | 1 | 0 | 5/10/2022 | [9 empty] | Yes |  | Less than 20nm |  |  | BRS Cruise 1 - Day 1 - We are trying to schedule 3 paired cruises, 7 days apart, for BRS deployments | Telepresence - BRS/Camera Testing/Transects/Other
901007 - Benthic Biology & Ecology | 10 | 1 | 0 | 5/17/2022 | [9 empty] | Yes |  | Less than 20nm |  |  | BRS Cruise 1 - Day 2 | Telepresence - BRS/Camera Testing/Transects/Other
901007 - Benthic Biology & Ecology | 12 | 1 | 0 | 6/7/2022 | [9 empty] | Yes |  | Between 20nm & 50nm |  |  | Requesting 6 12 Carson Days over June/July 2022 if we do not have a Western Flyer Cruise in July 2022 - Schedule is flexible | Telepresence - Sur Ridge - Deep Sea Coral Observatory
901007 - Benthic Biology & Ecology | 12 | 1 | 0 | 6/14/2022 | [9 empty] | Yes |  | Between 20nm & 50nm |  |  | Requesting 6 12 Carson Days over June/July 2022 if we do not have a Western Flyer Cruise in July 2022 - Schedule is flexible | Telepresence - Sur Ridge - Deep Sea Coral Observatory
901007 - Benthic Biology & Ecology | 12 | 1 | 0 | 6/21/2022 | [9 empty] | Yes |  | Between 20nm & 50nm |  |  | Requesting 6 12 Carson Days over June/July 2022 if we do not have a Western Flyer Cruise in July 2022 - Schedule is flexible | Telepresence - Sur Ridge - Deep Sea Coral Observatory
901007 - Benthic Biology & Ecology | 12 | 1 | 0 | 6/28/2022 | [9 empty] | Yes |  | Between 20nm & 50nm |  |  | Requesting 6 12 Carson Days over June/July 2022 if we do not have a Western Flyer Cruise in July 2022 - Schedule is flexible | Telepresence - Sur Ridge - Deep Sea Coral Observatory
901007 - Benthic Biology & Ecology | 12 | 1 | 0 | 7/12/2022 | [9 empty] | Yes |  | Between 20nm & 50nm |  |  | Requesting 6 12 Carson Days over June/July 2022 if we do not have a Western Flyer Cruise in July 2022 - Schedule is flexible | Telepresence - Sur Ridge - Deep Sea Coral Observatory
901007 - Benthic Biology & Ecology | 12 | 1 | 0 | 7/19/2022 | [9 empty] | Yes |  | Between 20nm & 50nm |  |  | Requesting 6 12 Carson Days over June/July 2022 if we do not have a Western Flyer Cruise in July 2022 - Schedule is flexible | Telepresence - Sur Ridge - Deep Sea Coral Observatory
901007 - Benthic Biology & Ecology | 10 | 1 | 0 | 10/11/2022 | [9 empty] | Yes |  | Less than 20nm |  |  | BRS Cruise 2 - Day 1 - We are trying to schedule 3 paired cruises, 7 days apart, for BRS deployments | Telepresence - BRS/Camera Testing/Transects/Other
901007 - Benthic Biology & Ecology | 10 | 1 |  | 10/18/2022 | [9 empty] | Yes |  | Less than 20nm |  |  | BRS Cruise 2 - Day 2 | Telepresence - BRS/Camera Testing/Transects/Other
901007 - Benthic Biology & Ecology | 10 | 1 |  | 11/9/2022 | [9 empty] | Yes |  | Less than 20nm |  |  | BRS Cruise 3 - Day 1 - We are trying to schedule 3 paired cruises, 7 days apart, for BRS deployments | Telepresence - BRS/Camera Testing/Transects/Other
901007 - Benthic Biology & Ecology | 10 | 1 |  | 11/16/2022 | [9 empty] | Yes |  | Less than 20nm |  |  | BRS Cruise 3 - Day 2 | Telepresence - BRS/Camera Testing/Transects/Other
901101 - Seafloor Mapping | 24 | 8 | 0 | 1/21/2022 |  |  | Yes | Yes |  | Yes |  |  |  |  | AMT for tide sensor |  |  |  |  | 2022 MBARI GOC RC Leg 1
901101 - Seafloor Mapping | 24 | 8 | 0 | 2/1/2022 |  |  | Yes | Yes |  | Yes |  |  |  |  | AMT for tide sensor |  |  |  |  | 2022 MBARI GOC RC Leg 2
901101 - Seafloor Mapping | 10 | 3 | 0 | 11/15/2022 | 12/1/2022 |  | Yes | Yes |  | Yes | [8 empty] | Three non-consecutive AUV test days, two in early January, the third in early December
901101 - Seafloor Mapping | 12 | 2 | 0 | 1/5/2022 | 12/1/2022 | [8 empty] | Yes | [5 empty] | Low altitude survey system testing on Ventana (Mapping Toolsled)
901103 - Biodiversity & Biooptics | 10 | 1 |  | 7/18/2022 | 7/19/2022 | [8 empty] | Yes |  | Less than 20nm | 36.7 , -122.05 | 36.7 , -122.05 |  | MW1
901103 - Biodiversity & Biooptics | 10 | 1 |  | 9/15/2022 | 9/22/2022 | [8 empty] | Yes |  | Less than 20nm | 36.7 , -122.05 | 36.7 , -122.05
901103 - Biodiversity & Biooptics | 10 | 1 |  | 10/4/2022 | 10/5/2022 | [8 empty] | Yes |  | Less than 20nm | 36.7 , -122.05 | 36.7 , -122.05
901103 - Biodiversity & Biooptics | 10 | 1 |  | 11/7/2022 | 11/9/2022 | [8 empty] | Yes |  | Less than 20nm | 36.7 , -122.05 | 36.7 , -122.05
901112 - Change in MB & CA Current | 10 | 1 | 0 | 1/15/2022
901112 - Change in MB & CA Current | 10 | 1 | 0 | 6/15/2022
901112 - Change in MB & CA Current | 10 | 1 | 0 | 7/15/2022
901112 - Change in MB & CA Current | 10 | 1 | 0 | 8/15/2022
901112 - Change in MB & CA Current | 10 | 1 | 0 | 10/15/2022
901112 - Change in MB & CA Current | 10 | 1 | 0 | 11/15/2022
901112 - Change in MB & CA Current | 10 | 1 | 0 | 12/15/2022
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/22/2022 | 3/23/2022 |  |  |  | No |  |  |  |  | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | midwater.
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/23/2022 | 3/24/2022 |  |  |  | No |  |  |  |  | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | midwater.
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/24/2022 | 3/25/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | Midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/25/2022 | 3/28/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/28/2022 | 3/29/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/29/2022 | 3/30/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 3/30/2022 | 3/31/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | we’d like to schedule 7 cruise days within the first 2 or 3 weeks of the Carson being back. A schedule might look like: 3/22 + 3/23 (midwater); 3/25, 3/28, 3/29 (benthic); 3/30 + 4/1 (midwater) | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 4/19/2022 | 4/20/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | Midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 4/26/2022 | 4/27/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 5/10/2022 | 5/11/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 5/17/2022 | 5/18/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 6/28/2022 | 6/29/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | A midwater or a benthic dive would be fine | try to space out cruise so it doesn't coincide with Flyer
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 8/9/2022 | 8/10/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 8/16/2022 | 8/17/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 9/6/2022 | 9/7/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 9/13/2022 | 9/14/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 10/4/2022 | 10/5/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 10/11/2022 | 10/12/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 11/1/2022 | 11/2/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 11/8/2022 | 11/9/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 12/6/2022 | 12/7/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | midwater
901200 - AMP (use 910001.03) | 10 | 1 | 0 | 12/13/2022 | 12/14/2022 | [8 empty] | Yes |  | Between 20nm & 50nm |  |  | one benthic + one midwater cruise on average in each of these months | benthic
901220 - Midwater Ecology | 10 | 8 | 0 | 2/27/2022 |  | No |  | No | Yes | Yes | No | No | No | No |  | Greater than 50nm | 24° 13 N/109° 36 W | 26° 11 N/110° 36 W | GOC/Robison Feb 27-March 8 with i2MAP | Begin/End waypoints TBD. These parallel our WF cruise, beginning at Cerralvo Bank and extending to Carmen Basin.
901220 - Midwater Ecology | 10 | 3 | 0 | 10/26/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | 10 | 1 | 0 | 1/5/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | 10 | 1 | 0 | 3/22/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | Paired Topo transects w/RC and MW transects w/i2MAP. Also MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | 10 | 1 | 0 | 5/17/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901220 - Midwater Ecology | 10 | 1 | 0 | 6/22/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | MRS Recovery. Needs to follow MRS deployment, i2Map
901221 - Midwater Time Series | 10 | 1 | 0 | 1/6/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | i2MAP & MRS Deployment. Needs to precede MRS deployment
901221 - Midwater Time Series | 10 | 1 | 0 | 3/23/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | Paired Topo transects w/RC and MW transects w/i2MAP. Also MRS Recovery. Needs to precede MRS deployment i2Map
901221 - Midwater Time Series | 10 | 1 | 0 | 5/18/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | i2MAP & MRS Deployment. Needs to precede MRS deployment
901221 - Midwater Time Series | 10 | 1 | 0 | 6/23/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | i2MAP & MRS Deployment. Needs to precede MRS deployment
901221 - Midwater Time Series | 10 | 1 | 0 | 10/27/2022 |  | No |  | No | Yes | Yes | No | No | No | Yes |  | Less than 20nm | 36.74978300/-122.10698300 | 36.74978300/-122.10698300 | i2MAP & MRS Deployment. Needs to precede MRS deployment
901502 - Passive Acoustic Sensing | 12 | 1 | 0 | 1/11/2022 | 1/18/2022 | [8 empty] | Yes |  | Less than 20nm | MARS |  | As early in 2022 as possible | For deployment of Naval Postgraduate School directional acoustic system
901618 - Pelagic-Benthic Coupling | 12 | 1 |  | 6/27/2022 | 6/20/2022 | [8 empty] | Yes | Elevator | Between 20nm & 50nm | Moss Landing | MARS | Two consecutive days in June | deploy the macro camera system, make ROV observations, and conduct further laser-measure measurements
901618 - Pelagic-Benthic Coupling | 12 | 1 |  | 6/28/2022 | 6/21/2022 | [8 empty] | Yes | Elevator | Between 20nm & 50nm | Moss Landing | MARS | Two consecutive days in June | deploy the macro camera system, make ROV observations, and conduct further laser-measure measurements
901618 - Pelagic-Benthic Coupling | 12 | 1 |  | 10/17/2022 | 10/24/2022 | [8 empty] | Yes | Elevator | Between 20nm & 50nm | Moss Landing | MARS | Two consecutive days in October | deploy the macro camera system, make ROV observations, and conduct further laser-measure measurements
901618 - Pelagic-Benthic Coupling | 12 | 1 |  | 10/18/2022 | 10/25/2022 | [8 empty] | Yes | Elevator | Between 20nm & 50nm | Moss Landing | MARS | Two consecutive days in October | deploy the macro camera system, make ROV observations, and conduct further laser-measure measurements
901700 - 2017 Acoustical Ocean Eco | 12 | 1 |  | 3/16/2022 | 3/2/2022 |  |  |  | Yes | Yes |  |  |  | Yes |  | Less than 20nm |  |  | As soon as possible after GOC | Deploy MARS echosounder replacement
901809 - Deep Sea Bioinspiration |  | 2 |  | 11/1/2022 | [7 empty] | Yes |  | No |  |  |  |  | Could also use Fulmar if needed | Deploy MiniROV over multi-day cruise to collect animals and test ML-integrated tracking and acquisition algorithms
901809 - Deep Sea Bioinspiration |  | 0 |  | 3/15/2022 | [7 empty] | Yes |  | Yes |  |  |  |  | Could also use Fulmar if needed | Use MiniROV to test ML-integrated tracking and acquisition algorithms, EyeRIS tests, observe animals
901809 - Deep Sea Bioinspiration |  | 0 |  | 5/1/2022 | [7 empty] | Yes | [6 empty] | Could also use Fulmar if needed | Deploy MiniROV over multi-day cruise to collect animals and test ML-integrated tracking and acquisition algorithms.
|  | 104 | 0
Notes:
Sep 3, 2021 9:45:09 AM PDT
Confidential Information. Do not distribute without permission.

## 2022_Paragon
Level | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV Crew | CTD winch | Transducer pole | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
300057 - Mooring Maint | 12 | 0 | 1/1/2022 | [7 empty] | M1
600034 - Control Tech - Rock | 2 | 0 | 3/16/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
600034 - Control Tech - Rock | 2 | 0 | 6/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901009 - CANON | 11 |  | 10/21/2022 |  | Yes | Yes
901009 - CANON | 2 | 0 | 8/22/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901009 - CANON | 2 | 0 | 10/21/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901103 - Biodiversity & Biooptics | 2 | 0 | 1/17/2022 | [6 empty] | Less than 20nm |  |  | - no specific dates yet | two days to conduct blue water diving operations
901103 - Biodiversity & Biooptics | 2 |  | 3/14/2022
901103 - Biodiversity & Biooptics | 2 |  | 5/16/2022
901103 - Biodiversity & Biooptics | 2 |  | 7/18/2022
901103 - Biodiversity & Biooptics | 2 |  | 9/19/2022
901103 - Biodiversity & Biooptics | 2 |  | 11/7/2022
901112 - Change in MB & CA Current | 2 | 0 | 1/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 2/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 3/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 4/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 5/3/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 6/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 7/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 8/2/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 9/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 10/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 11/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 12/1/2022 |  | Yes | Yes
901112 - Change in MB & CA Current | 2 | 0 | 1/4/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 2/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 3/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 4/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 5/3/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 6/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 7/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 8/2/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 9/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 10/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 11/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901112 - Change in MB & CA Current | 2 | 0 | 12/1/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901200 - AMP (use 910001.03) | 3 | 0 | 7/12/2022 | 8/8/2022 |  |  |  |  | Albacore collections between July-October depending on water temperatures and albacore presence | Between 20nm & 50nm |  |  | Albacore collections between July-October depending on water temperatures and albacore presence
901200 - AMP (use 910001.03) | 2 | 0 | 9/6/2022 | 10/3/2022 |  |  |  |  | Albacore collections between July-October depending on water temperatures and albacore presence | Between 20nm & 50nm |  |  | Albacore collections between July-October depending on water temperatures and albacore presence
901206 - Coastal Profiling Float | 15 | [11 empty] | 5 days roughly in April, 5 in August and 5 in October
901206 - Coastal Profiling Float
901217 - Chemical Sensor Program | 4 | [12 empty] | Various dates for testing
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 4/1/2022 | 4/15/2022
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 5/2/2022 | 5/16/2022
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 6/1/2022 | 6/15/2022
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 7/1/2022 | 7/15/2022
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 8/1/2022 | 8/15/2022
901405 - PowerBuoy Dvlpmnt-Expense | 1 | 0 | 9/1/2022 | 9/15/2022
901513 - Targeted Sampling by AUVs | 2 | 0 | 4/4/2022 | 4/11/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 6/6/2022 | 6/13/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 7/4/2022 | 7/11/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 2/7/2022 | 2/14/2022 |  |  |  |  | LRAUV |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 3/7/2022 | 3/14/2022 |  |  |  |  | LRAUV |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 4/4/2022 | 4/11/2022 |  |  |  |  | LRAUV |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 6/6/2022 | 6/13/2022 |  |  |  |  | LRAUV |  |  |  |  | Launch point Moss Landing
901513 - Targeted Sampling by AUVs | 2 | 0 | 7/4/2022 | 7/11/2022 |  |  |  |  | LRAUV |  |  |  |  | Launch point Moss Landing
901618 - Pelagic-Benthic Coupling | 2 | 0 | 1/1/2022 | 1/3/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901618 - Pelagic-Benthic Coupling | 2 | 0 | 3/1/2022 | 3/15/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901618 - Pelagic-Benthic Coupling | 2 | 0 | 5/2/2022 | 5/16/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901618 - Pelagic-Benthic Coupling | 2 | 0 | 7/4/2022 | 7/18/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901618 - Pelagic-Benthic Coupling | 2 | 0 | 9/14/2022 | 9/5/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 15 | [6 empty] | Yes |  | Less than 20nm |  |  | Spread throughout the year, working around other Paragon users
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 1/31/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 3/9/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 4/20/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 7/5/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 10/13/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 11/9/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 3/16/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 6/15/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901700 - 2017 Acoustical Ocean Eco | 2 | 0 | 9/15/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901713 - Nearshore FOCE | 8 | [11 empty] | we anticipate ~8 days spread from the late winter through late fall | Hopkins Marine Station
901803 - Carbon Wave Glider Develo | 5 | 0 | 11/17/2022 |  |  |  | Yes |  |  | Less than 20nm | Moss Landing | TBD within the Bay | Flexible dates for 10 outings | Collect validation samples near carbon wave glider or M1 mooring
901803 - Carbon Wave Glider Develo | 2 | 0 | 8/10/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901803 - Carbon Wave Glider Develo | 2 | 0 | 9/14/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901803 - Carbon Wave Glider Develo | 2 | 0 | 10/12/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901805 - Coastal Biogeochemical Se | 12 | [5 empty] | Yes |  | Rosette | Less than 20nm | MBARI | MBARI |  | Monthly sampling at C1. Timing is flexible
901805 - Coastal Biogeochemical Se | 20 | [8 empty] | Less than 20nm | MBARI | MBARI |  | Spray and Waveglider deployment, probably near C1
901805 - Coastal Biogeochemical Se | 2 | 0 | 8/8/2022 | 7/11/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
901809 - Deep Sea Bioinspiration | 5 |  | 5/9/2022 | [5 empty] | LRAUV, WaveGlider |  |  |  |  | Deploy EyeRIS-integrated LRAUV and WaveGlider to demonstrate Supervised Autonomy
901809 - Deep Sea Bioinspiration | 5 |  | 10/3/2022 | [5 empty] | LRAUV, WaveGlider |  |  |  |  | Deploy EyeRIS-integrated LRAUV and WaveGlider to demonstrate Supervised Autonomy
901809 - Deep Sea Bioinspiration | 2 | 0 | 6/20/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901809 - Deep Sea Bioinspiration | 2 | 0 | 11/8/2022 | [5 empty] | Wave Glider |  |  |  |  | Launch point Moss Landing
901809 - Deep Sea Bioinspiration | 2 | 0 | 6/13/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
901809 - Deep Sea Bioinspiration | 2 | 0 | 11/14/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
902000 - Multi-Spectral StealthCam | 2 |  | 7/11/2022 | 7/13/2022 |  |  |  | Yes | [5 empty] | Location (within MB) TBD
902000 - Multi-Spectral StealthCam | 2 |  | 8/15/2022 | 8/17/2022 |  |  |  | Yes | [5 empty] | Location (within MB) TBD
902000 - Multi-Spectral StealthCam | 2 |  | 9/19/2022 | 9/21/2022 |  |  |  | Yes | [5 empty] | Location (within MB) TBD
902000 - Multi-Spectral StealthCam | 2 |  | 10/17/2022 | 10/19/2022 |  |  |  | Yes | [5 empty] | Location (within MB) TBD
902000 - Multi-Spectral StealthCam | 2 |  | 11/7/2022 | 11/9/2022 |  |  |  | Yes | [5 empty] | Location (within MB) TBD
902004 - Planktivore | 1 |  | 4/6/2022 | 4/14/2022 |  |  | Yes |  | Spray Glider deployment
902004 - Planktivore | 1 |  | 5/10/2022 | 5/17/2022 |  |  |  |  | Spray Glider deployment
902004 - Planktivore | 1 |  | 6/8/2022 | 6/22/2022 |  |  |  |  | Spray Glider deployment
902004 - Planktivore | 1 |  | 7/20/2022 | 8/9/2022 |  |  |  |  | Wire walker deployment
902010 - Mesopelagic LRAUV | 4 |  | 11/1/2022
902101 - LRAUV Tech Dev &Fleet Ops | 10 |  | 7/13/2022 | 8/5/2022
902101 - LRAUV Tech Dev &Fleet Ops | 2 | 0 | 7/13/2022 | 8/5/2022 |  |  |  |  | LRAUV |  |  |  |  | Launch point Moss Landing
902201 - Blue Whale Observatory | 1 | 0 | 8/15/2022 | 8/16/2022 | [5 empty] | Less than 20nm |  |  | near deployment date of blue whale observatory
902201 - Blue Whale Observatory | 1 | 0 | 10/1/2222 | 10/2/2022 | [5 empty] | Less than 20nm |  |  | near mid-point of blue whale observatory deployment
902201 - Blue Whale Observatory | 1 | 0 | 11/15/2022 | 11/16/2022 | [5 empty] | Less than 20nm |  |  | near recovery date of blue whale observatory
902204 - Scalable Robotics | 5 | 0 | 10/1/2022 | 10/15/2022 | [9 empty] | Testing
902204 - Scalable Robotics | 5 | 0 | 11/1/2022 | 11/15/2022 | [9 empty] | Testing
701141 - SiphWeb | 2 | 0 | 1/18/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
701141 - SiphWeb | 2 | 0 | 3/8/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
701141 - SiphWeb | 2 | 0 | 5/10/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
701141 - SiphWeb | 2 | 0 | 7/12/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
701141 - SiphWeb | 2 | 0 | 9/12/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
701141 - SiphWeb | 2 | 0 | 11/8/2022 | [5 empty] | LRAUV |  |  |  |  | Launch point Moss Landing
701145 - Penguin Hotspots | 5 |  | 2/1/2022 |  |  |  |  | Yes |  | Less than 20nm
701149 - Improving pCO2 estimates | 2 | 0 | 4/4/2022 | 4/11/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
701149 - Improving pCO2 estimates | 2 | 0 | 9/1/2022 | 9/12/2022 |  |  |  |  | Wave Glider |  |  |  |  | Launch point Moss Landing
315
Notes:
Sep 3, 2021 9:46:01 AM PDT
Confidential Information. Do not distribute without permission.

## 2022_LRAUV
Level | Days | Proposed Date | Alternate Date | Payload | Launch Point | Notes
600034 - Control Tech - Rock | 1 | 3/16/2022
600034 - Control Tech - Rock | 1 | 6/1/2022
901009 - CANON | 11 | 2022-09-05 |  |  |  | Sync w/Western Flyer cruise
901009 - CANON | 11 | 2022-09-05 |  |  |  | Sync w/Western Flyer cruise
901112 - Change in MB & CA Current | 3 | 1/4/2022
901112 - Change in MB & CA Current | 3 | 2/1/2022
901112 - Change in MB & CA Current | 3 | 3/1/2022
901112 - Change in MB & CA Current | 3 | 4/1/2022
901112 - Change in MB & CA Current | 3 | 5/3/2022
901112 - Change in MB & CA Current | 3 | 6/1/2022
901112 - Change in MB & CA Current | 3 | 7/1/2022
901112 - Change in MB & CA Current | 3 | 8/2/2022
901112 - Change in MB & CA Current | 3 | 9/1/2022
901112 - Change in MB & CA Current | 3 | 10/1/2022
901112 - Change in MB & CA Current | 3 | 11/1/2022
901112 - Change in MB & CA Current | 3 | 12/1/2022
901513 - Targeted Sampling by AUVs | 1 | 2/7/2022 | 2/14/2022 |  | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 3/7/2022 | 3/14/2022 |  | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 4/4/2022 | 4/11/2022 |  | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 5/16/2022 | 5/23/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/17/2022 | 5/24/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/18/2022 | 5/25/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/19/2022 | 5/26/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/20/2022 | 5/27/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 6/6/2022 | 6/13/2022 |  | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 7/4/2022 | 7/11/2022 |  | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 5/23/2022 | 5/30/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/24/2022 | 5/31/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/25/2022 | 6/1/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/26/2022 | 6/2/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/27/2022 | 6/3/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/21/2022 | 5/28/2022 |  | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/22/2022 | 5/29/2022 |  | Other | ECOHAB: Santa Barbara Channel
901700 - 2017 Acoustical Ocean Eco | 7 | 3/16/2022 |  | bioacoustics | Moss Landing
901700 - 2017 Acoustical Ocean Eco | 7 | 6/15/2022 |  | bioacoustics | Moss Landing
901700 - 2017 Acoustical Ocean Eco | 7 | 9/15/2022 |  | bioacoustics | Moss Landing
901809 - Deep Sea Bioinspiration | 5 | 6/13/2022
901809 - Deep Sea Bioinspiration | 5 | 11/14/2022
902101 - LRAUV Tech Dev &Fleet Ops | 30 | 7/13/2022 | 8/5/2022
701141 - SiphWeb | 2 | 1/18/2022 |  | Bathyphotometer | Moss Landing
701141 - SiphWeb | 2 | 11/8/2022 |  | Bathyphotometer | Moss Landing
701141 - SiphWeb | 2 | 5/10/2022 |  | Bathyphotometer | Moss Landing
701141 - SiphWeb | 2 | 7/12/2022 |  | Bathyphotometer | Moss Landing
701141 - SiphWeb | 2 | 9/12/2022 |  | Bathyphotometer | Moss Landing
701141 - SiphWeb | 2 | 3/8/2022 |  | Bathyphotometer | Moss Landing
708143 - CA Current HABS | 14 | 5/16/2022 | 5/23/2022 | ESP w/SPR | Other | This is the Santa Barbara deployment of 1 LRAUV with ESP/SPR. Week 1 will be recon, week 2 will be intensive sampling.
TOTAL SEA DAYS | 164
Notes:
Sep 3, 2021 9:46:50 AM PDT
Confidential Information. Do not distribute without permission.

## 2022_Wave Glider
Level | Days | Proposed Date | Alternate Date | Payload | Launch Point | Notes
901009 - CANON | 11 | 9/5/2022
901009 - CANON | 11 | 9/5/2022
901112 - Change in MB & CA Current | 2 | 1/15/2022
901112 - Change in MB & CA Current | 2 | 2/15/2022
901112 - Change in MB & CA Current | 2 | 3/15/2022
901112 - Change in MB & CA Current | 2 | 4/15/2022
901112 - Change in MB & CA Current | 2 | 5/15/2022
901112 - Change in MB & CA Current | 2 | 6/15/2022
901112 - Change in MB & CA Current | 2 | 7/15/2022
901112 - Change in MB & CA Current | 2 | 8/15/2022
901112 - Change in MB & CA Current | 2 | 9/15/2022
901112 - Change in MB & CA Current | 2 | 10/15/2022
901112 - Change in MB & CA Current | 2 | 11/15/2022
901112 - Change in MB & CA Current | 2 | 12/15/2022
901513 - Targeted Sampling by AUVs | 1 | 4/4/2022 | 4/11/2022 | hotspot | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 6/6/2022 | 6/13/2022 | hotspot | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 7/4/2022 | 7/11/2022 | hotspot | Moss Landing
901513 - Targeted Sampling by AUVs | 1 | 5/22/2022 | 5/29/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/23/2022 | 5/30/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/24/2022 | 5/31/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/25/2022 | 6/1/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/26/2022 | 6/2/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/27/2022 | 6/3/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901513 - Targeted Sampling by AUVs | 1 | 5/28/2022 | 6/4/2022 | hotspot | Other | ECOHAB: Santa Barbara Channel
901618 - Pelagic-Benthic Coupling | 1 | 1/1/2022 | 1/3/2022 |  |  | 1 day for payload prep of Hotspot on shore
901618 - Pelagic-Benthic Coupling | 20 | 7/4/2022 | 7/18/2022 |  | Moss Landing | communicate with Rover and SES and do Loop and Cross
901618 - Pelagic-Benthic Coupling | 20 | 5/2/2022 | 5/16/2022 |  | Moss Landing | communicate with Rover and SES and do Loop and Cross
901618 - Pelagic-Benthic Coupling | 20 | 9/14/2022 | 9/5/2022 |  | Moss Landing | communicate with Rover and SES and do Loop and Cross. Rendezvous during Flyer cruise in September 2022
901618 - Pelagic-Benthic Coupling | 20 | 3/1/2022 | 3/15/2022 |  | Moss Landing | communicate with Rover and SES and do Loop and Cross
901700 - 2017 Acoustical Ocean Eco | 17 | 1/31/2022 |  | bioacoustics | Moss Landing | AOE
901700 - 2017 Acoustical Ocean Eco | 17 | 4/20/2022 |  | bioacoustics | Moss Landing | AOE
901700 - 2017 Acoustical Ocean Eco | 17 | 7/5/2022 |  | bioacoustics | Moss Landing | AOE
901700 - 2017 Acoustical Ocean Eco | 17 | 11/9/2022 |  | bioacoustics | Moss Landing | AOE
901700 - 2017 Acoustical Ocean Eco | 17 | 3/9/2022 |  | bioacoustics | Moss Landing | Astrid Leitner
901700 - 2017 Acoustical Ocean Eco | 17 | 10/13/2022 |  | bioacoustics | Moss Landing | Astrid Leitner
901803 - Carbon Wave Glider Develo | 5 | 8/10/2022 |  | DIC-pCO2 instrumentation |  | Sensor integration at MBARI
901803 - Carbon Wave Glider Develo | 5 | 9/14/2022 |  | Science + DIC-pCO2 instrumentation | Moss Landing | Dates flexible
901803 - Carbon Wave Glider Develo | 5 | 10/12/2022 |  | Science + DIC-pCO2 instrumentation | Moss Landing | Dates flexible
901805 - Coastal Biogeochemical Se | 10 | 8/8/2022 | 7/11/2022 | pCO2 | Moss Landing | Should be same time as WF cruise. A couple extra days to account for WG transit time to station
901809 - Deep Sea Bioinspiration | 5 | 6/20/2022
901809 - Deep Sea Bioinspiration | 5 | 11/8/2022
902201 - Blue Whale Observatory | 17 | 8/15/2022 | 8/22/2022 | Bio-acoustics | Moss Landing |  | HIGH PRIORITY over CANON
902201 - Blue Whale Observatory | 17 | 9/5/2022 | 9/12/2022 | Bio-acoustics | Moss Landing |  | HIGH PRIORITY over CANON
902201 - Blue Whale Observatory | 17 | 10/3/2022 | 10/10/2022 | Bio-acoustics | Moss Landing |  | HIGH PRIORITY over CANON
902201 - Blue Whale Observatory | 17 | 11/7/2022 | 11/14/2022 | Bio-acoustics | Moss Landing |  | HIGH PRIORITY over CANON
701149 - Improving pCO2 estimates | 17 | 4/4/2022 | 4/11/2022 | pCO2, MF DAT, | Moss Landing | Co-deployment with Spray
701149 - Improving pCO2 estimates | 17 | 9/1/2022 | 9/12/2022 | pCO2, MF DAT | Moss Landing | Co-deployment with Spray
TOTAL SEA DAYS | 376 | 262 in previous request, need to trim?
2021 was 337
Notes:
Sep 3, 2021 9:47:52 AM PDT
Confidential Information. Do not distribute without permission.

## 2022_External Ship Equipment
Level | Days | Transit Days | Proposed Date | Alternate Date | AUV - CTD | AUV - Mapping | AUV - Mapping 2 | AUV - Other | AUV Crew | CTD 12hr | CTD 24hr | Mini - ROV | Other Equipment | Distance | Lat/Long Beginning | Lat/Long End | Special Scheduling Considerations | Notes
600034 - Control Tech - Rock | 3 |  | 3/15/2022 | [8 empty] | Yes | [5 empty] | Test tank development work only
600034 - Control Tech - Rock | 0 |  | 6/15/2022
600034 - Control Tech - Rock | 0 |  | 9/15/2022
901023 - Continental Margin Proces | 200 |  | 5/1/2022 |  |  | Yes | Yes |  | Yes |  |  | Yes |  |  | Beaufort Sea, Arctic |  | Shipment to Korea planned for May 1st 2022, returning on November 15 2022. Sea operations will take up to 21 days, sometime between August 1st and Sept 15th
901200 - AMP (use 910001.03) | 9 | 4 | 3/14/2022 | 3/21/2022 | [7 empty] | Yes |  |  |  |  | RV Fulmar calendar will not be known until Jan/Feb 2022 | The plan is to use the Sanctuary vessel (R/V Fulmar) as the platform for the MiniROV. The actual expedition would be 5 days, but MBA is planning on two days of mob and two days of demob on board the R/V Fulmar. Time is requested for miniROV operators for the entire 9 days for each expedition
Notes:
Sep 3, 2021 9:48:35 AM PDT
Confidential Information. Do not distribute without permission.