## ResourceEstimate
2014 Tasks and milestones |  |  | EE Days | Tom SE Days | Brian SE Days | ME Days | Etech | Mtech | Video Lab | Machine Shop
Systems engineering |  |  | 5
HS-LRAUV RF link characterization | Measure range, connectivity of HS-to-LRAUV Freewave link; includes at-sea characterization |  | 2 | 4
Auto shore link selection | dynamically determine optimal shore link (e.g. based on signal strength, distance from shore, fail-over...) |  |  | 4
Shore link scheduling | When to establish shore connection? Periodically? Immediately after AUV connection? |  |  | 3
Link detection | HS detects, responds to endpoint link active (ppp or SLIP) |  |  | 2
Link duration management | How long should HS and endpoint keep link connected? |  |  | 5
Link power management | Power link radio/modem only when needed |  |  | 1
Endpoint naming conventions | Must associate endpoint IP address with directory names |  |  | 5
HS log | Log connections, errors. Provide retrieval-to-shore method |  |  | 2
| Radio Link Management Complete | Milestone 1 | 7 | 26 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hours | 56 | 208 | 0 | 0 | 0 | 0 | 0 | 0
Interface to WG communication infrastructure | Control some HS functions through WGMS (e.g. turn on cell modem, retrieve HS logs through WG Iridium) |  |  | 2 | 1
User interface | Enable user to configure Hotspot (schedules, etc) |  |  | 3
External interface | Provide API to applications, e.g. autonomy |  |  | 4
HS console gateway | HS enables shore-to-endpoint ssh |  |  | 4
| Applications Interface Complete | Milestone 2 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0
|  | Hours | 0 | 104 | 8 | 0 | 0 | 0 | 0 | 0
HS-acoustic adapter | Access to acoustic endpoints; file transfer via acoustic protocol |  |  | 7
| Implement Wave Glide specific software to operate a Benthos acoustic modem |  |  |  | 6
| Implement Wave Glider specific software to collect data from a synchronous acoustic data stream |  |  |  | 2
Acoustic GPS | implement software to provide GPS position over acoustic link. Data format will be a standard NMEA string (e.g. GGA). This would allow underwater localization of AUVs that carry an iUSBL |  |  |  | 4
| Acoustic Link Management Complete | Milestone 3 | 0 | 7 | 12 | 0 | 0 | 0 | 0 | 0
|  | Hours | 0 | 56 | 96 | 0 | 0 | 0 | 0 | 0
Kite-balloon experiment | Demonstrate relay through kite-balloon over 802.11 link |  |  | 4
AUV to Hotspot experiment application |  |  | 5 | 6 | 2
Acoustic to Hotsppot application |  |  | 5 | 6 | 4
| Support field experiments | Milestone 4 | 10 | 16 | 6 | 0 | 0 | 0 | 0 | 0
|  | Hours | 80 | 128 | 48 | 0 | 0 | 0 | 0 | 0
|  | Milestone 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | EE Days | Tom SE Days | Brian SE Days | ME Days | Etech | Mtech | Video Lab | Machine Shop
|  | Total | 17 | 62 | 19 | 0 | 0 | 0 | 0 | 0
|  | Hours | 136 | 496 | 152 | 0 | 0 | 0 | 0 | 0
|  |  | Total SE hours |  | 648

## BudgetEstimate
Item | Quantity | Cost | Capital | Expense | Outside service
0
0
0
0
0
0
0
0
subtotal |  |  | 0 | 0 | 0
0
0
0
0
0
subtotal |  |  | 0 | 0 | 0
0
0
subtotal |  |  | 0 | 0 | 0
0
0
subtotal |  |  | 0 | 0 | 0
Year 1 Subtotal |  |  | 0 | 0 | 0
Sales Tax @ | 8.25% |  | 0 | 0
Shipping |  |  |  | 200
Year 1 Total |  |  | 0 | 200 | 0