## PilotStationInterface
Module | Type | Channel | Function | Input Reg | Slope | Offset | Inverted | Checked
750-468 | AI | 1 | Lateral_Cmd | 0x000
|  | 2 | Turns_Cmd | 0x001
|  | 3 | Fore/Aft_Cmd | 0x002
|  | 4 | Vertical_Cmd | 0x003
750-468 | AI | 1 | Main_Cam_Pan | 0x004
|  | 2 | Main_Cam_Tilt | 0x005
|  | 3 | Main_Cam_Shld | 0x006
|  | 4 | Spare_Ana1_PSI | 0x007
750-468 | AI | 1 | VB_Cmd | 0x008
|  | 2 | Spare3000_Servo_Cmd | 0x009
|  | 3 | Spare_Ana2_PSI | 0x00A
|  | 4 | Spare_Ana3_PSI | 0x00B
750-1402 | DI | 1 | Spare_A | 0x00C
|  | 2 | Spare_B
|  | 3 | Upper_Pan_Left
|  | 4 | Upper_Pan_Right
|  | 5 | Upper_Tilt_Up
|  | 6 | Upper_Tilt_Down
|  | 7 | Jog_Up
|  | 8 | Jog_Down
|  | 9 | Bypass
|  | 10 | Bellypack_Enable
|  | 11 | Auto_Depth
|  | 12 | Auto_Alt
|  | 13 | Auto_Hdg
|  | 14 | Cruise
|  | 15 | Tlsld_Pan_Left
|  | 16 | Tlsld_Pan_Right
750-1402 | DI | 1 | Tlsld_Tilt_Up | 0x00D
|  | 2 | Tlsld_Tilt_Down
|  | 3 | Insite_Zoom_Tele
|  | 4 | Insite_Zoom_Wide
|  | 5 | Insite_Focus_Near
|  | 6 | Insite_Focus_Far
|  | 7 | Insite_Addr_0
|  | 8 | Insite_Addr_1
|  | 9 | Insite_Addr_2
|  | 10 | Insite_Addr_3
|  | 11 | Insite_Addr_4
|  | 12 | Insite_Addr_5
|  | 13 | Insite_Addr_6
|  | 14 | Insite_Addr_7
|  | 15 | Trigger_Open
|  | 16 | Trigger_Close
750-1402 | DI | 1 | Rocker Deploy | 0x00E
|  | 2 | Rocker Retract
|  | 3 | Still_Cam_Trigger
|  | 4 | Hold_Station

## ControlSystemInterface
Module | Type | Channel | Function | Input Reg | Output Reg | Slope | Offset | Inverted | Checked
750-1501 | DO | 1 | GFI_Ch_Sel_Bit0 | 0x200 | 0x003
|  | 2 | GFI_Ch_Sel_Bit1
|  | 3 | Hyd_Level_Alarm
|  | 4 | Hyd_Press_Alarm
|  | 5 | Tlsld_Rckr_Dply
|  | 6 | Tlsld_Rckr_Ret
|  | 7 | Tlsld_Det_Opn
|  | 8 | Tlsld_Det_Cls
|  | 9 | Com_Loss_Alrm
|  | 10 | Bellypack Kill
|  | 11 | Bypass_Interlock
|  | 12 | Tsld_Light_Pan_Right
|  | 13 | Tsld_Light_Pan_Left
|  | 14 | Tlsd_Light_Tilt_Up
|  | 15 | Tlsd_Light_Tilt_Down
750-468 | AI | 1 | GFI_Analog | 0x000 | NA
|  | 2 | 480_VAC | 0x001 | NA
|  | 3 | 480VAC_I | 0x002 | NA
|  | 4 | HFSS_Speed | 0x003 | NA
750-1402 | DI | 1 | Foot_PedalPan_Left | 0x007 | NA
|  | 2 | Foot_Pedal_Pan_Right |  | NA
|  | 3 | Foot_Pedal_Tilt_Up |  | NA
|  | 4 | Foot_Pedal_Tilt_Down |  | NA
|  | 5 | Console120_GF_Stat |  | NA
|  | 6 | Hotel480_GF_Stat |  | NA
|  | 7 | Motor2300_GF_Stat |  | NA
|  | 8 | Subsea2300_GF_Stat |  | NA
|  | 9 | Swing_Arm_Brake_On |  | NA
|  | 10 | Swing_Arm_Brake_Off |  | NA
|  | 11 | CP_Det_Opn |  | NA
|  | 12 | CP_Det_Cls |  | NA
|  | 13 | CP_Rckr_Dply |  | NA
|  | 14 | CP_Rckr_Ret |  | NA
|  | 15 | Sci_Index_Fwd |  | NA
|  | 16 | Sci_Index_Rev |  | NA
750-1402 | DI | 1 | Sci_Index_Stop | 0x008 | NA
|  | 2 | FrontPanel_Switch_Spare1 |  | NA
|  | 3 | FrontPanel_Switch_Spare2 |  | NA
750-638 | Counter | 1 | 480VAC_Freq
|  |  | C1_Ctrl/Status | 0x004
|  |  | C1_CounterValue | 0x004/0x005

## BellyPack
Module | Type | Channel | Function | Input Reg | Slope | Offset | Inverted | Checked
750-468 | AI | 1 | Port_Cmd | 0x000
|  | 2 | Stbd_Cmd | 0x001
|  | 3 | Lateral_Cmd | 0x002
|  | 4 | Vertical_Cmd | 0x003
750-1402 | DI | 1 | Auto_Hdg | 0x004
|  | 2 | Bypass

## SubSeaControlCan
Module | Type | Channel | Function | Input Reg | Output Reg | Slope | Offset | Inverted | Checked
750-557 | AO | 1 | Main_Cam_Shld_OP | 0x200 | 0x000
|  | 2 | Main_Cam_Tilt_OP | 0x201 | 0x001
|  | 3 | Main_Cam_Pan_OP | 0x202 | 0x002
|  | 4 | VB_Pump_OP | 0x203 | 0x003
750-557 | AO | 1 | Spare_Servo_B | 0x204 | 0x004
|  | 2 | Spare_HF_Servo | 0x205 | 0x005
|  | 3 | Spare_DAC1 | 0x206 | 0x006
|  | 4 | Spare_DAC2 | 0x207 | 0x007
750-557 | AO | 1 | Port_OP | 0x208 | 0x008
|  | 2 | Lat_OP | 0x209 | 0x009
|  | 3 | Stbd_OP | 0x20A | 0x00A
|  | 4 | Vert_OP | 0x20B | 0x00B
750-1505 | DO | 1 | Det1_Opn | 0x02F | 0x00F
|  | 2 | Det1_Cls
|  | 3 | Port_Spare2_A
|  | 4 | Port_Spare2_B
|  | 5 | Port_Swing_In
|  | 6 | Port_Swing_Out
|  | 7 | Port_Drawer_Opn
|  | 8 | Port_Drawer_Cls
|  | 9 | Det5_Opn
|  | 10 | Det5_Cls
|  | 11 | Det6_Opn
|  | 12 | Det6_Cls
|  | 13 | Port_Spare1_A
|  | 14 | Port_Spare1_B
|  | 15 | Det2_Opn
|  | 16 | Det2_Cls
750-1505 | DO | 1 | Port_Sw_Arm_Brake_On | 0x210 | 0x010
|  | 2 | Port_Sw_Arm_Brake_Off
|  | 3 | Spare
|  | 4 | Pump_Bypass
|  | 5 | Det4_Opn
|  | 6 | Det4_Cls
|  | 7 | Det8_Opn
|  | 8 | Det8_Cls
|  | 9 | Stbd_Spare2_A
|  | 10 | Stbd_Spare2_B
|  | 11 | Det3_Opn
|  | 12 | Det3_Cls
|  | 13 | Det7_Opn
|  | 14 | Det7_Cls
|  | 15 | Stbd_Drawer_Opn
|  | 16 | Stbd_Drawer_Cls
750-517 | DO | 1 | Upper_Pan_Left | 0x211 | 0x011
|  | 2 | Upper_Pan_Right
750-517 | DO | 1 | Upper_Tilt_Up
|  | 2 | Upper_Tilt_Down
750-517 | DO | 1 | Aux_Pan_Left
|  | 2 | Aux_Pan_Right
750-517 | DO | 1 | Aux_Tilt_Up
|  | 2 | Aux_Tilt_Down
750-517 | DO | 1 | FOG_+24_Sw
|  | 2 | Aux_Hdg_+24_Sw
750-517 | DO | 1 | Aux_Tlsld_Inst_24
|  | 2 | Aux_Tlsld_Inst_12
750-517 | DO | 1 | Aux_Tlsld_Vlv_24
|  | 2 | DVL_+48_Sw
750-517 | DO | 1 | SS_GFI_Bit0
|  | 2 | SS_GFI_Bit1
750-517 | DO | 1 | SS_GFI_Bit2 | 0x212 | 0x012
|  | 2 | SS_GFI_Bit3
750-517 | DO | 1 | Altimeter_+24_Sw
|  | 2 | Spare_DC1_Ctr
750-457 | AI | 1 | Port_OP_FB | 0x000 | NA
|  | 2 | Vert_OP_FB | 0x001 | NA
|  | 3 | Lat_OP_FB | 0x002 | NA
|  | 4 | Stbd_OP_FB | 0x003 | NA
750-468 | AI | 1 | VB_Press | 0x004 | NA
|  | 2 | HP_Oil_Press | 0x005 | NA
|  | 3 | LP_Oil_Press | 0x006 | NA
|  | 4 | Elec_Comp_Press | 0x007 | NA
750-468 | AI | 1 | Umb_Comp_Press | 0x008 | NA
|  | 2 | Main_Comp_Press | 0x009 | NA
|  | 3 | Mot_Comp_Press | 0x00A | NA
|  | 4 | Oil_Level | 0x00B | NA
750-468 | AI | 1 | VB_Level | 0x00C | NA
|  | 2 | Upper_Pan | 0x00D | NA
|  | 3 | Upper_Tilt | 0x00E | NA
|  | 4 | Aux_Pan | 0x00F | NA
750-468 | AI | 1 | Aux_Tilt | 0x010 | NA
|  | 2 | Main_Pan_Sin | 0x011 | NA
|  | 3 | Main_Pan_Cos | 0x012 | NA
|  | 4 | GF_Analog | 0x013 | NA
750-468 | AI | 1 | Main_Tilt_Sin | 0x014 | NA
|  | 2 | Main_Tilt_Cos | 0x015 | NA
|  | 3 | Main_Shld_Sin | 0x016 | NA
|  | 4 | Main_Shld_Cos | 0x017 | NA
750-468 | AI | 1 | Altimeter_Ana | 0x018 | NA
|  | 2 | Humidity | 0x019 | NA
|  | 3 | Temp | 0x01A | NA
750-1402 | DI | 1 | Txfmr_Water_State | 0x01F | NA
|  | 2 | Fog_Water_State |  | NA
|  | 3 | Aux_Hdg_Water_State |  | NA
|  | 4 | Term_Water_State |  | NA
|  | 5 | Cam_Servo_Water_State |  | NA
|  | 6 | Thrstr_Water_State |  | NA
|  | 7 | FO_Water_State |  | NA
|  | 8 | DVL_Water_State |  | NA
750-638 | Counter | 1 | 480VAC_Freq
|  |  | C1_Ctrl/Status | 0x004
|  |  | C1_CounterValue | 0x004/0x005

## CoreCan
Module | Type | Channel | Function | Input Reg | Output Reg | Slope | Offset | Inverted | Checked
750-557 | AO | 1 | DSSI_Cmd | 0x200 | 0x000
|  | 2 | Tlsld_SpareAna1 | 0x201 | 0x001
|  | 3 | Tlsld_SpareAna2 | 0x202 | 0x002
|  | 4 | Tlsld_SpareAna3 | 0x203 | 0x003
750-1505 | DO | 1 | Port_UHMI_OnOff | 0x204 | 0x004
|  | 2 | Stbd_UHMI_OnOff
|  | 3 | Port_LHMI_OnOff
|  | 4 | Stbd_LHMI_OnOff
|  | 5 | Cam_Inc_OnOff
|  | 6 | Aft_Inc_OnOff
|  | 7 | Port_THMI_OnOff
|  | 8 | Stdb_THMI_OnOff
|  | 9 | Port_UHMI_Iso
|  | 10 | Stbd_UHMI_Iso
|  | 11 | Port_LHMI_Iso
|  | 12 | Stbd_LHMI_Iso
|  | 13 | Cam_Inc_Iso
|  | 14 | Aft_Inc_Iso
|  | 15 | Port_THMI_Iso
|  | 16 | Stbd_THMI_Iso
750-517 | DO | 1 | HFSS_Index_A | 0x205 | 0x005
|  | 2 | HFSS_Index_B
750-517 | DO | 1 | CoreCam_1_OnOff
|  | 2 | CoreCam_2_OnOff
750-517 | DO | 1 | Spare_DC1_Core
|  | 2 | Tlsld_AC_OnOff
750-517 | DO | 1 | SBE_Pump_OnOff
|  | 2 | Spare_DC2_Core
750-468 | AI | 1 | Temperature | 0x000 | NA
|  | 2 | Humidity | 0x001 | NA
750-1402 | DI | 1 | Index_Read | 0x004 | NA
|  | 2 | Core_Water_Alrm

## FOModbus
Type | Channel | Function | Input Reg | Output Reg | Default | Inverted | Checked
DO | 1 | AuxCam1_OnOff | 0x000 | 0x000
| 2 | AuxCam2_OnOff
| 3 | AuxCam3_OnOff
| 4 | CTD_OnOff
| 5 | AuxHDCam_OnOff
| 6 | ACM_OnOff
| 7 | InsiteZoom_OnOff
| 8 | UpperCam_OnOff
| 9 | Homer_OnOff
| 10 | Sonar_OnOff
| 11 | Ethernet_OnOff
| 12 | Laser_OnOff
| 13 | FOSci24_OnOff
| 14 | StbdSci24_OnOff
| 15 | PortSci24_OnOff
| 16 | FOSci12_OnOff
| 17 | StbdSci12_OnOff | 0x001 | 0x001
| 18 | PortSci12_OnOff
| 19 | Gigabit_120VAC_OnOff
| 20 | FO_120VAC_OnOff
| 21 | USBL Power_OnOff
| 22 | VBFlood_OnOff
| 23 | SpareTriswitch1_OnOff
| 24 | SchillingT4_OnOff
| 25 | SchillingAtlasPower_OnOff
| 26 | SchillingAtlasData_OnOff
| 27 | HD_Cam_OnOff
| 28 | Spare_SSR_C
| 29 | Spare_SSR_D_Triswitch2
| 30 | USBLOmniDir_Sel
AI | 1 | Temperature | 0x002 | NA
| 2 | Humidity | 0x003 | NA