## LRAUV_901110
901110 | LRAUV
|  |  |  | Pay Period 1 |  |  |  | Pay Period 2 |  |  |  | Pay Period3 |  |  |  | Pay Period4 |  |  |  | Pay Period5 |  |  |  | Pay Period6 |  |  |  | Pay Period7 |  |  |  | Pay Period8 |  |  |  | Pay Period9 |  |  |  | Pay Period10 |  |  |  | Pay Period11 |  |  |  | Pay Period12 |  |  |  | Pay Period13 |  |  |  | Pay Period14 |  |  |  | Pay Period15 |  |  |  | Pay Period16 |  |  |  | Pay Period17 |  |  |  | Pay Period18 |  |  |  | Pay Period19
|  |  |  | 2013-12-15 |  |  |  | 2012-12-29 |  |  |  | 2012-01-12 |  |  |  | 2013-01-26 |  |  |  | 2013-02-09 |  |  |  | 2013-02-23 |  |  |  | 2013-03-09 |  |  |  | 2013-03-23 |  |  |  | 2013-04-06 |  |  |  | 2013-04-20 |  |  |  | 2013-05-04 |  |  |  | 2013-05-18 |  |  |  | 2013-06-01 |  |  |  | 2013-06-15 |  |  |  | 2013-06-29 |  |  |  | 2013-07-13 |  |  |  | 2013-07-27 |  |  |  | 2013-08-10 |  |  |  | 2013-08-24
| Allocated Time (hrs.) | 845 |  | 2013-12-28 |  |  |  | 2013-01-11 |  |  |  | 2013-01-25 |  |  |  | 2013-02-08 |  |  |  | 2013-02-22 |  |  |  | 2013-03-08 |  |  |  | 2013-03-22 |  |  |  | 2013-04-05 |  |  |  | 2013-04-19 |  |  |  | 2013-05-03 |  |  |  | 2013-05-17 |  |  |  | 2013-05-31 |  |  |  | 2013-06-14 |  |  |  | 2013-06-28 |  |  |  | 2013-07-12 |  |  |  | 2013-07-26 |  |  |  | 2013-08-09 |  |  |  | 2013-08-23 |  |  |  | 2013-09-06
Date Task Added | Task Description | Allocated tasks estimate | Additional tasks estimate | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance
2012-01-01 | Wkly Mtg's |  |  | 2 |  | 2 | 0 | 2 |  | 2 | 0 |  |  | 0 | 0 | 2 |  | 2 | 0 |  |  | 0 | 0 | 1 |  | 1 | 0 | 4 |  | 4 | 0 | 2 |  | 2 | 0 | 4 |  | 4 | 0 | 3 |  | 3 | 0 | 4 |  | 4 | 0 | 1 |  | 1 | -1 | 1 |  | 1 | 0 | 4 |  | 4 | 0 | 1 |  | 1 | 0 | 4 |  | 4 | 0 | 2 |  | 2 | 0 | 2 |  | 2 | 0 |  |  | 0 | 0
| Composite Tube Design(Validation) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Pressure Case |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 1 |  | 1 | -1 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Battery Pack Layout |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 7 |  | 7 | -7 |  |  | 0 | 0 |  |  | 0 | 0 | 3 |  | 3 | -3 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Chassis |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 3 |  | 3 | -3 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | BuoyancyEngine |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 12 |  | 12 | -12 | 7 |  | 7 | -7 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Main Thruster Assembly |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Fins - Linkage & Drives |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Propeller |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Shell Design / Fab. |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Drop Weight Assem. |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 24 |  | 24 | -24 | 3 |  | 3 | -3 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Control Electronics |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Sensor Integration |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 1 |  | 1 | -1 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 6 |  | 6 | -6 |  |  | 0 | 0 | 8 |  | 8 | -8 | 6 |  | 6 | -6 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Weight & Balance |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Top Level assem. Drawings |  |  | 4 |  | 4 | -4 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 10 |  | 10 | -10 | 5 |  | 5 | -5 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Sea Tests |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Bench Mock-Up |  |  | 3 |  | 3 | -3 | 9 |  | 9 | -9 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01
2013-01-01 | XXXXXX-Vehicle #3 - PARTS |  |  | 8 |  | 8 | -8 | 9 |  | 9 | -9 | 7 |  | 7 | -7 | 2 |  | 2 | -2 | 11 |  | 11 | -11 | 3 |  | 3 | -3 | 21 |  | 21 | -21 |  |  | 0 | 0 | 8 |  | 8 | -8 | 39 |  | 39 | -39 | 11 |  | 11 | -11 | 14 |  | 14 | -14 | 21 |  | 21 | -21 | 19 |  | 19 | -19 | 36 |  | 36 | -36 | 26 |  | 26 | -26 |  |  | 0 | 0 | 55 |  | 55 | -55 | 13 |  | 13 | -13
2013-01-01 | XXXXXX-Vehicle #3 - BUILD |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 18 |  | 18 | -18 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | G3-ESP 901228.99 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 9 |  | 9 | -9 | 14 |  | 14 | -14 | 13 |  | 13 | -13 | 3 |  | 3 | -3 | 26 |  | 26 | -26 | 16 |  | 16 | -16 | 14 |  | 14 | -14 | 13 |  | 13 | -13 | 9 |  | 9 | -9 | 3 |  | 3 | -3 | 11 |  | 11 | -11
2013-01-01 | Sea Tests |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | ECO's |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| Bubble extractor (3p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| VB mount Frame (2p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 2 |  | 2 | -2 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| DAT |  |  |  |  | 0 | 0 | 4 |  | 4 | -4 | 5 |  | 5 | -5 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| Prilmary Battery Pack_Rev.B (4p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-01-01 | Secondary Battery _V3 (7p) | [14 empty] | 13 |  | 13 | -13 |  |  | 0 | 0 |  |  | 0 | 0 | 18 |  | 18 | -18 | 34 |  | 34 | -34 |  |  | 0 | 0 | 12 |  | 12 | -12 | 17 |  | 17 | -17 | 27 |  | 27 | -27 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 34 |  | 34 | -34 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-02-01 | LRS - Ice Tongs (9p) | [14 empty] | 5 |  | 5 | -5 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 2 |  | 2 | -2 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| WaveGlider Tow Body |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 26 |  | 26 | -26 |  |  | 0 | 0 |  |  | 0 | 0 | 3 |  | 3 | -3 |  |  | 0 | 0 | 5 |  | 5 | -5
| PAR Sensor Integration (2p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Parts Purchase |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Monitor/support Fabrication |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Q.C. Parts |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Write P.O's |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Propaganda/Documentation |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | LRS system |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 2 |  | 2 | -2 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 2 |  | 2 | -2 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Ex-tern |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | PAPERS |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
| Totals | 0 | 0 | 17 | 0 | 17 | -17 | 24 | 0 | 24 | -24 | 12 | 0 | 12 | -12 | 22 | 0 | 22 | -22 | 23 | 0 | 23 | -23 | 21 | 0 | 21 | -21 | 45 | 0 | 45 | -45 | 70 | 0 | 70 | -70 | 32 | 0 | 32 | -32 | 68 | 0 | 68 | -68 | 53 | 0 | 53 | -53 | 51 | 0 | 51 | -51 | 56 | 0 | 56 | -56 | 71 | 0 | 71 | -71 | 51 | 0 | 51 | -51 | 77 | 0 | 77 | -77 | 32 | 0 | 32 | -32 | 60 | 0 | 60 | -60 | 29 | 0 | 29 | -29
Allocated tasks are the ones you originally allocated for in the proposal
Additional tasks are the ones that get added in as you work on the project | [5 empty] | 17 | hrs. |  |  | 41 | hrs. |  |  | 41 | hrs. |  |  | 63 | hrs. |  |  | 86 | hrs. |  |  | 107 | hrs. |  |  | 152 | hrs. |  |  | 222 | hrs. |  |  | 254 | hrs. |  |  | 322 | hrs. |  |  | 375 | hrs. |  |  | 426 | hrs. |  |  | 482 | hrs. |  |  | 553 | hrs. |  |  | 604 | hrs. |  |  | 681 | hrs. |  |  | 713 | hrs. |  |  | 773 | hrs. |  |  | 802 | hrs.

## 707976_PwrBuoy
707976 | Power Buoy: ProtoType/Proto-Dock
|  |  |  | 1 |  |  |  | 3 |  |  |  | 19
|  |  |  | 2013-12-15 |  |  |  | 2013-01-12 |  |  |  | 2013-08-24
| Allocated Time (hrs.) | 80 |  | 2013-12-28 |  |  |  | 2013-01-25 |  |  |  | 2013-09-06
Date Task Added | Task Description | Allocated tasks estimate | Additional tasks estimate | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance | Charged | ETC | Total | Variance
2012-01-01 | Mtg's |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Literature Search |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Buoy Hull |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Gas Spring Assem. |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Gimble conn. |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | SENSORS |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | I.R. laser |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Slip Ring parts (3p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Coil Cord (3p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Power Sys. / Leads (4p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Relay & Brackets (1p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Electronics Housing (3p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Lab Tests |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Mobilize for field test |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | field test |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | FLAPPING FOIL |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | NACA Foils (4s) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Frame (10p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Fin Mold (5p) |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | DOCKING |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | P.D.R. |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Drawings for shop |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | C.D.R. | 16 |  |  |  | 0 | 16 |  |  | 0 | 16 |  |  | 0 | 16
2012-01-01 | Final Drawings ( after CDR) | 32 |  |  |  | 0 | 32 |  |  | 0 | 32 |  |  | 0 | 32
DAT Parts
2012-01-01 | Monitor support Fabrication | 16 |  |  |  | 0 | 16 |  |  | 0 | 16 |  |  | 0 | 16
2012-01-01 | Q.C. Parts | 32 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-02-18 | Magnets
2012-03-18 | Dock Cam
2012-01-01 | Assembly | 80 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Test | 24 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Write P.O's |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | MOB for Sea
2012-01-01 | Sea Test
2012-01-01 | Francios |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Incorporate Design Revisions |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Operations Manual |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Archive Design |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Write Paper |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2012-01-01 | Board Documentation |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2013-08-24 | 662000 | [10 empty] | 4
| Totals | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 4 | 0 | 4 | 196
Allocated tasks are the ones you originally allocated for in the proposal | [5 empty] | 0 | hrs. |  |  | 0 | hrs. |  |  | 0 | hrs.
Additional tasks are the ones that get added in as you work on the project

## 900xxx_XXXXXX
900xxx | Composite Press. Cases.
10
2005-05-01
| Allocated Time (hrs.) | ? |  |  |  | 2005-05-14
Date Task Added | Task Description | Allocated tasks estimate | Additional tasks estimate | Shop Time | Tech Time | Charged | ETC | Total | Variance
9/17/2013-2014 | Literature Search | 45 | [5 empty] | 0
2013-09-17 | Machine S.S. End Rings 8ea. | 8 |  | 128
2013-09-17 | Machine S.S. EndCaps 2ea. | 2 |  | 32
0
2014-09-17 | S.S. Ring - Case Assembly Glue-up | 9 |  |  | 90 |  |  | 0 | 9
2014-09-17 | Glue-up strain gauges | 9 |  |  | 36
2014-09-17 | CMM Measurement 4 cases |  |  | 16
2014-09-17 | Pressure test 2 grain gauged cases | 9 |  |  | 45
2014-09-17 | Press. Test 2 items to Failure | 9 |  |  | 9
2014-09-17 | Fatigue Test 2 additional strain gauged Items at 10, 50, 100 cycles | 9 |  |  | 18
2014-09-17 | Documentation | 18
2014-09-17 | C.D.R. | 9
2014-09-17 | Final Drawings ( after CDR) | 5
2014-09-17 | Machine Ti End Rings 4ea. | 8 |  | 64
2014-09-17 | Machine Ti EndCaps 4ea. | 2 |  | 64
2014-09-17 | Ti. Ring - Case Assembly Glue-up | 9 |  |  | 45 |  |  | 0
2014-09-17 | CMM Measurement 2 cases |  |  | 8
2014-09-17 | Documentation | 18 | [5 empty] | 0 | 18
[8 empty] | 0 | 0
2014-09-17 | Mobilize for field test | 18 |  |  | 9 |  |  | 0
2014-09-17 | field test Launch and Recovery | 18 | [5 empty] | 0
2015-09-17 | CMM Measurement 2 cases |  |  | 8
2015-09-17 | Press. Test 2 items to Failure | 9 |  |  | 9
2015-09-17 | Documentation | 18
0
2015-09-17 | Archive Design | 9 | [5 empty] | 0
2015-09-17 | Write Paper | 32 | [5 empty] | 0
2015-09-17 | Presentation | 18
2015-09-17 | Board Documentation | 5 | [5 empty] | 0
0
| Totals | 296 | 0 | 320 | 261 | 0 | 0 | 0 | 296
Allocated tasks are the ones you originally allocated for in the proposal
Additional tasks are the ones that get added in as you work on the project