## LRAUV_901110
901418 | Composite Pressure Cases Proposed Extension Rapid Prototype Cases
[7 empty] | TIME |  |  |  |  | Expenses
Date Task Added | Task Description | Qty | ME erickson | Mtech scholfield | Machine Shop | Additional tasks estimate | Charged | ETC | Total | Variance | Allocated resources by task (h) | Est. Build Material Required (g) | Build Material Cost ($/g) | $ ea. | Total | Outside Services | Total Materials and expenses $ | Notes
| Literature Search | 24 | [6 empty] | 0 | 0 | 0 | [5 empty] | 0
[9 empty] | 0 | 0 | 0
2014 | Machine S.S. End Rings 8ea. | [7 empty] | 0 | 0 | 0 | [5 empty] | 0 | Accomplished
2014 | Machine S.S. EndCaps 2ea. | [9 empty] | 0 | [5 empty] | 0 | Accomplished
0
2014 | C.D.R. | [9 empty] | 0 | [5 empty] | 0 | Accomplished
2014 | Final Drawings ( after CDR) | [9 empty] | 0 | [5 empty] | 0 | Accomplished
2014 | S.S. Ring - Case Assembly Glue-up | 4 | 9 | 48 | [6 empty] | 57 | [5 empty] | 0
2014 | Glue-up strain gauges | 4 | 9 | 48 | [6 empty] | 57 |  |  | 67.75 | 271 |  | 271
2014 | CMM Measurement 4 cases | 4 | 9 |  | 8 | [5 empty] | 17 | [5 empty] | 0
2014 | Strain Gauge Bridge Modules Rental | 3 | [8 empty] | 0 |  |  | 173 | 519 |  | 519
2014 | Connectors and Parts | 8 |  | ? | [6 empty] | 0 |  |  | ? |  |  | 0
2014 | Pressure test 2 grain gauged cases | 2 | 2 | 16 |  |  |  |  | 0 | 18 | 18 | [5 empty] | 0
2014 | Press. Test 2 items to Failure | 2 | 2 | 16 |  |  |  |  | 0 | 18 | 18 | [5 empty] | 0
2014 | Fatigue Test 2 add'l strain gauged Items at 10, 50, 100 cycles | 2 | 2 | 16 |  |  |  |  | 0 | 18 | 18 | [5 empty] | 0
2014 | Documentation | [7 empty] | 0 | 0 | 0 | [5 empty] | 0
0
2015 | Machine Ti End Rings 4ea. | 4 |  |  | 32 |  |  |  | 0 | 32 | 32 |  |  | 426 | 1704 |  | 1704 | Accomplished
2015 | Machine Ti EndCaps 4ea. | 4 |  |  | 32 |  |  |  | 0 | 32 | 32 |  |  | 426 | 1704 |  | 1704 | Accomplished
2015 | Ti. Ring - Case Assembly Glue-up | [9 empty] | 0 | [5 empty] | 0
2015 | CMM Measurement 2 cases |  | 4 |  | 4 |  |  |  | 0 | 8 | 8 | [5 empty] | 0
2015 | Documentation | [7 empty] | 0 | 0 | 0 | [5 empty] | 0
[9 empty] | 0 | 0 | 0
2015 | Mobilize for field test |  | 8 | [7 empty] | 8 | [5 empty] | 0
2015 | field test Launch and Recovery | [9 empty] | 0 | [5 empty] | 0
2015 | CMM Measurement 2 cases |  | 4 |  | 4 | [5 empty] | 8 | [5 empty] | 0
2015 | Press. Test 2 items to Failure |  | 2 | 16 | [6 empty] | 18 | [5 empty] | 0
2015 | Documentation | [9 empty] | 0 | [5 empty] | 0
0
2015 | Parts Purchase |  | 1 | [5 empty] | 0 | 1 | 1 | [5 empty] | 0
2015 | Monitor/support Fabrication |  | 4 | [5 empty] | 0 | 4 | 4 | [5 empty] | 0
2015 | Q.C. Parts |  | 8 | [5 empty] | 0 | 8 | 8 | [5 empty] | 0
2015 | Write P.O's | [7 empty] | 0 | 0 | 0 | [5 empty] | 0
2015 | Rev. parts | [7 empty] | 0 | 0 | 0 | [5 empty] | 0
2015 | Propaganda/Documentation |  | 18 | [5 empty] | 0 | 18 | 18 | [5 empty] | 0
2015 | PAPERS / REPORTS |  | 32 | [5 empty] | 0 | 32 | 32 | [5 empty] | 0
2015 | Conference Presentations |  | 32 | [10 empty] | 2500 | 2500 |  | 2500
| Totals |  | 146 | 160 | 80 | 0 | 0 | 0 | 0 | 354 | 354 | 0 |  |  | 6698 |  | 6698
Allocated tasks are the ones you originally allocated for in the proposal
Additional tasks are the ones that get added in as you work on the project