## LRAUV_901110
901418 | Composite Pressure Cases Proposed Extension Rapid Prototype Cases
[8 empty] | TIME |  |  |  |  | Expenses
Date Task Added | Task Description | Qty | ME shane | ME erickson | Mtech scholfield | Machine Shop | Additional tasks estimate | Charged | ETC | Total | Variance | Allocated resources by task (h) | Est. Build Material Required (g) | Build Material Cost ($/g) | Est. Support Mat'l (g) | Support Mat'l Cost ($/g) | $ ea. | x 5 ea. = Total | Outside Services | Total Materials and expenses $ | Notes
0
| Pull Test Coupons | 1p |  | 4 | [5 empty] | 0 | 4 | 4 | 18.3 | 0.3025 |  |  | 5.5358 | 27.6788 |  | 27.6788 | Accomplished
| Build time (shop) | 10 ea |  |  |  | 24 |  |  |  | 0 | 24 | 24 | 18.3 | 0.3025 | 18.3 | 0.1905 | 9.0219 | 45.1095 |  | 45.1095 | Accomplished
| Coupon Pull Test (10) |  | 2 | [6 empty] | 0 | 2 | 2 | [6 empty] | 700 | 700 | Accomplished
| Compression Test Coupons | 1p |  | 4 |  | 24 | [6 empty] | 18.3 | 0.3025 |  |  | 5.5358 | 27.6788 |  |  | Accomplished
| Build time (shop) | 10ea. | [10 empty] | 18.3 | 0.3025 | 18.3 | 0.1905 | 9.0219 | 45.1095 |  |  | Accomplished
| Coupon Test (10) |  | 4 | 1 | [7 empty] | 5 | [6 empty] | 700 | 700 | Accomplished
| RP-Case (CAMTAG design) | 2p | 2 | 4 | [5 empty] | 0 | 6 | 6 | 87.62 | 0.3025 | 65.72 | 0.1905 | 39.0247 | 195.1235 |  | 195.1235 | Accomplished
| RP-EndCap (CAMTAG design) | 1p | 2 | 4 | [5 empty] | 0 | 6 | 6 | 17.63 | 0.3025 |  |  | 5.3331 | 26.6654 |  | 26.6654 | Accomplished
[10 empty] | 0 | 0 | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
| Horiz Build shop time | 5ea |  |  |  | 36 |  |  |  | 0 | 36 | 36 | 87.62 | 0.3025 | 65.72 | 0.1905 | 39.0247 | 195.1235 |  | 195.1235 | Accomplished
| Vert Build shop time | 5ea |  |  |  | 36 |  |  |  | 0 | 36 | 36 | 17.63 | 0.3025 |  |  | 5.3331 | 26.6654 |  | 26.6654 | Accomplished
| Assemble Test units |  |  | 6 | [5 empty] | 0 | 6 | 6 | [7 empty] | 0 | Accomplished
| Pressure test 5 cases (Tech) | 10ea |  |  | 18 |  |  |  |  | 0 | 18 | 18 | [7 empty] | 0 | Accomplished
[12 empty] | 0 | [7 empty] | 0
| Alt. larger size design Two | 3p | 2 | 4 | [5 empty] | 0 | 6 | 6 | 1366 | 0.3025 | 1082 | 0.1905 | 619.336 | 1858.008 |  | 1858.008
| 3 inch ID x 6 inch long Case | 3 ea | [7 empty] | 0 | 0 | 0 | 418 | 0.3025 |  |  | 126.445 | 379.335 |  | 379.335
| 4.5 inch OD End Cap | 3 ea | [17 empty] | 0
| Build Time - (shop) |  |  |  |  | 24 |  |  |  | 0 | 24 | 24 | [7 empty] | 0
| Assemble for test |  |  | 4 | 4 |  |  |  |  | 0 | 8 | 8 | [7 empty] | 0
| Pressure Test (Tech) |  |  |  | 6 |  |  |  |  | 0 | 6 | 6 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
| Parts Purchase | [8 empty] | 0 | 0 | 0 | [7 empty] | 0
| Monitor/support Fabrication |  |  | 3 | [5 empty] | 0 | 3 | 3 | [7 empty] | 0
| Q.C. Parts |  |  | 2 | [5 empty] | 0 | 2 | 2 | [7 empty] | 0
| Write P.O's |  | 2 | [6 empty] | 0 | 2 | 2 | [5 empty] | 14 |  | 14
| Rev. parts | [8 empty] | 0 | 0 | 0 | [7 empty] | 0
| Propaganda/Documentation |  | 6 | 6 | [5 empty] | 0 | 12 | 12 | [7 empty] | 0
| PAPERS / REPORTS |  | 24 | 24 | [5 empty] | 0 | 48 | 48 | [7 empty] | 0
| Conference Presentations |  | 24
0
| Totals |  | 68 | 66 | 28 | 144 | 0 | 0 | 0 | 0 | 254 | 254 | 1994.5 |  |  |  |  | 2840.4974 |  | 4167.7091
Allocated tasks are the ones you originally allocated for in the proposal
Additional tasks are the ones that get added in as you work on the project