## LRAUV_901110
901418 | Composite Pressure Cases Proposed Extension Rapid Prototype Cases
[8 empty] | TIME |  |  |  |  | Expenses
Date Task Added | Task Description | Qty | ME shane | ME erickson | Mtech scholfield | Machine Shop | Additional tasks estimate | Charged | ETC | Total | Variance | Allocated resources by task (h) | Est. Build Material Required (g) | Build Material Cost ($/g) | Est. Support Mat'l (g) | Support Mat'l Cost ($/g) | $ ea. | x 5 ea. = Total | Outside Services | Total Materials and expenses $ | Notes
| Pull Test Coupons | 1p | [7 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | Accomplished
| Build time (shop) | 10 ea | [7 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | Accomplished
| Coupon Pull Test (10) | [8 empty] | 0 | 0 | 0 | [7 empty] | 0 | Accomplished
| Compression Test Coupons | 1p | [14 empty] | 0 | 0 |  | 0 | Accomplished
| Build time (shop) | 10ea. | [14 empty] | 0 | 0 |  | 0 | Accomplished
| Coupon Test (10) | [10 empty] | 0 | [7 empty] | 0 | Accomplished
| RP-Case (CAMTAG design) | 2p | [7 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | Accomplished
| RP-EndCap (CAMTAG design) | 1p | [7 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | Accomplished
[10 empty] | 0 | 0 | 0
| Horiz Build shop time | 5ea | [7 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | Accomplished
| Vert Build shop time | 5ea | [7 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | Accomplished
| Assemble Test units | [8 empty] | 0 | 0 | 0 | [7 empty] | 0 | Accomplished
| Pressure test 5 cases (Tech) | 10ea | [7 empty] | 0 | 0 | 0 | [7 empty] | 0 | Accomplished
0
| Alt. larger size design Two | 3p | 2 | 4 | [5 empty] | 0 | 6 | 6 | [7 empty] | 0
| 3 inch ID x 6 inch long Case | 3 ea | [7 empty] | 0 | 0 | 0 | 1366 | 0.3025 | 1082 | 0.1905 | 619.336 | 1858.008 |  | 1858.008
| 4.5 inch OD End Cap | 3 ea | [9 empty] | 0 | 418 | 0.3025 |  |  | 126.445 | 379.335 |  | 379.335
| Build Time - (shop) |  |  |  |  | 24 |  |  |  | 0 | 24 | 24 | [7 empty] | 0
| Assemble for test |  |  | 4 | 4 |  |  |  |  | 0 | 8 | 8 | [7 empty] | 0
| Pressure Test (Tech) |  |  |  | 6 |  |  |  |  | 0 | 6 | 6 | [7 empty] | 0
0
| Parts Purchase | [8 empty] | 0 | 0 | 0 | [7 empty] | 0
| Monitor/support Fabrication |  |  | 3 | [5 empty] | 0 | 3 | 3 | [7 empty] | 0
| Q.C. Parts |  |  | 2 | [5 empty] | 0 | 2 | 2 | [7 empty] | 0
| Write P.O's |  | 2 | [6 empty] | 0 | 2 | 2 | [7 empty] | 0
| Rev. parts | [8 empty] | 0 | 0 | 0 | [7 empty] | 0
| Propaganda/Documentation |  | 8 | 8 | [5 empty] | 0 | 16 | 16 | [7 empty] | 0
| PAPERS / REPORTS |  | 24 | 24 | [5 empty] | 0 | 48 | 48 | [7 empty] | 0
| Conference Presentations |  | 24 | [13 empty] | 2500 | 2500 |  | 2500
| Totals |  | 60 | 45 | 10 | 24 | 0 | 0 | 0 | 0 | 115 | 115 | 1784 |  |  |  |  | 4737.343 |  | 4737.343
Allocated tasks are the ones you originally allocated for in the proposal
Additional tasks are the ones that get added in as you work on the project