## LRAUV_901110
901418 | Composite Pressure cases - RP-Cases
|  |  |  | TIME |  |  |  | COST
| Allocated Time (hrs.) | ???
Date Task Added | Task Description | Allocated tasks estimate | Additional tasks estimate | Charged | ETC | Total | Variance | EST. (g) | $$$/g | x 3 ea. | Total $
| Pull Test Coupons (1p) | 2 |  |  |  | 0 | 2
| Build time (shop) (6 ea) | 24 |  |  |  | 0 | 24
| Coupon Pull Test (6) | 2 |  |  |  | 0 | 2 |  |  |  | 600 | ?
| RP-Case (CAMTAG design) (2p) | 4 |  |  |  | 0 | 4 | 87.62 | 0.3025 | 79.5152 | 92.0348
| RP-EndCap (CAMTAG design) (1p) | 4 |  |  |  | 0 | 4 | 17.63 | 0.3025 | 15.9992 | 15.9992
[6 empty] | 0 | 0
| Horizontal Build (3 ea.) | 3 |  |  |  | 0 | 3
| Alternate (Vert) Build (3 ea.) | 3 |  |  |  | 0 | 3
| Horiz Build shop time | 36 |  |  |  | 0 | 36
| Vert Build shop time | 36 |  |  |  | 0 | 36
| Assemble Test units | 6 |  |  |  | 0 | 6
| Pressure test 5 cases (Tech) | 18 |  |  |  | 0 | 18
| Alt. larger size design 2 (6 sheets) | 12 |  |  |  | 0 | 12
| 3 inch ID x 6 inch long |  |  |  |  | 0 | 0 | 1649 | 0.3025 | 1496.4675 | 1566.8992
| 5 inch ID x 10 inch long ?? |  |  |  |  | 0 | 0
| Build Time - (shop) | 24 |  |  |  | 0 | 24
| Asssemble for test | 4 |  |  |  | 0 | 4
| Pressure Test (Tech) | 6 |  |  |  | 0 | 6
| Parts Purchase |  |  |  |  | 0 | 0
| Monitor/support Fabrication | 3 |  |  |  | 0 | 3
| Q.C. Parts | 2 |  |  |  | 0 | 2
| Write P.O's | 1 |  |  |  | 0 | 1 |  |  |  | 14
| Rev. parts |  |  |  |  | 0 | 0
| Propaganda/Documentation | 3 |  |  |  | 0 | 3
| PAPERS / REPORTS | 40 |  |  |  | 0 | 40
| Totals | 233 | 0 | 0 | 0 | 0 | 233 | 1754.25 | 0.9075 |  | 2288.9332
Allocated tasks are the ones you originally allocated for in the proposal
Additional tasks are the ones that get added in as you work on the project