## Labor
|  |  |  | MS1 | MS2 | MS3 | MS4 | M5
| ME | 315 |  | 0 | 75 | 50 | 190 |  | 315
| SE | 675 |  | 180 | 200 | 220 | 75 |  | 675
| EE | 0 |  | 0 | 0 | 0 | 0 |  | 0
| ET | 20 |  | 0 | 20 | 0 | 0 |  | 20
| MT | 20 |  | 0 | 20 | 0 | 0 |  | 20
| AUV Engr | 90 |  | 0 | 40 | 0 | 50 |  | 90
| Machine Shop | 25 |  | 0 | 25 |  | 0 |  | 25
| Total By Designation | 1145 | [6 empty] | 0
|  |  |  | 180 | 380 | 270 | 315 |  | 1145
| Total By Hours | 1145
|  |  |  | SE | ME | EE | ME | SE | EE |  |  |  | SE | SE |  | SE
|  |  |  | 175 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 155 | 0 | 0 | 0 | 0 | 20 | 20 | 25 | 90
|  |  | Totals | Caress | Hobson |  |  | Headley |  | Cline | Chaffey |  | McEwen | Henthorn | Headley | SE | EE | McCann | MT | ET | Machine | AUV Eng
TRN
| Description | Task ID
| Side-looking TRN control | 1.1 | 140 | [9 empty] | 100 | 40
| Plumb Imagenex ranges to TRN | 1.2 | 40 | [10 empty] | 40
| Plump Reson ranges to TRN | 1.3 | 0
|  | 1.4 | 0
| Total |  | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High Resolution Mapping and Imaging | Description | Task ID | Totals
| Configure vehicle for down-looking | 2.1 | 40 | [15 empty] | 10 | 10 |  | 20
| Configure vehicle back to side-looking | 2.2 | 20 | [18 empty] | 20
| Design side/down looking light mounts for (4) LED panels | 2.3 | 100 |  | 75 | [15 empty] | 25
| Process low-altitude multibeam to generate a 20 cm resolution map | 2.4 | 120 | 100 | [14 empty] | 10 | 10 | 0
| Limit Cycle troubleshooting | 2.5 | 100 | [9 empty] | 100
| Total |  | 380 | 100 | 75 | [7 empty] | 100 | [5 empty] | 20 | 20 | 25 | 40
Operations | Description | Task ID | Totals
| 2850 clam site | 3.1 | 70 | 10 | 10 | [7 empty] | 40 | 10 | [7 empty] | 0
| 1000m wall site | 3.2 | 100 | 20 | 20 | [7 empty] | 40 | 20
| Portuguese Ledge | 3.3 | 100 | 20 | 20 | [7 empty] | 40 | 20
0
| Total |  | 270 | 50 | 50 | [7 empty] | 120 | 50 | [7 empty] | 0
Project Management |  |  | Totals
| Description | Task ID
| Overhead for meetings, etc. | 4.1 | 150 | 25 | 50 | [7 empty] | 25 | 25 | [7 empty] | 25
| Contingency to respond to issues | 4.2 | 65 |  | 40 | [16 empty] | 25
| Project Management | 4.3 | 100 |  | 100
| Total |  | 315 | 25 | 190 | [7 empty] | 25 | 25 | [7 empty] | 50
|  |  |  | Caress | Hobson |  |  | Headley |  | Cline | Chaffey |  | McEwen | Henthorn | Headley | SE | EE | McCann | MT | ET | Machine | AUV Eng
| Prepare & Sim 2800m Imaging Mission | 40
| Portuguese L TRN Closed Loop & Photos | 160
| Side-Looking TRN if SE plumbs Imagenexes | 60
| Other | 40

## Expense
| Item | Description | price | Notes
1
2
3
4
5
7
8
9
10
11
|  | Total = | 0
6

## JIRA
MBARI JIRA
Displaying 53 issues as at 2014-07-30 13:51.
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date | Original Estimate
New Feature | TETHYS-525 | Add support for serial BREAK | Brian Kieft | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2014-07-29 15:26 | 2014-07-29 15:26 |  | 43200
Bug | TETHYS-524 | missing CommandLine_TestComponent.pauseCfg for LRAUVTest | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2014-06-06 11:47 | 2014-06-06 11:47 |  | 86400
Improvement | TETHYS-523 | deprecate and remove asDouble from readers | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2014-06-05 13:33 | 2014-07-29 14:14 |  | 86400
Improvement | TETHYS-522 | Move interface configuration parameters for sensors and servos from vehicle.cfg to either Science.cfg, Sensor.cfg, or Servo.cfg | Michael Jordan Stanway | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2014-06-05 11:36 | 2014-06-05 11:36 |  | 7200
Improvement | TETHYS-520 | Change to default mission to run surface in parallel | Brian Kieft | Brian Kieft | Major | Open | UNRESOLVED | 2014-05-19 09:39 | 2014-07-29 15:20 |  | 86400
New Feature | TETHYS-518 | component to log memory & CPU usage | Brian Kieft | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2014-04-23 12:26 | 2014-07-22 09:33 |  | 86400
Improvement | TETHYS-515 | move magnetic declination to its own derivation component | Brian Kieft | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2013-12-19 11:11 | 2013-12-19 11:11 |  | 86400
Improvement | TETHYS-513 | replace deprecated libmagdev with geographiclib (or other comparable library) | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2013-12-17 12:13 | 2013-12-17 12:13 |  | 86400
Bug | TETHYS-512 | CommandLine up-arrow causes command to execute immediately | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2013-12-10 16:12 | 2014-07-22 09:53 |  | 86400
Bug | TETHYS-506 | Timeout values in mission components can not be changed after component is started | Brian Kieft | Michael Godin | Major | Open | UNRESOLVED | 2013-11-19 14:15 | 2013-11-19 14:15
Bug | TETHYS-504 | Extra long buffering time for syslog writes | Brian Kieft | Brian Kieft | Major | Open | UNRESOLVED | 2013-10-21 14:23 | 2013-10-21 14:23
Improvement | TETHYS-503 | Update SCPI interface to use PAR data to determine camera triggering | Brian Kieft | Brian Kieft | Minor | Open | UNRESOLVED | 2013-10-11 08:55 | 2014-07-22 09:52 |  | 172800
Bug | TETHYS-497 | Sim should write platform_mass_position before moving mass. | Brian Kieft | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2013-10-02 15:50 | 2013-10-02 15:52 |  | 432000
Improvement | TETHYS-487 | safety parameters as configuration variables | Brian Kieft | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2013-09-25 14:07 | 2013-09-25 14:10 |  | 432000
Improvement | TETHYS-486 | Change HTTP cache control response headers in realtime log displays | Brian Kieft | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2013-09-23 16:58 | 2013-09-23 17:01 |  | 14400
Improvement | TETHYS-485 | Make tabs persist on top of page on tethysdash | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2013-09-23 16:19 | 2013-09-23 16:29 |  | 86400
Improvement | TETHYS-483 | change "restart hardware" to an alias for "restart system" | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2013-09-23 15:57 | 2014-07-29 13:57 |  | 7200
Improvement | TETHYS-475 | move mass aft if dropweight is missing | Brian Kieft | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2013-09-18 09:41 | 2013-09-18 09:42 |  | 1209600
Improvement | TETHYS-466 | Orientation should be stored internally as a matrix or quaternion | Michael Jordan Stanway | Michael Jordan Stanway | Minor | Open | UNRESOLVED | 2013-08-14 13:30 | 2014-07-29 13:35 |  | 259200
New Feature | TETHYS-465 | Vertical Temperature Homogeneity Index | Michael Jordan Stanway | Michael Jordan Stanway | Major | Open | UNRESOLVED | 2013-08-13 15:38 | 2013-10-09 13:45 |  | 1209600
Improvement | TETHYS-454 | Surfacing architecture | Brian Kieft | Brian Kieft | Major | Open | UNRESOLVED | 2013-01-22 10:02 | 2013-09-25 13:56
Bug | TETHYS-429 | Simulator.cfg; fin location | Rob McEwen | Rob McEwen | Trivial | Open | UNRESOLVED | 2012-06-22 13:24 | 2014-07-29 13:30 |  | 86400
Bug | TETHYS-428 | If the mission Timeout uses an Arg, setting this arg during the mission has no effect. | Michael Godin | Michael Godin | Major | Open | UNRESOLVED | 2012-06-21 08:56 | 2012-06-21 08:56
New Feature | TETHYS-424 | Add serial number checking for instruments | Brian Kieft | Brian Kieft | Minor | Open | UNRESOLVED | 2012-05-15 09:03 | 2014-07-29 13:31 |  | 72000
New Feature | TETHYS-423 | Add horizontal control check | Richard Henthorn | Brian Kieft | Minor | Open | UNRESOLVED | 2012-05-07 15:31 | 2012-05-15 09:03
New Feature | TETHYS-422 | Add backup capability | Richard Henthorn | Brian Kieft | Minor | Open | UNRESOLVED | 2012-05-01 16:27 | 2012-05-15 09:02
Bug | TETHYS-398 | Smooth heading internal gets stuck | Brian Kieft | Brian Kieft | Minor | Open | UNRESOLVED | 2011-12-20 16:07 | 2011-12-20 16:07
Bug | TETHYS-382 | Serial transfer from mobo to receiver through MAX3100 fails | Brian Kieft | Brian Kieft | Major | Open | UNRESOLVED | 2011-10-26 10:45 | 2011-10-26 10:45
Bug | TETHYS-335 | SBIT shouldn't fail when mass default is something other than 0 | Brian Kieft | Brian Kieft | Minor | Open | UNRESOLVED | 2011-06-12 14:13 | 2011-06-12 14:13
New Feature | TETHYS-334 | Add servo delay to simulation | Brian Kieft | Brian Kieft | Minor | Open | UNRESOLVED | 2011-06-07 15:51 | 2014-07-29 13:21
Bug | TETHYS-257 | Figure out problem with WTMP file | Brian Kieft | Brian Kieft | Minor | Open | UNRESOLVED | 2011-01-19 14:23 | 2011-01-19 14:23
Task | TETHYS-198 | Update load controller test plan and functional spec | Brian Kieft | Brian Kieft | Major | Open | UNRESOLVED | 2010-08-17 12:00 | 2010-09-23 14:44
Generated at Wed Jul 30 13:51:09 PDT 2014 by Brian Kieft using JIRA Enterprise Edition, Version: 3.12.1-#299.
[11 empty] | 429.3333 | Total

## Operations
MBTS 12 days: 12 hours Stanway (SE), 12 hours Kieft (SE), 10 hours Mellinger (EE), 10 hours Klimov (EE) and 10 hours Hobson (ME)
Francisco Increased the MBTS request to Stanway, Kieft (40), Mellinger, Klimov, Hobson (20)
CANON 60 days (21 with 3 vehicles): 170 hours Stanway (SE), 170 hours Kieft (SE), 40 hours Mellinger (EE), 40 hours Klimov (EE) and 40 hours Hobson (ME)
Francisco reduced the CANON request to Stanway, Kieft (120), Mellinger, Klimov, Hobson (20)
Surf (20 days):30 hours for Stanway, 30 hours for Kieft, 10 hours for Hobson, 10 hours for Mellinger, 10 hours for Klimov
MiVegas: 5 days with 3 vehicles: 45 hours Stanway, 45 hours Kieft, 15 hours for Hobson, 15 hours for Mellinger, 15 hours for Klimov
There are three primary users of the LRAUVs at this point: LRAUV Development, CANON/MBTS and SURF. For purposes of watch-standing we'll blend Yanwu's Targeted Sampling into Development. Anytime your group is using the vehicle, it is assumed that your group will be covering the majority of the watch-standing shifts, with some volunteer help for the other groups. Brian and Jordan ("Super-Users") are splitting all the shifts so will not perform watch-standing duty. I think we have about 5 people per group, so for a one week deployment, which has 21 shifts, we'd hope to get the about 15 covered by the core group, or 3 shifts per person. Of the 6 remaining shifts, I'll take three (I tend to watch all shifts anyway) and hopefully you'll get three other volunteers from the other groups. We hope to get some support from DMO (Chris and Jared) with vehicle check-out, launch/recovery, vehicle check-in as well as some watch-standing, but that is still being worked out. For the shared engineering resources, we need to bill our time to your project. We are basing vehicle support on the MTBF of the vehicles, which is currently about 24 hours, but we hope to increase this to 100 hours. So, aside from launch/recovery and planned mission changes etc. we'd expect to have to respond to something about once per day. The "Super Users" will bill one hour to your project every day if it is a routine operation, and three hours if it is Development work, which includes most CANON operations. For the hourly people, we need to avoid overtime. Here's a list of registered pilots: Active pilots: Development: Brett, Ed, Denis, Yanwu and Ben, CANON/MBTS: Brent, John R., Reiko, Monique, Jason SURF: Bill, Jim B., Roman, Doug P., Semi-operators: Chris W., Jared, Marguerite, Carlos, Tom O'Reilly, Mark C., Duane, Gabe and Francisco