## Sheet1
Task | Week
Cruise Schedule | [10 empty] | Midwater Cruise |  |  |  |  | Mini/DeepPIV Cruise Days |  |  |  | Benthic Cruise |  |  | Midwater Cruise |  |  | Brewer Cruise | [5 empty] | Sur Ridge Cruise
| 2016-01-18 | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29
Define components for camera system | bar: 2016-01-18
Define components for laser system | bar: 2016-01-18
Define components for linear stage | bar: 2016-01-25
Define components for dye injector | bar: 2016-01-25
Draw block diagrams for integrated DeepPIV system (camera, laser, dye injector, linear stage) | bar: 2016-02-01
Purchase components for camera system | bar: 2016-02-01
Purchase components for laser system | bar: 2016-02-01
Test camera settings (comms and power interfaces, recording, saving video) | bar: 2016-02-08
Purchase components for dye injector | bar: 2016-02-08
Purchase components for linear stage | bar: 2016-02-08
Test fiber optic configuration with laser (estimate power output) | bar: 2016-02-15
Layout components for camera housing | bar: 2016-02-15
Layout components for laser housing | bar: 2016-02-15
Design frame connecting camera, linear stage, and laser | bar: 2016-02-22
Build camera and laser housings | bar: 2016-02-22 to 2016-02-29
Write controller for linear stage | bar: 2016-02-29
Write controller for dye injector | bar: 2016-03-07
Test linear stage | bar: 2016-03-07
Test dye injector | bar: 2016-03-14
Build frame, including manip mechanical interface | bar: 2016-03-14 to 2016-03-21
Design and build attachments for remaining DeepPIV components | bar: 2016-03-28 to 2016-04-04
Test camera system in test tank | bar: 2016-04-11
Test laser system in test tank | bar: 2016-04-18
Test stage and dye injector in test tank | bar: 2016-04-25
Compile DeepPIV documentation | bar: 2016-04-25
Deploy new camera system on DeepPIV | bar: 2016-05-02
Deploy with new laser system on DeepPIV | bar: 2016-05-09
Deploy with new linear stage on DeepPIV | bar: 2016-05-09
Deploy with new dye injector on DeepPIV | bar: 2016-05-09
Integrate all DeepPIV components (camera housing, laser controller and head, fiber optic penetrators, optics housing, linear stage, dye injector, video camera, near-IR light, and frame) | bar: 2016-05-16
Test fully integrated DeepPIV in test tank | bar: 2016-05-16
Test fully integrated DeepPIV on Doc Ricketts | bar: 2016-05-23
Deploy fully integrated DeepPIV | bar: 2016-05-30