## DeepPIV
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
To Do | Determine max depth of field with 2/5 f-stop increments |  |  |  | TW | in progress,in progress,past due | 14 | https://trello.com/c/VrZVicDZ
To Do | find laser safety signs |  |  |  | DK |  | 44 | https://trello.com/c/2o593gtU
To Do | Confirm power req of laser controller |  |  |  | AS |  | 41 | https://trello.com/c/hBKROUkR
To Do | confirm with peter whether to use BCRs or FCRs for laser cable |  |  |  | JE |  | 42 | https://trello.com/c/zQafuOoL
To Do | email controller company for latest manual |  |  |  | AS,C |  | 43 | https://trello.com/c/4XBO9RgW
To Do | Draw up coherent laser schematic |  |  |  | AS |  | 40 | https://trello.com/c/2lkpOUNH
To Do | Test Lytro camera to determine z-resolution of image stack, Denis will find collimated lens to test back lighting. |  |  |  | KK,DK | in progress,in progress,partially completed | 21 | https://trello.com/c/Zs5t0muy
To Do | look into automating deployment/stowage of DeepPIV on Schilling T4 with Knute |  |  |  | BE |  | 39 | https://trello.com/c/5wBFV52E
Ongoing | Test new AC/DCs with new laser |  |  |  | AS |  | 15 | https://trello.com/c/8sQYfjSp
Ongoing | Determine interface needs for a two-axis galvo for 3DR |  |  |  | DK |  | 11 | https://trello.com/c/kqFVGb5T
Ongoing | Look into options for a function generator board to drive/sync camera and galvanometer |  |  |  | AS |  | 12 | https://trello.com/c/elLScyL9
Ongoing | Make list of potential end of year purchases with prices. |  |  |  | AS | in progress | 29 | https://trello.com/c/UGSd05CN
Ongoing | discuss laser safety issues at MBARI with administration |  |  |  | DK,C | in progress,partially completed | 33 | https://trello.com/c/IVFmRFFG
Completed | Skype with Raytrix for camera demo |  |  |  | KK,AS | completed | 26 | https://trello.com/c/d1T3DCkD
Completed | Determine path forward using a galvanometer with DeepPIV |  |  |  | DK,KK | completed | 16 | https://trello.com/c/v5m62gbJ
Completed | Follow up with Knute after new Year about storing manip positions and/or hydraulic ram on the core vehicle for DeepPIV during midwater deployments; also can we do midwater ops using benthic sled and vice versa? |  |  |  | KK,AS,JE | in progress,partially completed,completed | 28 | https://trello.com/c/bNbTeFII
Completed | Find out how much color camera would cost without near-IR filter |  |  |  | KK | partially completed,completed | 8 | https://trello.com/c/eA9lPBrI
Completed | Forward laser spec sheets to LEC; hopefully sufficient detail to sync controllers to laser heads |  |  |  | KK | completed | 36 | https://trello.com/c/vg5pS9eP
Completed | follow up with Doug on laser safety |  |  |  | C | completed | 38 | https://trello.com/c/FrgAvxs5
Completed | Get cooling fan to Jon for designing laser heatsink |  |  |  | DK | in progress,in progress,completed | 30 | https://trello.com/c/ZZ3jTp51
Completed | follow up on fiber injectors with German company; purchase fiber injector based on Denis' input |  |  |  | KK,DK | partially completed,in progress,in progress,completed | 2 | https://trello.com/c/psnHUZRy
Completed | Midwater Research Cruise |  |  |  |  | completed | 17 | https://trello.com/c/H9XeGqLW
Upcoming goals | DeepPIV cruise (midwater) on Rachel Carson/Ventana |  |  | 2018-03-26 12:00 |  |  | 18 | https://trello.com/c/mEIGFi9q

## Archived DeepPIV
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Completed | [archived] Order 2 m patch cable with various core sizes (e.g., 12.5 and 25 microns) |  |  |  | DK | completed | 6 | https://trello.com/c/Tq6kap20
Completed | [archived] Purchase 1 and 1.33 diopters and 2 adapters |  |  |  | DK | completed | 3 | https://trello.com/c/6SlTOLLX
Completed | [archived] Look into mounting diopter to camera; send drawings to machine shop |  |  |  | JE | completed | 4 | https://trello.com/c/oId6aDud
Completed | [archived] Follow up on IT1000 availability from the FOCE project |  |  |  | C,AS | in progress,in progress,past due,completed | 9 | https://trello.com/c/lHL2Veb1
Completed | [archived] functional requirements for automated 3DR |  |  |  | KK | completed | 1 | https://trello.com/c/b4nrf9F2
Completed | [archived] check with Raytrix about local users of camera |  |  |  | KK | completed | 23 | https://trello.com/c/dY5vh3rp
Completed | [archived] talk with ROV pilots about scanning preferences |  |  |  | AS,KK | completed | 25 | https://trello.com/c/LCDbPrn4
Completed | [archived] Follow up on delivery date for Coherent laser |  |  |  | KK | completed | 20 | https://trello.com/c/14qLidEy
Completed | [archived] Discuss ship schedule for 2018 |  |  |  | KK | completed | 19 | https://trello.com/c/Hvzdh2Sa
Completed | [archived] Follow up with Coastal Connections on high power patch cables and fiber end caps |  |  |  | DK | completed | 5 | https://trello.com/c/L3ZQ8tPD
Completed | [archived] find out if we can export notes to email and take snapshots to upload to project library |  |  |  | KK | completed | 32 | https://trello.com/c/IvCvXUjv
Completed | [archived] use trello |  |  |  | C | completed | 31 | https://trello.com/c/5gQUMEGQ
Completed | [archived] Bound translation rate of 3DR based on functional requirements (size, z-res) |  |  |  | KK | partially completed,completed | 22 | https://trello.com/c/6dbue7bF
Completed | [archived] Alana will adopt trello.com |  |  |  | AS | in progress,completed | 27 | https://trello.com/c/rNTnNW4K
Completed | [archived] call Terry and ask about 90% power beam diameter and actual beam size from lasers being shipped |  |  |  | DK | completed | 34 | https://trello.com/c/jrSuSt1R
Completed | [archived] Figure out cooling solutions for running new laser on bench |  |  |  | DK,JE | in progress,partially completed,completed | 10 | https://trello.com/c/UzIE7vos
Completed | [archived] check out labor budget for 2D-3D |  |  |  | KK | completed | 35 | https://trello.com/c/VPUBmYJH
[archived] Purchases Needed Before Year-End | Pencil camera for laser sheet | [5 empty] | 13 | https://trello.com/c/sIzWKqtX