## Slide 1: Park&Fly
Year-long AUV deployment w/ periodic or event-driven monitoring.
Build 2 AUVs
  Program 1: feasibility study of benthic monitoring (Ken Smith)
  Program 2 : 2019 mud-volcano monitoring in Arctic (Charlie Paull).
Far-reaching concept, cross-field applicability:
  on-demand monitoring, field-residence
  Event response
  Station-keeping power generator

## Slide 2: Near-term opportunities
Benthic AUV (Ken)
4 deep transects in 12 months.
Sample w/down-looking camera one way, MBES the other way.
Highly desirable: Event-triggered response.
Arctic AUV (mud volcanoes, Charlie)
6 under-ice surveys in 12 months
MBES & SSS
Highly desirable: Event-triggered response.
Ship date: April 2019
Notes
Camera: low-altitude / low-speed
Trigger: a-comms from sediment event sensor.
Notes
300m<D< 750m depending on volcano
Trigger: sound-pressure level from eruption.

## Slide 3: Risk elements
Schedule (arctic AUV 2019 launch window).
Long-term environmental exposure.
Long-duration.
Robust docking/undocking.
Unattended boot reliability.
Guaranteeing data quality & integrity.
Extended duration S/W error-handling.
Testing long mission in a short time.
Cannot monitor AUV progress while under-ice.

## Slide 4: Proposed Approach
Risk | Approach
Schedule | ramp-up funding July 2016 resource continuity go/nogo gates
Long-term environmental exposure | all Ti/plastic larger oil reserve / testing
Long-duration | hibernation battery chemistry: trade study
Robust docking | Lots of testing
Unattended boot | testing/fix
Data quality/integrity | testing/fix
S/W error-handling | testing/fix
Testing long-duration in short time | see Test Sequence
No progress monitoring under-ice | fail-safe mission aborts

## Slide 5: Proposed Test Sequence

## Slide 6
USBL transponder
acoustic release
anchor
float
iUSBL
science payload
battery
control
LBL (x4)
Avtrak
(track&comms)
INS/DVL
hibernation controller
nose
trigger:
a-modem (benthic)
eruption detector (arctic)
Notional Vehicle
emergency scuttle
corrosion-free exterior
AUV Dock
Opt.
Data
Power
Transfer

## Slide 7
MBARI Dock

## Slide 8: Docking Sequence
N
E
Outer Marker
Waypoint
Dock
Bearing
Inertially Fixed
Coordinates
y Cross-Track Error
Heading
Current
Vehicle
Pure Pursuit Homing & Navigation Fix
Cross-track control (Waypoint)
Cross-track USBL control (Docking)
-DY
4 states; DY, r, y, v
DY is heading deviation
y is cross-track error
1
2
3
yB
xB

## Slide 9: Docking State Transition Diagram
Flight
(Waypoints,
Setpoints)
Docking
Homing
Stopped
Missed
Approach
Undocking
Electrical
Dock
Contact
Pin
Inserted

## Slide 11: Docking Video
Will show other three docks last

## Slide 12: New Design elements
Must have
  Benthic payload.
  Docking system.
  Hibernation controller.
  Corrosion-free exterior.
  Extended duration s/w.
  Fail-safe aborts:
    when docked: stay docked.
    when undocked: park on seafloor.
Highly desirable
  Event-triggered response

## Slide 13: Timelines

## Slide 14: WBS: see spreadsheet

## Slide 15: Resources
year | labor | ship time
2016 (acceleration) | Brett: +1month Rob: +2 weeks Hans: + 1 month (MK: 1 day/week) | 3 days
2017 | 5 FTEs: design/fab/testing | 10 days
2018 | 5 FTEs: fab/assembly/at-sea testing | 10 days
2019 | 2 deployments | 5 days (contingency)
2020 | 2 recoveries | n/a

## Slide 16: General Atomics - Notional

## Slide 17: WPDX Medium Power Data Sheet MBARI/Maughan
Power:
  150 Watt continuous, 240 Watt peak (1 hr), resonant transfer using PowerByProxi technology
  Voltage: 24v DC input and output
  Current: 6 Amp output
  Efficiency: ~75%
Data:
  100 Mbps ethernet
  Option RF: 2.4 GHz point to point Ubiquity Radio, 10mW nominal, adjustable to 600mW
  Option Optical: ‘work in progress’
0 to 5 mm separation (derated from 1cm to allow for potting thickness)

## Slide 18: Block Diagram of What we want to build for MARS Toast goes in the Toaster
Input:
375v @ 2 amps
or
24v @ 30 amps
Load Light
Resonant Power
Load Control / Mon
802.11 PtP Radio
Ethernet Switch / Status Mon
Inrush Lim / 375 to 24v
150W continuous
240W peak

## Slide 19: Backups

## Slide 20: Park&Fly: Notional CONOPS
Arrive at site
Deploy the dock and LBL
Prep the AUV
Launch the AUV
Run first transect
Park
Parking verification
Depart site
AUV periodically parks and flies
Return to site
Recover AUV
Recover dock and LBL (minus anchor)