## WBS
Phase | Task # | Task name
1 | Risk Reduction
| 1.1 | Long-term environmental exposure
|  | 1.1.1 | Define corrosion-free mods
|  | 1.1.2 | Assess oil leakage effect
|  | 1.1.3 | Battery leaking
| 1.2 | Robust docking
|  | 1.2.1 | Set pass-fail criterion
|  | 1.2.2 | Review MBARI docking data
|  | 1.2.3 | Model USBL error
|  | 1.2.4 | Simulate performance
|  | 1.2.5 | Define requirements
|  | 1.2.6 | Solicit quote for existing docking system
| 1.3 | Unsupervised boot reliability
|  | 1.3.1 | Set the pass/fail criterion
|  | 1.3.2 | Define the measurement protocol
|  | 1.3.3 | Measure the propability of not booting correctly
|  | 1.3.4 | Identify the boot reliability bottlenecks
|  | 1.3.5 | Make improvements
|  | 1.3.6 | Re-measure the probability of not booting correctly and identify cause
| 1.4 | System architecture
|  | 1.4.1 | Define CONOPS
|  | 1.4.2 | Address risk elements
|  | 1.4.3 | Define vehicle architecture
|  | 1.4.4 | Make subsystem make/buy decisions
|  | 1.4.5 | Update existing design plan
|  | 1.4.6 | Write engineering trials plan
| 1.5 | Management
|  | 1.5.1 | Conceptual Design Review
|  | 1.5.2 | First Go/No-go gate
2 | Design, Fab, and Integration
| 2.1 | Corrosion-free exterior
|  | 2.1.1 | Define design changes
|  | 2.1.2 | Review at PDR
|  | 2.1.3 | Fabrication
|  | 2.1.4 | Vehicle assembly
| 2.2 | Docking design
|  | 2.2.1 | Write down the specification
|  | 2.2.2 | Write down the test plan
|  | 2.2.3 | Architect the system
|  | 2.2.4 | Review design at PDR
|  | 2.2.5 | Acquire/Design the algorithm
|  | 2.2.6 | Acquire/Design the dock
|  | 2.2.7 | Acquire/Design the AUV docking module
|  | 2.2.8 | Review design at CDR
|  | 2.2.9 | Fabrication
|  | 2.2.10 | Assembly
|  | 2.2.11 | Execute the test plan
|  | 2.2.12 | Fix bugs & re-test
|  | 2.2.13 | Write documentation and archive
| 2.3 | Hibernation controller
|  | 2.3.1 | Write down the specification
|  | 2.3.2 | Write down the test plan
|  | 2.3.3 | Architect the system
|  | 2.3.4 | Review design at PDR
|  | 2.3.5 | Acquire/design the PCB
|  | 2.3.6 | Acquire/design the firmware
|  | 2.3.7 | Review design at CDR
|  | 2.3.8 | Fabrication
|  | 2.3.9 | Assembly
|  | 2.3.10 | Execute the test plan
|  | 2.3.11 | Fix bugs and re-test
|  | 2.3.12 | Write documentation and archive
| 2.4 | Extended duration s/w
| 2.5 | Low-altitude flight behavior
| 2.6 | Emergency systems
| 2.7 | Benthic payload design
| 2.8 | Arctic payload design
| 2.9 | First vehicle Integration
| 2.10 | Management
|  | 2.10.1 | PDR
|  | 2.10.2 | Docking Make/buy decision
|  | 2.10.3 | CDR
|  | 2.10.4 | Post-CDR go/no-go gate
|  | 2.10.5 | 2nd vehicle fab go/no-go gate
| 2.11 | Volcano eruption trigger ***
| 2.12 | Control plane module ***
| 2.13 | Second vehicle integration***
3 | Engineering trials
| 3.1 | Docking tests
|  | 3.1.1 | Homing
|  | 3.1.1 | Docking
|  | 3.1.2 | Undocking
| 3.2 | Hibernation tests
|  | 3.2.1 | Short-duration hibernation (1h)
|  | 3.2.2 | Medium-duration hibernation (24h)
|  | 3,2,3 | Long-duration hibernation (7 days)
| 3.3 | Payload tests
|  | 3.3.1 | Benthic payload tests
|  | 3.3.2 | Arctic payload tests
| 3.4 | Extended duration tests
|  | 3.4.1 | 24h duration tests @ nearshore
|  | 3.4.2 | Arctic AUV @ MARS for 3 months
|  | 3.4.3 | Benthic AUV @ station M for 1 week
4 | Benthic AUV Trials
| 4.1 | Test plan
| 4.2 | Test readiness review
| 4.3 | Testing preps
| 4.4 | Vehicle deployment
| 4.5 | Vehicle recovery
5 | Arctic AUV Trials
| 5.1 | Test plan
| 5.2 | Test logistics
| 5.3 | Test readiness review
| 5.4 | Shipping of test equipment
| 5.5 | Mobilization
| 5.6 | Vehicle deployment
| 5.7 | Vehicle recovery
| 5.8 | Demobilization
| 5.9 | Shipping back of equipment

## Timelines
| 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
AUV Reliability
System Architecture
Hibernation Controller
Homing Reliability
Docking to Riser
Detailed Design
Vehicle Fab
3 month test at MARS
1 year test at MARS
Repair and Refine
Science Opps
FAB
CONCEPT REVIEW
PDR
CDR
END OF FAB
END ENG TRIALS
BENTHIC AUV LAUNCH
BENTHIC AUV SERVICE
1 Year MARS test
Repair and Refine
MILESTONE
GO/NOGO GATE
START ENG TRIALS
GO/NOGO 2ND AUV
Ready to ship or deploy
3 MONTH BUFFER