## WBS
Phase | Task # | Task name |  | Hobson | Thomas | Kemp | McEwen | Kemp | McEwen
1 | Risk Reduction
| 1.1 | Boot reliability
|  | 1.1.1 | Set the pass/fail criterion
|  | 1.1.2 | Define the measurement protocol
|  | 1.1.3 | Measure the propability of not booting correctly
|  | 1.1.4 | Identify the boot reliability bottlenecks
|  | 1.1.5 | Make improvements
|  | 1.1.6 | Re-measure the probability of not booting correctly and identify cause
|  | 1.1.7 | Assess if reliable unattended booting is possible
| 1.2 | Leakage
|  | 1.2.1 | Set the pass/fail criterion
|  | 1.2.2 | Define the measurement protocol
|  | 1.2.3 | Measure the leakage rate
|  | 1.2.4 | Identify the leak sources
|  | 1.2.5 | Make improvements
|  | 1.2.6 | Re-measure the leakage rate
|  | 1.2.7 | Assess if leakage can be contained
| 1.3 | Long-term exposure
|  | 1.3.1 | Define risky components
|  | 1.3.2 | Set pass/fail criteria
|  | 1.3.3 | Define the measurement protocol
|  | 1.3.4 | Execute the protocol and assess
| 1.4 | Docking
|  | 1.4.1 | Set pass-fail criterion |  |  | 2
|  | 1.4.1 | Review MBARI docking data |  |  | 8
|  | 1.4.2 | Model USBL error |  |  | 8
|  | 1.4.3 | Simulate performance |  |  | 4 | 32
|  | 1.4.4 | Define requirements |  |  | 8
|  | 1.4.5 | Solicit quote for existing docking system |  |  | 8
| 1.5 | System Architecture
|  | 1.5.1 | Define CONOPS |  |  | 2
|  | 1.5.2 | Define system components |  |  | 4
|  | 1.5.3 | Define new subsytem requirements |  |  | 8
|  | 1.5.4 | Make subsystem make/buy decisions
|  | 1.5.5 | Update existing design plan |  |  | 2
|  | 1.5.6 | Write engineering trials plan |  |  | 2
| 1.6 | Management
|  | 1.6.1 | Conceptual Design Review |  |  | 4
|  | 1.6.2 | First Go/No-go gate |  |  | 2
2 | Design, Fab, and Integration
| 2.1 | Docking design
|  | 2.1.1 | Write down the specification
|  | 2.1.2 | Write down the test plan
|  | 2.1.3 | Architect the system
|  | 2.1.4 | Review design at PDR
|  | 2.1.5 | Acquire/Design the algorithm
|  | 2.1.6 | Acquire/Design the dock
|  | 2.1.7 | Acquire/Design the AUV docking module
|  | 2.1.8 | Review design at CDR
|  | 2.1.9 | Fabrication
|  | 2.1.10 | Assembly
|  | 2.1.11 | Execute the test plan
|  | 2.1.12 | Fix bugs & re-test
|  | 2.1.13 | Write documentation and archive
| 2.2 | Hibernation controller
|  | 2.2.1 | Write down the specification
|  | 2.2.2 | Write down the test plan
|  | 2.2.3 | Architect the system
|  | 2.2.4 | Review design at PDR
|  | 2.2.5 | Acquire/design the PCB
|  | 2.2.6 | Acquire/design the firmware
|  | 2.2.7 | Review design at CDR
|  | 2.2.8 | Fabrication
|  | 2.2.9 | Assembly
|  | 2.2.10 | Execute the test plan
|  | 2.2.11 | Fix bugs and re-test
|  | 2.2.12 | Write documentation and archive
| 2.3 | Corrosion-free exterior
|  | 2.3.1 | Define design changes
|  | 2.3.2 | Review at PDR
|  | 2.3.3 | Fabrication
|  | 2.3.4 | Vehicle assembly
| 2.4 | Extended duration s/w
| 2.5 | Low-altitude flight behavior
| 2.6 | Emergency system
| 2.7 | Benthic payload design
| 2.8 | Arctic payload design
| 2.9 | Volcano eruption trigger ***
| 2.10 | Control plane module ***
| 2.11 | First vehicle Integration
| 2.12 | Second vehicle integration***
| 2.13 | Management
|  | 2.13.1 | PDR
|  | 2.13.2 | Docking Make/buy decision
|  | 2.13.3 | CDR
|  | 2.13.4 | Post-CDR go/no-go gate
|  | 2.13.5 | 2nd vehicle fab go/no-go gate
3 | Engineering trials
| 3.1 | docking tests
|  | 3.1.1 | docking
|  | 3.1.2 | undocking
| 3.2 | hibernation tests
|  | 3.2.1 | short-duration hibernation (1h)
medium-duration hibernation (24h)
long-duration hibernation (7 days)
| 3.3 | payload tests
| 3.4 | extended duration tests
|  | 3.4.1 | 6 x runs @ 24h each, shallow water, both vehicles
|  | 3.4.2 | 6 runs @ 1 week each, shallow water, both vehicles
|  | 3.4.3 | 6 runs @ 1 week each @ station M
|  | 3.4.4 | 6 runs @ 1 week each @ simulated mud volcano location
4 | Benthic AUV Trials
| 4.1 | Test plan
| 4.2 | Test readiness review
| 4.3 | Testing preps
| 4.4 | Vehicle deployment
| 4.5 | Vehicle recovery
5 | Arctic AUV Trials
| 5.1 | Test plan
| 5.2 | Test logistics
| 5.3 | Test readiness review
| 5.4 | Shipping of test equipment
| 5.5 | Mobilization
| 5.6 | Vehicle deployment
| 5.7 | Vehicle recovery
| 5.8 | Demobilization
| 5.9 | Shipping back of equipment

## Timelines
|  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
RISK REDUCTION
SYSTEM ARCHITECTURE
DESIGN
FAB
INTEGRATION
AT-SEA ENGINEERING TRIALS
DOCKING
HIBERNATION
BENTHIC PAYLOAD
ARCTIC PAYLOAD
EXTENDED DURATION
BENTHIC AUV TRIALS
ARCTIC AUV TRIALS
CONCEPT REVIEW
PDR
CDR
END OF FAB
END ENG TRIALS
BENTHIC AUV LAUNCH
BENTHIC AUV RECOVERY
ARCTIC AUV LAUNCH
ARCTIC AUV RECOVERY
MILESTONE
GO/NOGO GATE
START ENG TRIALS
GO/NOGO 2ND AUV
ARCTIC AUV SHIPPING
3 MONTH BUFFER