## Slide 1: Park –n- Fly AUV
PI: Ken Smith
Scientists: Ken Smith and Charlie Paull
Project Manager: Brett Hobson
Systems Engineer: Mathieu Kemp
AUV Engineer: Hans Thomas
Controls Engineer: Rob McEwen
EE: Scott Jensen, Paul McGill
SE: Kent Headley, Rich Henthorn
ME: Jon Erickson, Brett Hobson

## Slide 2: Park & Fly AUV – Abstract
Develop the capability for a persistent presence in the deep ocean
Conduct seasonal, seafloor imaging and bioacoustics surveys at Station-M. Without a ship.
Conduct seasonal, seafloor mapping with sidescan and multi-beam sonars to investigate the geologic evolution of mud volcanoes in the Arctic. Under the ice, without a ship, for one year.

## Slide 3: Near-term opportunities
Benthic AUV (Ken)
4 deep transects in 12 months.
Sample w/down-looking camera one way, MBES the other way.
Highly desirable: Event-triggered response.
Arctic AUV (mud volcanoes, Charlie)
6 under-ice surveys in 12 months
MBES & SSS
Highly desirable: Event-triggered response.
Ship date: April 2019
Notes
Camera: low-altitude / low-speed
Trigger: a-comms from sediment event sensor.
Notes
300m<D< 750m depending on volcano
Trigger: sound-pressure level from eruption.

## Slide 4: Approach -1
Stretch AUV operation from a continuous run over 17 hours to ~four 3-hours missions spaced over one year
Park the AUV inside of a docking station between missions and put it to sleep
Use an independent hibernation controller to wake the AUV up, run the checks, start the mission and watch for problems. If the AUV cannot get back to the dock, sink the AUV to the seafloor and wait for help
Optionally trigger the deployments remotely or locally for event response

## Slide 5: Why we think this is Do-able
Strong fleet of Dorado vehicles, spares and operational know-how
Dorado docking success in 2007, and efforts at Bluefin, WHOI/Hydroid and SPAWAR
Long-term deployment of the Benthic Rover
Industrial partnerships (motivated to ensure our success) with Sonardyne (homing), Bluefin, General Atomics (power/data transfer, batteries, homing)

## Slide 6: What are the Risk elements?
Schedule (arctic AUV 2019 launch window)
Long-term environmental exposure
Long-duration
Robust docking/undocking
Unattended boot reliability
Guaranteeing data quality & integrity
Extended duration S/W error-handling
Testing long mission in a short time
Cannot monitor AUV status
Cost and # of operational assets

## Slide 7: Risk Reduction
Risk | Approach
Schedule | ramp-up funding July 2016 resource continuity go/nogo gates
Long-term environmental exposure | all Ti/plastic/FRP larger oil reserve / testing
Long-duration | hibernation battery chemistry: trade study
Robust docking | Lots of testing
Unattended boot | testing/fix
Data quality/integrity | testing/fix
S/W error-handling | testing/fix
Testing long-duration in short time | see Test Sequence
No AUV status | WG for St. M, fail-safe mission abort

## Slide 8: Proposed Test Sequence

## Slide 9: Estimated Resources
year | labor | expense | ship time
2016 (acceleration) | Brett: +1month Rob: +2 weeks Hans: + 1 month (MK: 1 day/week) | $2k | 3 days
2017 | 5 FTEs: design/fab/testing | $100k | 10 days
2018 | 5 FTEs: fab/assembly/at-sea testing | $ 700k | 10 days
2019 | 2 deployments |  | 5 days (contingency)
2020 | 2 recoveries |  | n/a

## Slide 10
USBL transponder
acoustic release
anchor
float
iUSBL
science payload
battery
control
Opt. LBL (x4)
Avtrak
(track&comms)
INS/DVL
hibernation controller
nose
trigger:
a-modem (benthic)
eruption detector (arctic)
Notional Vehicle
emergency scuttle
corrosion-free exterior
AUV Dock
Data & Opt.
Power
Transfer

## Slide 11
2007 MBARI Dock

## Slide 12: ‘07 Docking Video - plays during question period

## Slide 13: End

## Slide 14: Approach -2
Leverage previous work by MBARI and others
  MBARI’s AUV docking (2007), Bluefin, WHOI/Hydroid, General Atomics, SPAWAR
  Benthic Rover – 5 years of continuous (almost) operations at St.M
Build 2 AUVs
  Program 1: Pelagic Benthic Coupling and Carbon Cycling (Smith)
  Program 2 : 2019 mud-volcano monitoring in Arctic (Paull)

## Slide 15: Docking State Transition Diagram
Flight
(Waypoints,
Setpoints)
Docking
Homing
Stopped
Missed
Approach
Undocking
Electrical
Dock
Contact
Pin
Inserted

## Slide 17: New Design elements
Must have
  Benthic payload.
  Docking system.
  Hibernation controller.
  Corrosion-free exterior.
  Extended duration s/w.
  Fail-safe aborts:
    when docked: stay docked.
    when undocked: park on seafloor.
Highly desirable
  Event-triggered response

## Slide 18: Timelines

## Slide 19: WBS: see spreadsheet

## Slide 20: General Atomics - Notional

## Slide 21: WPDX Medium Power Data Sheet MBARI/Maughan
Power:
  150 Watt continuous, 240 Watt peak (1 hr), resonant transfer using PowerByProxi technology
  Voltage: 24v DC input and output
  Current: 6 Amp output
  Efficiency: ~75%
Data:
  100 Mbps ethernet
  Option RF: 2.4 GHz point to point Ubiquity Radio, 10mW nominal, adjustable to 600mW
  Option Optical: ‘work in progress’
0 to 5 mm separation (derated from 1cm to allow for potting thickness)

## Slide 22: Block Diagram of What we want to build for MARS Toast goes in the Toaster
Input:
375v @ 2 amps
or
24v @ 30 amps
Load Light
Resonant Power
Load Control / Mon
802.11 PtP Radio
Ethernet Switch / Status Mon
Inrush Lim / 375 to 24v
150W continuous
240W peak

## Slide 23: Backups

## Slide 24: Park&Fly: Notional CONOPS
Arrive at site
Deploy the dock and LBL
Prep the AUV
Launch the AUV
Run first transect
Park
Parking verification
Depart site
AUV periodically parks and flies
  - At Station-M, could control from shore via wave-glider comm relay
Return to site
Recover AUV
Recover dock and LBL (minus anchor)