## Sheet1
| Week of | System | Mechanical | Electrical | Software | Launch System
1 | 2017-04-03
2 | 2017-04-10
3 | 2017-04-17
4 | 2017-04-24
5 | 2017-05-01
6 | 2017-05-08
7 | 2017-05-15 |  | Drawings for test housing submitted to shop (5/17)
8 | 2017-05-22 |  | Mechanical Design Review (5/25)
9 | 2017-05-29 |  | Drawings of chassis, housing, & bases finalized (6/1) |  |  | Launch/recover review
10 | 2017-06-05 |  |  | Order the final tether
11 | 2017-06-12 |  | Parts for test housing complete (6/15)
12 | 2017-06-19 |  | Test housing on Paragon & All drawings to shop (6/20)
13 | 2017-06-26 |  |  | Top side system built
14 | 2017-07-03
15 | 2017-07-10
16 | 2017-07-17 |  | All mechanical parts ready for assembly (7/20)
17 | 2017-07-24
18 | 2017-07-31 |  | Pressure test of final housing (8/1)
19 | 2017-08-07
20 | 2017-08-14 |  | Assemble electronics into final housing (8/15)
21 | 2017-08-21
22 | 2017-08-28 | Test Tank Testing
23 | 2017-09-04
24 | 2017-09-11 | R/V John Martin
25 | 2017-09-18
26 | 2017-09-25
27 | 2017-10-02 | Deployment | Deployment | Deployment | Deployment | Deployment