Project team responses

901704 Benthic Observation System

Rating: 2

MT contact: Scholin

Management Team Feedback

General Comments:

Thank for preparing such a clear proposal. We’re pleased to see how this is going -- this project is of keen interest to the Packard Foundation.

For 2018 please focus on delivering the 8-camera system to TNC. Make sure your TNC counterparts procure a load-rated winch so that it can be used on any vessel.

We plan to purchase the winch/tether in late 2017 using funds from the TNC budget.

Defer transfer of the 2-camera system to Kelly B-B for now. We think a more productive use of your time would be to fully understand what is required to meet the needs of Kelly and others before undertaking further modifications of the 2-camera system. For example, would the mini-ROV smart clump meet Kelly’s needs?

Thank you. That did seem like a lot to accomplish in one year.

You mentioned use of the Martin – is that provided by MLML with support from TNC or other? We don’t see a request for the Martin in your budget.

Yes, TNC is paying for all of the Martin ship time. Sorry, I overlooked mentioning that in the proposal.

For Phase 2 please address the following:

Adjust budget request to reflect the focus on the 8-camera system only, and adjust your labor request accordingly (see below).

You requested use of the Paragon, but no operator is identified. Jared?

Yes, Jared will be the operator. I mentioned him in the proposal, but I forgot to enter him in the labor budget. He is now down for a total of 30 hours in 2018.

Eric Martin is oversubscribed. Please reduce this request from 240 hours to 140 hours.

I have adjusted Eric’s hours down to 140.

Kent Headley's time should be reduced from 360 hours to 160 hours as there are no requirements to integrate contextual sensors.

I have adjusted Kent’s hours down to 160.

| 2018 Project Start Date: 01/01/2018 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Total Resources for each resource category for all milestones listed here |
| --- | --- | --- | --- | --- | --- | --- |
| Milestone Date | 02/2018 | 08/2018 | 09/2018 | 10/2018 | 12/2018 |  |
| Milestone Description | Launch/Recovery Spec/order | Design/Build 8-cam sys | Test 8-cam System | Deploy 8-cam sys | Xfer 2-cam sys to KBB |  |
| Electrical Engineer | CK: 60 | CO: 300 CK: 300 | EM: 120 CO: 60 CK: 120 | CK: 80 |  | CK: 560 CO: 360 EM: 140 |
| Software Eng-Embedded |  | KH: 120 | KH: 40 |  |  | KH: 160 |
| Software Eng-Info Eng |  |  |  |  |  |  |
| Mechanical Engineer | FC: 40 | FC: 300 | FC: 40 | FC: 40 |  | FC: 420 |
| Mechanical Eng-Division |  |  |  |  |  |  |
| Mechanical Eng-Mfg |  |  |  |  |  |  |
| Associate Engineer |  |  |  |  |  |  |
| Electrical Tech |  | 140 | 60 |  |  | 200 |
| Software Tech |  |  |  |  |  |  |
| Mechanical Tech |  | 120 |  |  |  | 120 |
| Machinist |  | 330 |  |  |  | 330 |
| Divers |  |  |  |  |  |  |
| Paragon Operator |  |  | Jared: 30 |  |  | Jared: 30 |

This number should be the same number you entered on the resource requests for this particular resource.