# Fault Detection Meeting

# 08/01/2018

# Attendees

Matt, Eric, Scott, Jon, Alana.

# Housing

Jon went over the proposed housing design:

- 13.8L x 6.0"OD.  The extra length provides ~ 6" to fit the compute and pitch sensor.

- 11.85" inner length x 5.7"ID.

- 7.8 lbs positive buoyancy.

- Rated to 300m.

- Vacuum port, sacrificial anode, 2 connectors.

- Minimum wire clearance: 0.4"

After discussing it, a decision was made to use 3 connectors instead of 2.

# Power budget

Eric went over the power budget:

- 9174 chassis with 3 cards 	2.5W peak.

- AHRS				0.5W

- computer			6 to 12W depending on model

- TOTAL				9 to 15W depending on model.

The LCB can source 2A, and has previously been modified to source 5A.

Conclusion:  the LCB can deliver the required power.

# Computer

Eric went over the computer he's planning or ordering:

- conga-MA5 computer running Windows 10.

- ConnectTech COM Expresss Type 10 carrier board.

Eric has identified two models of interest with different clock speed and number of cores. A decision was made to order both of them for evaluation.

# TODO

No changes from the July 13 list.

## Connectors (Scott)

Sept 15: order the connectors.

Nov 15: connectors are in-house.

## Housing (Jon)

Oct 1: order the housing.

Nov 15: housing is in-house.

## Integration (al)

Nov 15: start of integration.

Dec 15: end of integration.

## Testing (Matt)

Dec 15: first tank test.

For reference, the timelines submitted by Eric, Scott, and Alana in July 12 email are below, with changes made as a result of this meeting highlighted in yellow.

| Column1 | Scott (mh) | Eric (mh) | Expected Completion Date |
| --- | --- | --- | --- |
| generate power budget |  | 16 | done |
| talk with MCC |  | 4 | done |
| buy and configure computer |  | 40 | Buy (8/1) Configure (9/1) |
| modify the Python code |  | 80 | 1-Nov |
| wiring + connectorization | 80 | 2 | 1-Oct --> pushed to 15 Nov |
| integration | 40 | 40 | 1-Nov --> pushed to 15 Dec |
| maintenance | 20 | 20 |  |
| meetings | 20 | 20 |  |
| TOTAL | 160 | 222 |  |