## labor estimates
Task | Start | End | Scott | Eric
|  |  | (mh) | (mh)
generate power budget |  |  |  | 16
talk with MCC |  |  |  | 4
buy and configure computer |  |  |  | 40
modify the Python code |  |  |  | 80
wiring + connectorization |  |  | 80 | 2
integration |  |  | 40 | 40
maintenance |  |  | 20 | 20
meetings |  |  | 20 | 20
TOTAL |  |  | 160 | 222

## DAQ and CTR signals
DAQ
current + | current -
voltage+ | voltage -
stringpot + | stringpot -
CTR
encoder A | encoder B | encoder gnd

## project timelines
Task | subtask | 2018 | [5 empty] | 2019
|  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Mass-shifter
parameter sensitivity
time of fault detection
payload fab
payload integration
tank testing
at-sea testing | bar: 2019 Jan to 2019 Feb
PHM presentation
Journal paper | bar: 2019 Mar
Thruster
model building
payload fab
payload integration | bar: 2019 Jan
tank testing | bar: 2019 Feb
at-sea testing | bar: 2019 Mar
parameter extraction | bar: 2019 Mar to 2019 Apr
at-sea re-testing | bar: 2019 Apr
AIAA paper
AIAA presentation | bar: 2019 Jan
Journal paper | bar: 2019 May
Feasibility studies
DVL | bar: 2019 Jun
Power buoy | bar: 2019 Jun
Reinforcement learning
simulation | bar: 2019 Jul to 2019 Sep
microROV testing | bar: 2019 Oct to 2019 Dec