# Fault Detection Meeting

# 07/13/2018

# Attendees

Matt, Eric, Scott, Jon.

# Payload content

MK went over the payload content - see the companion PowerPoint:

- Data acquisition: we'll use a COTS NI solution: 9174 chassis, 9239 DAQ, and 9361 counter.

- Computer:  we plan on using a CongaTec PA5. Eric will make a final decision Sept 1.

- Absolute position sensor: we will use the TE SP1-4.

- Signal conditioning: we plan on using a custom PCB.

- The data acquisition hardware and the computer will live in their own housing.

- The signal conditioning PCB will live in the vehicle housing.

# Housing options

Option 1:

- 5.75" ID x 9.5" internal length. Both ID and length could be made bigger.

- Compatible with either wet-mateable or pbof connectors.

- Estimated cost: $3 to 5K.

- Estimated housing lead time: 4 to 6 weeks.

- Machined in-house.

- Estimated connector lead time: 6 to 8 weeks.

Option 2:

- A design based on the ESP housing: 12" OD x variable length.

- Uses an 84-in penetrator.

- Estimated cost: $30 to 40K.

- Estimated lead-time: 10 to 16 weeks.

# Housing decision

Option 1: although option 2 offers more room and better noise immunity, it is not achievable given the project's time and budget constraints.

# Revised schedule

Given the required lead times (8 weeks) and people's availability, the critical milestones have been revised as follows:

## Connectors (Scott)

Sept 15: order the connectors.

Nov 15: connectors are in-house.

## Housing (Jon)

Oct 1: order the housing.

Nov 15: housing is in-house.

## Integration (al)

Nov 15: start of integration.

Dec 15: end of integration.

## Testing (Matt)

Dec 15: first tank test.

For reference, the timelines submitted by Eric, Scot, and Alana in July 12 email are below, with changes made as a result of this meeting highlighted in yellow.

| Column1 | Scott (mh) | Eric (mh) | Expected Completion Date |
| --- | --- | --- | --- |
| generate power budget |  | 16 | 1-Aug |
| talk with MCC |  | 4 | done |
| buy and configure computer |  | 40 | Buy (8/1) Configure (9/1) |
| modify the Python code |  | 80 | 1-Nov |
| wiring + connectorization | 80 | 2 | 1-Oct --> pushed to 15 Nov |
| integration | 40 | 40 | 1-Nov --> pushed to 15 Dec |
| maintenance | 20 | 20 |  |
| meetings | 20 | 20 |  |
| TOTAL | 160 | 222 |  |