## Slide 1: Fault Detection March 14
Concept Design Review scheduling
Task updates
Failure Injection pros/cons

## Slide 2: 1. Concept Design Review Scheduling
Milestone | Completion date | Entry criteria
Concept Design Review | April 4 | Risk elements retired System diagram done System requirements done
Design Review | May 31 | Design meets requirements Hardware verification done
Requirements verification review - bench | August 30 | Requirements tested on the bench.
Requirements verification review - tank | October 31 | Requirements tested in the tank.
First at-sea trial | November 30 | Test Readiness Review

## Slide 3: Top-level requirements
SYS. System requirements
SYS01. The system will be composed of 1) a predictive fault-detection subsystem, 2) a fault-injection subsystem, and 3) a fault-injection mission scripting tool, and 4) a post-mission analysis tool.
SYS02. The fault-detection and fault-injection subsystems will run on dedicated hardware that fits inside the LRAUV main housing, and that runs off power provided by the LRAUV.
SYS03. The fault-detection and fault-injection subsystems will have access to the vehicle data described in the Data Sources appendix.
SYS034. The system will be testable on the bench, in the tank, and at sea.
SYS04. The fault-detection and fault-injection processor will be selected to 1) support computationally-intensive floating-point algorithms, 2) support a substantial scaling-up of the computational load.
SYS05. The fault-detection and fault-injection applications will be written in Python.
SYS06. The system will be capable of native compilation.
SYS07. The system will support fast file transfer without having to recover the vehicle.

## Slide 4: Requirements 1st cut – cont’d
FD. Fault Detection
FD01. The fault-detection subsystem will detect the following mass-shifter faults:
  Limit-tab current overload
  Loose lead-screw
  Position sensor failure
FD02. The fault-detection subsystem will estimate the remaining time to failure.
FD03. Optionally, the fault-detection subsystem will also detect the following thruster faults:
  Current overload
  Magnetic coupler failure
  Propeller loss
and estimate the remaining time to failure.

## Slide 5: Requirements 1st cut – cont’d
FI. Fault Injection
FI01. The fault-injection subsystem will be capable of injecting the mass-shifter faults enumerated in FD01:
FI02. The fault-injection subsystem will be capable of injecting faults during a mission.
FI03. The fault-injection subsystem will be capable of injecting faults reversibly, repeatedly, and controllably.
  reversibly: can return to nominal.
  repeatedly: can do it multiple times during a mission.
  controllably: has hooks to control the fault parameters: rate of fault application, fault magnitude, etc.
FI04. The fault-injection subsystem will be capable of coordinating fault injection and actuator motion.
  i.e. if we inject a mass-shifter failure, we ought to make sure the mass-shifter is commanded to move.
FI05. Optionally, the fault-injection subsystem will be capable of injecting the thruster faults enumerated in FD03
  Current overload
  Magnetic coupler failure
  Propeller loss
and do so in accordance with FI02, FI03, and FI04.

## Slide 6: Risk Elements
risk element | point person | approach
getting required sensor resolution, noise level, and repeatability | Mark | analyze high-sampling rate data for required noise rejection analyze block-by-block the expected noise level derive reqs for speed sensing from position
reversible/repeatable/controllable fault-injection | MK | - hold a brainstorming session - rank candidate solutions
overload fault recovery | Eric | meet with LRAUV s/w people to assess the exact sequence of events after an overload identify options for shortening the recovery time
getting data from the vehicle (pitch, commanded position, encoder position) | Eric | identify possible sources, e.g. LCM, separate sensor, data sniffing, and their properties , e.g. rate, packet format. identify pros/cons of each.
GSAP appropriatness: compatibility with Python, and implementation overhead. | MK | SPECIFY APPROACH THIS WEEK

## Slide 7: Labor burn
Person | Hours to date | Hours budgeted
Mark | 32.5 | 480
Eric | 21 | 400
S/W | 0 | 1713
Jon | 0 | 120
Jared, Mike Parker, Jose, Brian | 0 | 284

## Slide 8: 2. Task updates

## Slide 9: 3. Fault Injection Pros/Cons: Overload
Concept | Pros | Cons
1. Adjustable limit tab |  | 
2. Retractable limit tab |  | 
3. Retractable, secured to tab |  | 

## Slide 10: Fault Injection Pros/Cons: Lead Screw
Concept | Pros | Cons
1. Clutch replaces torque coupler |  | 
2. Clutch replaces flange |  | 
3. Solenoid-mounted pin |  | 
4. Manual & easier to align/insert |  | 

## Slide 11: Fault Injection Pros/Cons: Bad sensor
Concept | Pros | Cons
1. Continuous extender |  | 
2. Binary extender |  | 
3. Manual / slots |  | 
4. Voltage injection |  | 

## Slide 12: BACKUPS