# Fault Detection Meeting

# 10/03/2018

# Attendees

Matt, Scott.

# Connectors and cables

- Connectors are done.

- Cables are long-lead (December). The schedule for Design, Bring-up, and Integration will go as planned - the moment the cables come in we'll schedule the first tank test.

# PCB design

- Layout for the in-vehicle PCB is done. Next step is ordering. We will order 5 boards, and populate 2 (1 for bring-up, 1 spare).

- Layout for the external bottle PCV is underway, and expected to be complete next week. Next step will be ordering: we'll order 5 and populate 4 (1 each for bring-up/vehicle, Eric, Lauren, and spare).

# TODO

## Scott

- Oct 10: order the PCBs.

- Oct 17: start populating.

- Oct 24: start board bring-up

- Oct 31: deliver PCBs.

## Jon

- Sept 27: check housing fab status.

- Oct 31: order parts for the long nose. The long-leadtime item is the shell (4 months). If all goes to plan, we will switch to the long-nose configuration at the end of February 2019.

## Eric

- Sept 27: Finish the LCM install.

- Oct 3: Test and integrate the Microstrain AHRS.