Fault Detection Meeting
10/03/2018
Attendees
Matt, Scott.
Connectors and cables
· Connectors are done.
· Cables are long-lead (December). The schedule for Design, Bring-up, and Integration will go as planned - the moment the cables come in we'll schedule the first tank test.
PCB design
· Layout for the in-vehicle PCB is done. Next step is ordering. We will order 5 boards, and populate 2 (1 for bring-up, 1 spare).
· Layout for the external bottle PCV is underway, and expected to be complete next week. Next step will be ordering: we'll order 5 and populate 4 (1 each for bring-up/vehicle, Eric, Lauren, and spare).
TODO
Scott
· Oct 10: order the PCBs.
· Oct 17: start populating.
· Oct 24: start board bring-up
· Oct 31: deliver PCBs.
[bookmark: _GoBack]Jon
· Sept 27: check housing fab status.
· Oct 31: order parts for the long nose. The long-leadtime item is the shell (4 months). If all goes to plan, we will switch to the long-nose configuration at the end of February 2019.
Eric
· Sept 27: Finish the LCM install.
· Oct 3: Test and integrate the Microstrain AHRS.
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