# Fault Detection Meeting

# 10/17/2018

# Attendees

Matt, Jon, Eric

# Integration

The integration will start after Eric returns from his cruise. The tentative integration sequence is:

- Install the connectors.

- Connect the chassis.

- Test the noise level.

- Check the LCM interface.

- Run the fault-detection application on the bench.

- Run the fault-detection application in the tank.

# PCB design

- The PCBs were ordered. The ship date is Oct 22.

- Parts for 5 sets of PCBs are on order.

# Eric

- now working on the counter/DAQ integration.

- The plan is to, by the time Eric leaves for his cruise, have working code for all the modules (DAQs, AHRS, LCM string, fault-detection algorithm, logging) + a basic skeleton of the main application.

- Eric and MK will meet next Wednesday to go over the computer.

- Computer credentials: user = p-lab   pw = faultdetection

# Scott

- Oct 25: start populating.

- Oct 29: start bring-up

- Nov 5: deliver working PCBs.

# Jon

- The housing is in-house!

- Next step: pressure testing.

- Need to order the standoffs.

- Oct 31: order parts for the long nose. The long-leadtime item is the shell (4 months). If all goes to plan, we will switch to the long-nose configuration at the end of February 2019.

# TODO

Jon:

- order the standoffs

- pressure-test the housing

Scott:

- bring up the PCBs after Jose's done.

Eric:

- Initial release of the software modules + main app.

- Sit down with MK next Wednesday to go over the computer + software.