# Fault Detection Meeting

# 09/19/2018

# Attendees

Matt, Eric, Jon, Scott.

# Connectors

- Scott reviewed the wiring diagram.

- Cable length: given the 124mm minimum bend radius, we'll use a ~6" gap between the payload and vehicle housings. As a result, the housing will stick out by a few inches until we switch to the long nose configuration (end of February 2019).

- Ordering date: shooting for Sept 25.

# PCB design

Follow-up to a meeting between SJ and MK earlier this week:

- The PCB design will be reviewed at our Oct 3 meeting.

- We will populate 3 of each board (payload, dev, spare), and populate the others as needed.

- We're shooting for having the boards ready for integration into the payload 4 weeks later (Oct 31).

# Computer

- The chassis is now assembled.

# TODO

## Scott

- Sept 25: order the connectors.

- Oct 3: review the PCB designs at our meeting.

- Oct 31: PCBs in-house, populated, tested, and ready for integration.

## Jon

- Sept 27: check housing fab status.

- Oct 31: order parts for the long nose. The long-leadtime item is the shell (4 months). If all goes to plan, we will switch to the long-nose configuration at the end of February 2019.

## Eric

- Sept 27: Finish the LCM install.

- Oct 3: Test and integrate the Microstrain AHRS.