## Sheet1
Micro Node |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Design Internal Electronics | Chad | 2020-01-06: Done
Order/Assemble Elec Parts | Chad | 2020-01-06: Done
Populate Vicor Board | ET Shop | 2020-01-06: Done
Design Housing | Mike | bar: 2020-01-27
Specify Tether Connection | Dale/Mike | bar: 2020-01-20
Design Internal Bracketry | Mike | bar: 2020-01-27
Fabricate Housing | Mach Shop | bar: 2020-03-16
Fabricate Internal Bracketry | Mach Shop | bar: 2020-03-16
Assemble Internal Electronics | ET Shop | bar: 2020-03-30
Test Wired Electronics | Chad | bar: 2020-04-06
Attach Tether | ET Shop | bar: 2020-04-13
Final Assembly | Chad
W2 Cable Assy |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Cut to Length | ET Shop | bar: 2020-01-27
Connectorize One End | ET Shop | bar: 2020-01-27
W3 Cable Assy |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Cut to Length | ET Shop | bar: 2020-01-27
Micro Node J-Tube |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Design Internal Electronics | Chad | 2020-01-06: Done
Order/Assemble Elec Parts | Chad | 2020-01-06: Done
Fabricate Housing | Mach Shop | bar: 2020-03-02
Assemble Internal Electronics | ET Shop | bar: 2020-03-09
Attach Cable W2 | ET Shop | bar: 2020-03-09
Attach Cable W3 | ET Shop | bar: 2020-03-09
Final Assembly | ET Shop | bar: 2020-03-16
W4 Cable Assemblies (4) |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Cut to Length | ET Shop | bar: 2020-02-24
Distribution Node |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Design Internal Electronics | Chad | 2020-01-06: Done
Order/Assemble Elec Parts | Chad | 2020-01-06: Done
Populate Vicor Board | ET Shop | 2020-01-06: Done
Design Housing | Mike | bar: 2020-02-10
Design Internal Bracketry | Mike | bar: 2020-02-10
Fabricate Housing | Mach Shop | bar: 2020-03-30
Fabricate Internal Bracketry | Mach Shop | bar: 2020-03-30
Assemble Internal Electronics | ET Shop | bar: 2020-04-06
Attach Cable W3 | ET Shop | bar: 2020-04-06
Attach Cables W4A-W4D | ET Shop | bar: 2020-04-06
Test Wired Electronics | Chad | bar: 2020-04-13
Software Testing | Dale/Chad | bar: 2020-04-20
Final Assembly | Chad
Tether |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Tether Delivery | Shipping | bar: 2020-03-09
Initial Tether Testing | Chad | bar: 2020-03-16
Integrate with Micro Node | ET Shop | bar: 2020-03-30
W5 Cable Assemblies (4) |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Cut to Length | ET Shop
Chamber #1 J-Tube |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Design Internal Electronics | Chad | 2020-01-06: Done
Order/Assemble Elec Parts | Chad | 2020-01-06: Done
Fabricate Housing | Mach Shop | bar: 2020-03-02
Assemble Internal Electronics | ET Shop | bar: 2020-03-09
Attach Cable W4A | ET Shop | bar: 2020-03-09
Attach Cable W5A | ET Shop | bar: 2020-03-09
Final Assembly | ET Shop | bar: 2020-03-16
Chamber #1 Electronics (Reuse) |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Design Internal Electronics | Chad | 2020-01-06: Done
Order/Assemble Elec Parts | Chad | 2020-01-06: Done
Populate Vicor Boards (3) | ET Shop | 2020-01-20: Done
Design Housing | Mike | bar: 2020-02-24
Design Internal Bracketry | Mike | bar: 2020-02-24
Fabricate Housing | Mach Shop | bar: 2020-04-06
Fabricate Internal Bracketry | Mach Shop | bar: 2020-04-06
Assemble Internal Electronics | ET Shop | bar: 2020-04-27
Attach All External Cables | ET Shop | bar: 2020-04-27
Test Wired Electronics | Chad | bar: 2020-05-04
Software Testing | Dale/Chad | bar: 2020-05-11
Final Assembly | Chad
Valve Housing #1 (Pre-Built) |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Integrate with Chamber Elec | Chad | bar: 2020-04-27
Software Testing | Dale/Chad | bar: 2020-05-04
Thruster Housing #1 (Pre-Built) |  | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
Integrate with Chamber Elec | Chad | bar: 2020-04-27
Software Testing | Dale/Chad | bar: 2020-05-04