## Sheet1
Known documentation errors and revisions |  | X:\LRAUV5\Drawings\EE\LRAUVWiring\BatterySystem\10021057-APACK\10021057-HALF-PACK-HARNESSES.BOM.2017-06-01-RevC.xlsx
Drawing Number | Description | Problem | Status/Resolution
100221161-2 | Thruster wiring fab. | Need wire length of harness 100221161-2-H1 | Jrosal added lengths. (done)
100221161-10 | Keller pressure sensor wiring | Want to substitute orginal drawing | Cannot find orginal drawing.
100221165-12 | Load control backplane wiring | Need wire length of harness 100221161-12-H3,H1 | Pulled in MiVegas drawing - latest update from Ed. Added harness #'s. Still missing one cable length until board placement in the backplane is finalized.
100221161-14 | Fwd endcap | Need to specify wire length on penetrators, standard length too short. FWD penetrators 120cm 22AWG colored wire. | (done)
100221160-1 | Rear end cap | Need to add port numbers to drawing. Also penetrator call-out on one place only. Need to identify full DGO penetrator PN's. Aft penetrators 90cm 20AWG colored wire. | (done)
10201076 | Charging umbilical | Need to update drawing and make definative umbilical reference (all other versions are wrong) | Pulled in Tethys drawing - the most current revision. (done)
100221160-6 | LRAUV Actuator wiring | Need wire lengths, also suggested wiring revision for easier assembly. Brett has wire lengths. Wiring change for easier assembly OK. | Wire lengths and correct PN's added - (done) 1/30/17.
100221161-14 | Fwd endcap | Brett working through updating drawing with wiring changes with Jose. | Jrosal edited with Brett. (done)
| Battery system | Denis has completed all drawing revisions and is working on a top level drawing with BOM | Jrosal made one. (done)
| Motherboard | Mark needs to revise and re-netlist and move design files into LRAUV5 folder | (Done)
| LCB | Schematic revision needs to be completed to replace obsolete parts. Decision to replace relay with two standard parts. | pending
| Charge Box | Paul nearly finished with updating redlines and re-specifying unavailabe parts and will forward current revision. | Drawings and BOM are in the LRAUV5 folder. Outstanding issues for Paul to resolve: 1. Re-specify front panel Enet connector. 2. Measure wiring lengths and add to drawing. 3 & 4 are two no available parts that Paul re-specified and needs to confirm with Brett.
| Antenna system | Rigid coax PN not specified. Jose will check. | Craig making drawings
| Thruster wiring (internal) | Rev. drawing to new wire lengths. | Jrosal: lengths good. (done)
| Analog only LCB | Ed needs to check for redlines and confirm OK.
| Load backplane | Ed needs to revise for blue wires and re-netlist.