## JOSE ORDER
LRAUV Electrical Assembly BOM
Filename: | /Users/Ben/Desktop/[Copy of REMOVED_partsnotneeded WHOI-ME-BOM-NotPurchased (bh)-(ALK072617).xlsx]Sheet1
100221189-01 Revision: |  |  |  | = calculated values, do not edit
Bill Of Materials June 5,2017 14:58:02
Vehicle Build Quantity: |  | 5
Item | Quantity per vehicle | Reference | Part | Description | Distributor | Distributor Number | Manufacturer | Manufacturer Number | Configuration | Quote Number | PO/Charge Number1 | PO/Charge Number2 | WHOI PO Number | STATUS | WHOI Order Status | Lead / Expected Delivery Time | Cost Each | Cost Each (2) | Mesobot | Spares Qty. | Total Qty for N vehicles | Total Cost for N vehicles | Part order responsibility
1 | 62 | BATT1,BATT2,ETC | NH2034HD34 | Lithium battery 4s2p, NH2034 series, 14.4V, 6.8Ah, 98Wh |  |  | Inspired Energy | NH2034HD34 |  | MBARI Quote 17-07-10 rfq NH CH | 1710929 (QTY:250) |  |  | PO emailed 7/11. Ordered 250 for MBARI | WHOI alrady purchase. Waiting for delivery to MBARI. | 6-8 Weeks | 104.5 |  |  |  | 310 | 32395 | Jrosal
2 | 1 | H1 | 10021057-H06 | RS-232 Half-Pack AFT Harness | MCElectronics |  | MBARI | 10021057-H06 |  | Q6224 | 1710919 (QTY:5) |  |  | PO emailed 7/18. MBARI ordered enough for 5 vehicles. | WHOI needs to purchase |  | 8453.76 |  | 1 |  | 5 | 42268.8 | Jrosal
3 | 2 | H2,H5 | 10021057-H03 | Power Interface Charge Harness | MCElectronics |  | MBARI | 10021057-H03 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
4 | 1 | H3 | 10021057-H04 | Motherboard Charge/Dischage Harness | MCElectronics |  | MBARI | 10021057-H04 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
5 | 1 | H4 | 10021057-H07 | Battery Pack Control Harness | MCElectronics |  | MBARI | 10021057-H07 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
6 | 1 | H6 | 10021057-H05 | RS-232 Half-Pack FRW Harness | MCElectronics |  | MBARI | 10021057-H05 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
7 | 1 | H7 | 10021057-H02 | Aft Bulkhead Charge Harness | MCElectronics |  | MBARI | 10021057-H02 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
8 | 1 | H8 | 10021161-12-H3 | Converter PWM Clock Sync Harness | MCElectronics |  | MBARI | 10021161-12-H3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
9 | 1 | H9 | 10021161-12-H1 | Backplane Power Harness | MCElectronics |  | MBARI | 10021161-12-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
10 | 1 | H10 | 10021161-12-H2 | Backplane Boost Harness | MCElectronics |  | MBARI | 10021161-12-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
11 | 1 | H11 | 10021057-H01 | Aft Bulkhead Charge Harness (Main Umbilical) | MCElectronics |  | MBARI | 10021057-H01 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
12 | 1 | H12 | 10021161-7-H1 | MB Iridium Harness | MCElectronics |  | MBARI | 10021161-7-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
13 | 1 | H13 | 10021161-7-H2 | Iridium Pwr LCB Harness | MCElectronics |  | MBARI | 10021161-7-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
14 | 1 | H14 | 10021161-9-H3 | Iridium to Motherboard Power Harness | MBARI |  | MBARI | 10021161-9-H3 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts. |  | 0 |  | 1 |  | 5 | 0 | Jrosal
15 | 1 | H15 | 10021161-8-H2 | Cradlepoint Ethernet Motherboard Harness | MBARI |  | MBARI | 10021161-8-H2 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts |  | 0 |  | 1 |  | 5 | 0 | Jrosal
16 | 1 | H16 | 10021161-13-H1 | Forward Section Wire Harness | MCElectronics |  | MBARI | 10021161-13-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
17 | 1 | H17 | 10021161-2-H1 | BLDC Motor Harness | MCElectronics |  | MBARI | 10021161-2-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
18 | 1 | H18 | 10021161-4-H1 | Rudder Bulkhead Harness | MCElectronics |  | MBARI | 10021161-4-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
19 | 1 | H19 | 10021161-5-H2 | VB Pressure Switch Harness | MCElectronics |  | MBARI | 10021161-5-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
20 | 1 | H20 | 10021161-3-H1 | Elevator Bulkhead Harness | MCElectronics |  | MBARI | 10021161-3-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
21 | 1 | H21 | 10021161-5-H3 | VB Oil Pump Harness | MBARI |  | MBARI | 10021161-5-H3 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts |  | 0 |  | 1 |  | 5 | 0 | Jrosal
22 | 1 | H22 | 10021161-6-H2 | Mass Shifter Drive Harness | MCElectronics |  | MBARI | 10021161-6-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
23 | 1 | H23 | 10021161-6-H3 | Mass Shifter Optical Switch Harness | MCElectronics |  | MBARI | 10021161-6-H3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
24 | 1 | H24 | 10021161-14-H1 | Forward Bulkhead Harness | MCElectronics |  | MBARI | 10021161-14-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
25 | 1 | H25 | 10021161-13-H3 | DAT Comms Harness | MCElectronics |  | MBARI | 10021161-13-H3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
26 | 1 | H26 | 10021161-2-H2 | Thruster LCB Harness | MCElectronics |  | MBARI | 10021161-2-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
27 | 1 | H27 | 10021161-13-H2 | DAT Modem Power Harness | MCElectronics |  | MBARI | 10021161-13-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
28 | 1 | H28 | 10021161-4-H2 | Rudder LCB Harness | MCElectronics |  | MBARI | 10021161-4-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
29 | 1 | H29 | 10021161-3-H2 | Elevator LCB Harness | MCElectronics |  | MBARI | 10021161-3-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
30 | 1 | H30 | 10021161-5-H1 | VB Valve Motor Harness | MCElectronics |  | MBARI | 10021161-5-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
31 | 1 | H31 | 10021161-6-H1 | Mass Shifter LCB Harness | MCElectronics |  | MBARI | 10021161-6-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
32 | 1 | H32 | 10021161-8-H1 | Cradlepoint PWR LCB Harness | MCElectronics |  | MBARI | 10021161-8-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 1 |  | 5 | 0 | Jrosal
33 | 1 | H33 | 10021161-10-H1 | LCB Analog Pressure Sensor Assembly | MBARI |  | MBARI | 10021161-10-H1 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts |  | 0 |  | 1 |  | 5 | 0 | Jrosal
34 | 1 | H34 | 10021161-9-H1 | Aft DGO-Iridium Coax Cable | MegaPhase |  | MBARI | 10021161-9-H1 |  | SQ171460 | 1710889 (QTY:5) |  |  | PO sent 6/28. Only ordered enough for MBARI | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. | 2017-08-16 | 824.24 |  | 1 | 1 | 6 | 4945.44 | Jrosal
35 | 1 | H35 | 10021161-9-H2 | Aft DGO-mux Coax Cable | MegaPhase |  | MBARI | 10021161-9-H2 |  | SQ171460 | 1710889 (QTY:5) |  |  | PO sent 6/28. Only ordered enough for MBARI | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. | 2017-08-16 | 828.15 |  | 1 | 1 | 6 | 4968.9 | Jrosal
36 | 1 | H36 | 10021161-9-H4 | Quadplexer to Iridium GPS Coax Cable | MegaPhase |  | MBARI | 10021161-9-H4 |  | SQ171460 | 1710889 (QTY:4) |  |  | PO sent 6/28. Only ordered enough for MBARI | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. | 2017-07-27 | 76.4 |  | 1 |  | 5 | 382 | Jrosal
37 | 1 | H37 | 10021161-9-H6 | Quadplexer Cell Coax Cable | MegaPhase |  | MBARI | 10021161-9-H6 |  | SQ171460 | 1710889 (QTY:4) |  |  | PO sent 6/28. Only ordered enough for MBARI | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. | 2017-07-27 | 79.07 |  | 1 |  | 5 | 395.35 | Jrosal
38 | 1 | H38 | 10021161-9-H5 | Quadplexer Wifi Coax Cable | MegaPhase |  | MBARI | 10021161-9-H5 |  | SQ171460 | 1710889 (QTY:4) |  |  | PO sent 6/28. Only ordered enough for MBARI | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. | 2017-07-27 | 174.78 |  | 1 |  | 5 | 873.9 | Jrosal
39 | 2 | H39,H50 | 10021057-PORT1 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
40 | 2 | H40,H51 | 10021057-PORT2 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
41 | 2 | H41,H52 | 10021057-PORT3 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
42 | 2 | H42,H53 | 10021057-PORT4 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT4 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
43 | 2 | H43,H54 | 10021057-PORT5 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT5 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
44 | 2 | H44,H55 | 10021057-PORT6 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT6 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
45 | 2 | H45,H56 | 10021057-PORT7 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT7 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
46 | 2 | H46,H57 | 10021057-PORT8 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT8 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
47 | 2 | H47,H58 | 10021057-CDC1 | Charge Distribution Cables | MCElectronics |  | MBARI | 10021057-CDC1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
48 | 2 | H48,H59 | 10021057-CDC2 | Charge Distribution Cables | MCElectronics |  | MBARI | 10021057-CDC2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
49 | 2 | H49,H60 | 10021057-RS232 | Half-Pack Serial Cable | MCElectronics |  | MBARI | 10021057-RS232 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  | 0 |  | 2 |  | 10 | 0 | Jrosal
69 | 1 | OP1 | Optical Switch | Mass shifter optical home switch | DigiKey | 365-1260-ND | Optek | OPB817Z | [5 empty] | Ben orded QTY:5. Received but MBARI needs to assemble. | WHOI needs to order. Does not show upin their purchased spreadsheet. |  | 3.7 |  | 1 |  | 5 | 18.5 | Jrosal
70 | 1 | PCB1 | 10021057-PIB1 | Power Interface PCB Assembly | Circuits West/Indtec |  | MBARI | 10021057-PIB1 |  | FAB:53184 | 1710852 (QTY:9) |  | E118804 | FAB PO emailed 6/26. MBARI still needs to assemble. | WHOI purchased blank PCBs only. Cost of BOM for this board has yet to be determined. | FAB: 5-Days | 56 |  | 1 | 5 | 10 | 560 | Jrosal
71 | 1 | PCB2 | 11021173rA | Low Voltage Converter Board Assembly | Circuits West/Indtec |  | MBARI | 11021173rA |  | FAB:53185 ASSY:Q-MB2K470 | 1710854 (QTY:12) | 1710891 (QTY:8) | E118804 | FAB PO emailed 6/26. FAB dropped off for assembly 7/14 | WHOI purchased blank PCBs. Sent Marie quote for assembly cost but does not show up in their purchased spreadsheet. | FAB: 5-Days ASSY: 3-4Weeks | 67.86 | 143.35 | 2 | 5 | 10 | 2112.1 | Jrosal
72 | 1 | PCB3 | 10020881rC | Motherboard Assembly | Circuits West/Indtec |  | MBARI | 10020881rC |  | FAB:53188 ASSY:Q-MB2k230 | 1710856 (QTY:14) | 1710872 (QTY:10) | E118804 | FAB PO emailed 6/27. ASSY PO sent 6/28 | WHOI purchased blank PCBs. Sent Marie quote for assembly cost but does not show up in their purchased spreadsheet. | FAB: 5-Days ASSY: 3-4Weeks | 215 | 772.9 | 2 | 6 | 11 | 10866.9 | Jrosal
73 | 1 | PCB4 | 11021164rA | Load Control Backplane | Circuits West/Indtec |  | MBARI | 11021164rA | [5 empty] | Ed modifying schematic | Board is not complete. WHOI unable to order. |  |  |  | 2 |  | 5 | 0 | Jrosal
74 | 1 | PCB5 | HVC | High Voltage Converter Board Assembly |  |  | MBARI | Not Yet Avaliable | [6 empty] | Board is not complete. WHOI unable to order. |  |  |  | 1 |  | 5 | 0 | Jrosal
75 | 1 | PCB6 | PCM-040-332EUPR.A0 | Motherboard Processer SOM |  |  | PHYTEC | PCM-040-332EUPR.A0 |  | 170628C | 1710940 (QTY:6) |  |  | PO emailed 7/13. Order enough for all vehicles and spares. | WHOI needs to pay for this assembly. |  | 299 |  | 1 | 1 | 6 | 1794 | Jrosal
76 | 1 | PCB7 | 98267-0469 | Motherboard to Backplane Flex PCB | DigiKey | WM14131-ND | Molex | 98267-0469 | [5 empty] | Need to order from Digikey | WHOI needs to purchase |  | 2.48 |  | 1 |  | 5 | 12.4 | Jrosal
78 | 1 | PCB9 | 10020864rA | Maxon motor adaptor | PCB MBARI Stock (11) |  | MBARI | 10020864rA |  | FAB:53198 | 1710857 (QTY:49) |  | E118804 | FAB PO emailed 6/26. MBARI still needs to assemble. | WHOI purchased blank PCBs only. Cost of BOM for this board is $0.80. | FAB: 5-Days | 8.8 | 0.8 | 1 | 10 | 15 | 144 | Jrosal
79 | 1 | PCB11 | 10020689rA | MBARI 10020689, Motorized VB Iso Valve Control Board | Circuits West/Indtec |  | MBARI | 10020689rA |  | FAB:53186 ASSY:Q-MB2K540 | 1710853 (QTY:14) | 1710892 (QTY:10) | E118804 | FAB PO emailed 6/26. FAB dropped off for assembly 7/14 | WHOI purchased blank PCBs. Sent Marie quote for assembly cost but does not show up in their purchased spreadsheet. | FAB: 5-Days | 37.34 | 123.12 | 1 | 6 | 11 | 1765.06 | Jrosal
80 | 1 | PCB15 | DAT-903-MF5 | Teledyne Benthos Medium Frequency OEM DAT board set short chassis with remote transducer with right angle mount MCBH12MP. |  |  | Teledyne Benthos | DAT-903-MF5 | [5 empty] | MBARI will not purchase this item. Mark is making a proposal for next year. | WHOI decided not to purchase this item. |  |  |  | 1 |  | 5 | 0 | Jrosal
81 | 1 | PCB16 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-24V-5A | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:5) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | Not needed. |  | 10.4 | 99.75 | 0 |  | 5 | 550.75 | Jrosal
82 | 3 | PCB17,PCB20,PCB25 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-12V | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:23) |  |  | Not needed. |  | 10.4 | 99.75 | 0 | 8 | 23 | 2533.45 | Jrosal
83 | 6 | PCB18,PCB21,PCB24,PCB27,PCB28,PCB30 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 485-BATT-5A | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:35) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | Not needed. |  | 10.4 | 99.92 | 0 | 5 | 35 | 3861.2 | Jrosal
84 | 2 | PCB19,PCB22 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-BATT-5A | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:19) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | Not needed. |  | 10.4 | 99.75 | 0 | 9 | 19 | 2092.85 | Jrosal
85 | 1 | PCB23 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-5V | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:12) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | Not needed. |  | 10.4 | 99.75 | 0 | 7 | 12 | 1321.8 | Jrosal
86 | 2 | PCB26,PCB31 | 10020568r1-0 | Load Control Board (Analog) |  |  | MBARI | 10020568r1-0 | [5 empty] | Ed verifying latest layout. | Board is not complete. WHOI unable to order. |  |  |  | 2 | 4 | 14 | 0 | Jrosal
87 | 1 | PCB29 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | OFF-12V | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:9) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | Not needed. |  | 10.4 | 88.65 | 0 | 4 | 9 | 891.45 | Jrosal
88 | 1 | PCB32 | 100221186rB | RF Multiplexer PCB | PCB MBARI Stock (8) |  | MBARI | 100221186rB |  | ASSY:Q-MB2K545 | No extra fabs needed | 1710901 (QTY:5) |  | FAB dropped off for assembly 7/14 |  |  |  | 123.12 | 1 |  | 5 | 615.6 | Jrosal
89 | 1 | PCB33 | 9602-LP | Iridium/GPS Tracker |  |  | NAL Research | 9602-LP |  | NAL17-0622-01 | 1710859 (QTY:4) |  |  | Received | WHOI already purchased. Waiting for delivery to MBARI |  | 600 |  | 1 |  | 5 | 3000 | Jrosal
90 | 1 | PCB34 | COR IBR600LPE-VZ | 3G/4G/WiFi Router w/ 170585-000 cable |  |  | Cradlepoint | COR IBR600LE-VZ |  | PWS_CradlePointRouterQuote.pdf | 1710862 (QTY:4) |  |  | Received | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. |  | 594 |  | 1 |  | 5 | 2970 | Jrosal
91 | 2 | PCB35,PCB37 | 10021057-BPC1 | MBARI Battery Pack Controller 2017-05-14-RevB sheets 1-11 | Circuits West/Indtec |  | MBARI | 10021057-BPC1 |  | FAB:53187 | 1710855 (QTY:14) |  | E118804 | FAB PO emailed 6/26. Waiting for assembly PO to be approved. | WHOI purchased blank PCBs. WHOI needs to pay for assembly. | FAB: 5-Days | 93.34 |  | 2 | 6 | 16 | 1493.44 | Jrosal
93 | 1 | PCB39 | 100221187rA | Dual UWB Antenna PCB Assembly | PCB MBARI Stock (5) |  | MBARI | 100221187rB |  | FAB:53250 ASSY:Q-MB2K545 | 1710858 (QTY:24) | 1710901 (QTY:25) | E118804 | FAB dropped off for assembly 7/14 | WHOI purchased blank PCBs. WHOI needs to pay for assembly. | FAB: 7-Days | 76.96 | 86.15 | 1 | 20 | 25 | 4077.75 | Jrosal
109 | 24 | SPARE PCB | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | Non Configured | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (QTY:24) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | WHOI needs to pay for blank boards and assemblies. |  | 10.4 | 89.95 | 24 |  | 24 | 2408.4 | Jrosal
110 | 1 |  | CC141-SBSB-24 | Conformable Cable assembly 24in, DC-4 GHz, SMA Female Bulkhead - SMA Female Bulkhead. For antennae mold | MegaPhase | CC141-SBSB-24 |  |  |  | SQ171143-1 | 1710889 (QTY:4) |  |  | PO sent 6/28 | Sent Marie quote for assembly but does not show up in their purchased spreadsheet. | 2017-07-27 | 55.36 |  | 1 |  | 1 | 55.36 | Jrosal