## Electrical
LRAUV Electrical Assembly BOM
Filename: | Q:\BillsOfMaterials\EE_BOM\[LRAUVBuild5MasterElectricalBOM_11_13_23.xlsx]Electrical
100221189-01 Revision: |  |  |  | = Calculated values, do not edit
Bill Of Materials June 5,2017 14:58:02 |  |  |  | = Outstanding issues (order not in, not received) |  | = Deferred or not necessary
MBARI Vehicle Build Quantity: |  | 4 |  | =Items received at MBARI
Item | Quantity per vehicle | Reference | Part | Description | Distributor | Distributor Number | Manufacturer | Manufacturer Number | Configuration | Quote Number | PO/Charge Number1 | PO/Charge Number2 | WHOI PO Number | STATUS | WHOI Order Status | Lead / Expected Delivery Time | Cost Each | Cost Each (2) | MBARI Only (4x) | DHS (WHOI) | DHS Spares | MBARI purchased for WHOI | Mesobot (Kakani) | MBARI Spares Qty. | Total Qty for MBARI ONLY | Total Qty for N + DHS + MesoBot vehicles | Total Cost for MBARI Vehicles | Total Cost per Vehicle | Total Cost for N + DHS + MesoBot vehicles | Cost WHOI owes MBARI | Part order responsibility | NOTES
1 | 62 | BATT1,BATT2,ETC | NH2034HD34 | Lithium battery 4s2p, NH2034 series, 14.4V, 6.8Ah, 98Wh |  |  | Inspired Energy | NH2034HD34 |  | MBARI Quote 17-07-10 rfq NH CH | 1710929 |  |  | PO emailed 7/11. Ordered 250 for MBARI. Received | WHOI purchaseed. Received MBARI. | 6-8 Weeks | 104.5 |  | 248 |  |  | 0 |  |  | 248 | 248 | 25916 | 6479 | 25916 | 0 | Jrosal | Order 250. WHOI ordered their own
1A | 1 |  |  | Wire Harness set 1/2 Pack (Consolidated Harness Set) | MCElectronics |  |  | 10021057rC | [10 empty] | 4 | 1 |  | 0 | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
1B | 1 |  |  | Wire Harness set A Pack (Consolidated Harness Set) | MCElectronics |  |  | 10021057rD | [10 empty] | 4 | 1 |  | 0 | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
1C | 1 |  |  | Wire Harness Internal Pressure Vessel (Consolidated Harness Set) | MCElectronics |  |  | 10021161 | [10 empty] | 4 | 1 |  | 0 | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
2 | 1 | H1 | 10021057-H06 | RS-232 Half-Pack AFT Harness | MCElectronics |  | MBARI | 10021057-H06 |  | Q6224 | 1710919 (QTY:4) |  |  | PO emailed 7/18. MBARI ordered enough for 4 vehicles. | WHOI needs to purchase |  |  |  | 4 | 1 |  | 0 | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
3 | 2 | H2,H5 | 10021057-H03 | Power Interface Charge Harness | MCElectronics |  | MBARI | 10021057-H03 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
4 | 1 | H3 | 10021057-H04 | Motherboard Charge/Dischage Harness | MCElectronics |  | MBARI | 10021057-H04 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
5 | 1 | H4 | 10021057-H07 | Battery Pack Control Harness | MCElectronics |  | MBARI | 10021057-H07 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
6 | 1 | H6 | 10021057-H05 | RS-232 Half-Pack FRW Harness | MCElectronics |  | MBARI | 10021057-H05 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
7 | 1 | H7 | 10021057-H02 | Aft Bulkhead Charge Harness | MCElectronics |  | MBARI | 10021057-H02 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
8 | 1 | H8 | 10021161-12-H3 | Converter PWM Clock Sync Harness | MCElectronics |  | MBARI | 10021161-12-H3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
9 | 1 | H9 | 10021161-12-H1 | Backplane Power Harness | MCElectronics |  | MBARI | 10021161-12-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
10 | 1 | H10 | 10021161-12-H2 | Backplane Boost Harness | MCElectronics |  | MBARI | 10021161-12-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
11 | 1 | H11 | 10021057-H01 | Aft Bulkhead Charge Harness (Main Umbilical) | MCElectronics |  | MBARI | 10021057-H01 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
12 | 1 | H12 | 10021161-7-H1 | MB Iridium Harness | MCElectronics |  | MBARI | 10021161-7-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
13 | 1 | H13 | 10021161-7-H2 | Iridium Pwr LCB Harness | MCElectronics |  | MBARI | 10021161-7-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
14 | 1 | H14 | 10021161-9-H3 | Iridium to Motherboard Power Harness | MBARI |  | MBARI | 10021161-9-H3 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts. |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
15 | 1 | H15 | 10021161-8-H2 | Cradlepoint Ethernet Motherboard Harness | MBARI |  | MBARI | 10021161-8-H2 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
16 | 1 | H16 | 10021161-13-H1 | Forward Section Wire Harness | MCElectronics |  | MBARI | 10021161-13-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
17 | 1 | H17 | 10021161-2-H1 | BLDC Motor Harness | MCElectronics |  | MBARI | 10021161-2-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
18 | 1 | H18 | 10021161-4-H1 | Rudder Bulkhead Harness | MCElectronics |  | MBARI | 10021161-4-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
19 | 1 | H19 | 10021161-5-H2 | VB Pressure Switch Harness | MCElectronics |  | MBARI | 10021161-5-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
20 | 1 | H20 | 10021161-3-H1 | Elevator Bulkhead Harness | MCElectronics |  | MBARI | 10021161-3-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
21 | 1 | H21 | 10021161-5-H3 | VB Oil Pump Harness | MBARI |  | MBARI | 10021161-5-H3 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
22 | 1 | H22 | 10021161-6-H2 | Mass Shifter Drive Harness | MCElectronics |  | MBARI | 10021161-6-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
23 | 1 | H23 | 10021161-6-H3 | Mass Shifter Optical Switch Harness | MCElectronics |  | MBARI | 10021161-6-H3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
24 | 1 | H24 | 10021161-14-H1 | Forward Bulkhead Harness | MCElectronics |  | MBARI | 10021161-14-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
25 | 1 | H25 | 10021161-13-H3 | DAT Comms Harness | MCElectronics |  | MBARI | 10021161-13-H3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
26 | 1 | H26 | 10021161-2-H2 | Thruster LCB Harness | MCElectronics |  | MBARI | 10021161-2-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
27 | 1 | H27 | 10021161-13-H2 | DAT Modem Power Harness | MCElectronics |  | MBARI | 10021161-13-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
28 | 1 | H28 | 10021161-4-H2 | Rudder LCB Harness | MCElectronics |  | MBARI | 10021161-4-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
29 | 1 | H29 | 10021161-3-H2 | Elevator LCB Harness | MCElectronics |  | MBARI | 10021161-3-H2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
30 | 1 | H30 | 10021161-5-H1 | VB Valve Motor Harness | MCElectronics |  | MBARI | 10021161-5-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
31 | 1 | H31 | 10021161-6-H1 | Mass Shifter LCB Harness | MCElectronics |  | MBARI | 10021161-6-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
32 | 1 | H32 | 10021161-8-H1 | Cradlepoint PWR LCB Harness | MCElectronics |  | MBARI | 10021161-8-H1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
33 | 1 | H33 | 10021161-10-H1 | LCB Analog Pressure Sensor Assembly | MBARI |  | MBARI | 10021161-10-H1 | [5 empty] | MBARI to make using LRAUV inventory parts | MBARI to make using LRAUV inventory parts |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jrosal
34 | 1 | H34 | 10021161-9-H1 | Aft DGO-Iridium Coax Cable | MegaPhase |  | MBARI | 10021161-9-H1 |  | SQ171460 | 1710889 (QTY:5) |  |  | PO sent 6/28. Only ordered enough for MBARI | Pending JOSE to finalize details | 2017-08-16 | 824.24 |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 3296.96 | 824.24 | 4121.2 | 0 | Jrosal | Sent Marie quote for assembly
35 | 1 | H35 | 10021161-9-H2 | Aft DGO-mux Coax Cable | MegaPhase |  | MBARI | 10021161-9-H2 |  | SQ171460 | 1710889 (QTY:5) |  |  | PO sent 6/28. Only ordered enough for MBARI | Pending JOSE to finalize details | 2017-08-16 | 828.15 |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 3312.6 | 828.15 | 4140.75 | 0 | Jrosal | Sent Marie quote for assembly
36 | 1 | H36 | 10021161-9-H4 | Quadplexer to Iridium GPS Coax Cable | MegaPhase |  | MBARI | 10021161-9-H4 |  | SQ171460 | 1710889 (QTY:4) |  |  | PO sent 6/28. Only ordered enough for MBARI | Pending JOSE to finalize details | 2017-07-27 | 76.4 |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 305.6 | 76.4 | 382 | 0 | Jrosal | Sent Marie quote for assembly
37 | 1 | H37 | 10021161-9-H6 | Quadplexer Cell Coax Cable | MegaPhase |  | MBARI | 10021161-9-H6 |  | SQ171460 | 1710889 (QTY:4) |  |  | PO sent 6/28. Only ordered enough for MBARI | Pending JOSE to finalize details | 2017-07-27 | 79.07 |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 316.28 | 79.07 | 395.35 | 0 | Jrosal | Sent Marie quote for assembly
38 | 1 | H38 | 10021161-9-H5 | Quadplexer Wifi Coax Cable | MegaPhase |  | MBARI | 10021161-9-H5 |  | SQ171460 | 1710889 (QTY:4) |  |  | PO sent 6/28. Only ordered enough for MBARI | Pending JOSE to finalize details | 2017-07-27 | 174.78 |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 699.12 | 174.78 | 873.9 | 0 | Jrosal | Sent Marie quote for assembly
39 | 2 | H39,H50 | 10021057-PORT1 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
40 | 2 | H40,H51 | 10021057-PORT2 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
41 | 2 | H41,H52 | 10021057-PORT3 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT3 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
42 | 2 | H42,H53 | 10021057-PORT4 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT4 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
43 | 2 | H43,H54 | 10021057-PORT5 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT5 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
44 | 2 | H44,H55 | 10021057-PORT6 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT6 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
45 | 2 | H45,H56 | 10021057-PORT7 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT7 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
46 | 2 | H46,H57 | 10021057-PORT8 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT8 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
47 | 2 | H47,H58 | 10021057-CDC1 | Charge Distribution Cables | MCElectronics |  | MBARI | 10021057-CDC1 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
48 | 2 | H48,H59 | 10021057-CDC2 | Charge Distribution Cables | MCElectronics |  | MBARI | 10021057-CDC2 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
49 | 2 | H49,H60 | 10021057-RS232 | Half-Pack Serial Cable | MCElectronics |  | MBARI | 10021057-RS232 |  | Q6224 | Reference line item 2 |  |  | Reference line item 2 | Reference line item 2 |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
50 | 1 | H61 | 100221160-03 | Overdrive Umbilical |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 4 6/29/17 | Received at MBARI |  | 511 |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 2044 | 511 | 2555 | 0 | Mchaffey
51 | 1 | H62 | 100221164-04 | Boost and Drop Weight Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17 | Received at MBARI |  | 553.5 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 5943.75 | 1485.9375 | 7132.5 | 0 | Mchaffey
52 | 1 | H63 | 100221164-11 | BBFL2 PUCK Wet Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17, received 5 9/13/17 | Received at MBARI |  | 257.25 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 1286.25 | 321.5625 | 1543.5 | 0 | Mchaffey
53 | 1 | H64 | 10021076-B | Shore Power Umbilical |  |  | Brantner & Assoc (SeaCon) |  |  |  | 1710886 |  |  | Ordered 4 6/28/17 | Not at MBARI, we think we ordered / check with Rie. Believe this item never made it through Seacon. |  | 520 | 635.25 | 4 | 1 |  |  | 0 | 0 | 4 | 5 | 4621 | 1155.25 | #REF! | 0 | Mchaffey
54 | 1 | H65 | 100221161-16 | Seabird CTD Wet Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 8 6/29/17, received qty 8 on 8_24_17 | Received at MBARI |  | 237 |  | 4 | 1 |  |  | 0 | 4 | 8 | 9 | 1896 | 474 | 2133 | 0 | Mchaffey
55 | 2 | H66,H68 | 100221160-05 | Antenna Wet Cable |  |  | Teledyne/?/Falmat | [6 empty] | Part of antenna assembly. | Part of antenna assembly, MBARI will provide 3 antenna assemblies to WHOI |  |  |  | 8 | 2 |  | 3 | 0 | 1 | 9 | 11 | 0 | 0 | 0 | 0 | Jrosal
56 | 1 | H67 | 100221164-12 | Benthos DAT Modem Wet Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17. Order cancelled 9/19/17. Deferred until DAT ordered. | not needed |  | 504.5 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 2522.5 | 630.625 | 3027 | 0 | Mchaffey
57 | 1 | H69 | 100221160-09 | LICOR PAR Wet Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17 | Received at MBARI |  | 271.5 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 1357.5 | 339.375 | 1629 | 0 | Mchaffey
58 | 1 | H70 | 100221164-13 | Aanderra O2 Wet Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17 | Received at MBARI |  | 271.5 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 1357.5 | 339.375 | 1629 | 0 | Mchaffey
59 | 1 | H71 | 100221160-10 | Rowe DVL Wet Cable |  |  | Teledyne Impulse | [7 empty] | not needed |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Mchaffey
60 | 2 | H72,H75 | 100221160-06-H1 | Acuator Connector Harness |  |  | MBARI | [6 empty] | Built at MBARI still needs final mechanical assembly | Waiting on WHOI mechanical parts (A-200711-09_CS_LDA_Assmy Rev4.) |  |  |  | 8 | 2 |  |  | 0 | 1 | 9 | 11 | 0 | 0 | 0 | 0 | Jrosal
61 | 2 | H73,H76 | 100221160-07 | Rudder Wet Cable |  |  | Teledyne Impulse | [6 empty] | Ordered 5 6/29/17 | Received at MBARI |  | 366.75 |  | 8 | 2 |  |  | 0 | 2 | 10 | 12 | 3667.5 | 916.875 | 4401 | 0 | Mchaffey
62 | 2 | H74,H77 | 100221160-06-H2 | Acuator Motor Harness |  |  | MBARI | [6 empty] | Built at MBARI still needs final mechanical assembly | Waiting on WHOI mechanical parts (A-200711-09_CS_LDA_Assmy Rev4.) |  |  |  | 8 | 2 |  |  | 0 |  | 8 | 10 | 0 | 0 | 0 | 0 | Jrosal
63 | 3 | P1,J1,J2 | MCBH12F-AS-90cm-COLORED | MCBH12F-AS-90cm-COLORED |  |  | Teledyne Impulse | MCBH12F-AS-90cm-COLORED |  |  | 1710898 |  |  | Ordered 13 6/29/17 received 11 9/20/17 | Received at MBARI |  | 178 |  | 12 | 3 |  |  | 0 | 1 | 13 | 16 | 2314 | 578.5 | 2848 | 0 | Mchaffey
64 | 6 | J3,J5,J6,J8,J9,J10 | MCBH8F-AS-120cm-22AWG-WHT | MCBH8F-AS-120cm-22AWG-WHT |  |  | Teledyne Impulse | MCBH8F-AS-120cm-22AWG-WHT |  |  | 1710898 |  |  | Ordered 5 6/29/17 | Received at MBARI |  | 95 |  | 24 | 6 |  |  | 0 | 1 | 25 | 31 | 2375 | 593.75 | 2945 | 0 | Mchaffey
65 | 2 | J4,J7 | MCBH12F-AS-120cm-22AWG-WHT | MCBH12F-AS-120cm-22AWG-WHT |  |  | Teledyne Impulse | MCBH12F-AS-120cm-22AWG-WHT |  |  | 1710898 |  |  | Ordered 9 6/29/17, received 9 9/5/17 | Received at MBARI |  | 177 |  | 8 | 2 |  |  | 0 | 1 | 9 | 11 | 1593 | 398.25 | 1947 | 0 | Mchaffey
66 | 1 | MOTOR1 | Mass Shifter Drive | Mass shifter drive motor 110138/110357/MR-201935 |  |  | Maxon | 266628 | [6 empty] | Received at MBARI + 1 spare |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jerickson
67 | 1 | M1 | DT85 L Frameless Motor | Thruster Motor (on Mech BOM) |  |  | Maxon | 759875 | [6 empty] | WHOI received X 2. Needs motor mechanical parts to complete assembly |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0
68 | 1 | M2 | Maxon 221024 | Maxon 221024 plus 110340 Gear (ref) Valve Motor |  |  | Maxon | 221024 | [5 empty] | MBARI has 3 complete valve assemblies, missing parts for 4th unit | WHOI has parts for 1 unit + 2 spares (MBARI might want to trade 1 unit) |  |  |  | 4 | 1 |  |  | 0 |  | 4 | 5 | 0 | 0 | 0 | 0 | Jerickson
69 | 1 | OP1 | Optical Switch | Mass shifter optical home switch | DigiKey | 365-1260-ND | Optek | OPB817Z | [5 empty] | Ben orded QTY:5. Received but MBARI needs to assemble. | MBARI purchased/assembled unit for WHOI |  | 3.7 |  | 4 | 1 |  | 1 | 0 |  | 4 | 5 | 14.8 | 3.7 | 18.5 | 3.7 | Jrosal | Ben ordered already
70 | 1 | PCB1 | 10021057-PIB1 | Power Interface PCB Assembly | Circuits West/Indtec |  | MBARI | 10021057-PIB1 |  | FAB:53184 | 1710852 (QTY:9) |  | E118804 (1) | 10 assemblies complete | WHOI purchased blank PCBs only. (MBARI PURCHASED PARTS AND ASSEMBLED IN HOUSE) | FAB: 5-Days | 56 |  | 4 | 1 |  | 1 | 0 | 4 | 8 | 9 | 224 | 56 | 504 | 56 | Jrosal
71 | 1 | PCB2 | 11021173rA | Low Voltage Converter Board Assembly | Circuits West/Indtec |  | MBARI | 11021173rA |  | FAB:53185 ASSY:Q-MB2K470 | 1710854 (QTY:12) | 1710891 (QTY:8) | E118804 (2) | 8 Assemblies received for MBARI | WHOI purchased 2 assembled boards - received at MBARI | FAB: 5-Days ASSY: 3-4Weeks | 67.86 | 143.35 | 4 | 1 |  | 0 | 1 | 4 | 8 | 10 | 844.84 | 211.21 | 2112.1 | 0 | Jrosal | Sent Marie quote for assembly
72 | 1 | PCB3 | 10020881rC | Motherboard Assembly | Circuits West/Indtec |  | MBARI | 10020881rC |  | FAB:53188 ASSY:Q-MB2k230 | 1710856 (QTY:14) | 1710872 (QTY:10) | E118804 (2) | FAB PO emailed 6/27. ASSY PO sent 6/28. 10 Assemblies in house complete. | WHOI purchased blank PCBs. Needs to order assembly (Recommend concurrently with Mesobot). | FAB: 5-Days ASSY: 3-4Weeks | 215 | 772.9 | 4 | 1 |  | 0 | 2 | 6 | 10 | 13 | 3951.6 | 987.9 | 12842.7 | 0 | Jrosal | Sent Marie quote for assembly
73 | 1 | PCB4 | 11021164rA | Load Control Backplane | Circuits West/Indtec |  | MBARI | 11021164rA |  | FAB:Q55344 | 1711531 (QTY:10) |  |  | Sent out RFQ for assemblies and fabs 11/28/17. FAB PO sent 11/29. | WHOI notified of build run 11/31 and is purchasing their boards concurrently. |  |  |  | 4 | 1 |  |  | 2 | 2 | 6 | 9 | 0 | 0 | 0 | 0 | Jrosal
74 | 1 | PCB5 | HVC | High Voltage Converter Board Assembly | Circuits West/Indtec |  | MBARI | 11021173rA | [6 empty] | Board is not complete. WHOI unable to order. |  |  |  | 4 | 1 |  |  | 1 | 5 | 9 | 11 | 0 | 0 | 0 | 0 | Jrosal
75 | 1 | PCB6 | PCM-040-332EUPR.A0 | Motherboard Processer SOM |  |  | PHYTEC | PCM-040-332EUPR.A0 |  | 170628C | 1710940 (QTY:6) |  |  | PO emailed 7/13. Ordered 6 - MBARI build + 2 spares. | WHOI bought 2 - received at MBARI |  | 299 |  | 4 | 1 |  |  | 0 | 2 | 6 | 7 | 1196 | 299 | 2093 | 0 | Jrosal
76 | 1 | PCB7 | 98267-0469 | Motherboard to Backplane Flex PCB | DigiKey | WM14131-ND | Molex | 98267-0469 | [5 empty] | Ordered from Digikey | MBARI PURCHASED 1x for WHOI |  | 2.48 |  | 4 | 1 |  | 1 | 0 |  | 4 | 5 | 9.92 | 2.48 | 12.4 | 2.48 | Jrosal
77 | 5 | PCB8,PCB10,PCB12,PCB13,PCB14 | EZSV23 WV | EZ Servo Motor Drive Board |  |  | AllMotion | EZSV23 WV |  |  | 1711011 (QTY: 20) |  |  | PO sent 7/31 for 20 boards. Only purchased enough for MBARI | WHOI needs to order EZ servo boards |  | 325 |  | 20 | 5 |  |  | 0 |  | 20 | 25 | 6500 | 1625 | 8125 | 0 | Jrosal
78 | 1 | PCB9 | 10020864rA | Maxon motor adaptor | PCB MBARI Stock (11) |  | MBARI | 10020864rA |  | FAB:53198 | 1710857 (QTY:49) |  | E118804 (1) | FAB PO emailed 6/26. MBARI assembled 5. | WHOI purchased blank PCBs only. Cost of BOM for this board is $0.80. MBARI purchased parts and assembled 1x) | FAB: 5-Days | 8.8 | 0.8 | 4 | 1 |  | 1 | 1 | 10 | 14 | 16 | 38.4 | 9.6 | 153.6 | 9.6 | Jrosal
79 | 1 | PCB11 | 10020689rA | MBARI 10020689, Motorized VB Iso Valve Control Board | Circuits West/Indtec |  | MBARI | 10020689rA |  | FAB:53186 ASSY:Q-MB2K540 | 1710853 (QTY:14) | 1710892 (QTY:10) | E118804 (1) | FAB PO emailed 6/26. FAB dropped off for assembly 7/14. 10 received | WHOI purchased blank PCB (1). WHOI purchased 3 assemblies. In their kit | FAB: 5-Days | 37.34 | 123.12 | 4 | 1 |  |  | 1 | 6 | 10 | 12 | 641.84 | 160.46 | 1925.52 | 0 | Jrosal | Sent Marie quote for assembly
81 | 1 | PCB16 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-24V-5A | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (8) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boards to cover MBARI vehicles and spares | WHOI needs to order blank boards and assemblies. |  | 10.4 | 99.75 | 4 | 3 |  | 1 | 0 | 4 | 8 | 11 | 440.6 | 110.15 | 1211.65 | 110.15 | Jrosal
82 | 4 | PCB17,PCB20,PCB25 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-12V | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (20) |  |  | WHOI needs to order blank boards and assemblies. |  | 10.4 | 99.75 | 16 | 4 |  | 0 |  | 4 | 20 | 24 | 1762.4 | 440.6 | 2643.6 | 0 | Jrosal
83 | 5 | PCB18,PCB21,PCB24,PCB27,PCB28,PCB30 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 485-BATT-5A | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (24) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boards to cover MBARI vehicles and spares | WHOI needs to order blank boards and assemblies. |  | 10.4 | 99.92 | 20 | 5 |  |  |  | 4 | 24 | 29 | 2206.4 | 551.6 | 3199.28 | 0 | Jrosal
84 | 2 | PCB19,PCB22 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-BATT-5A | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (12) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boards to cover MBARI vehicles and spares | WHOI needs to order blank boards and assemblies. |  | 10.4 |  | 8 | 2 |  |  |  | 4 | 12 | 14 | 83.2 | 20.8 | 145.6 | 0 | Jrosal
85 | 1 | PCB23 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | 232-5V | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (6) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boards to cover MBARI vehicles and spares | WHOI needs to order blank boards and assemblies. |  | 10.4 |  | 4 | 1 |  |  |  | 2 | 6 | 7 | 41.6 | 10.4 | 72.8 | 0 | Jrosal
86 | 2 | PCB26,PCB31 | 10020568r1-0 | Load Control Board (Analog) |  |  | MBARI | 10020568r1-3 |  | FAB:55343 | 1711528 (QTY:12) |  |  | Request for assembly and fabrication quote sent 11/29/17. Fabrication quote sent 11/30 | WHOI notified of build run 11/31 and purchasing their boards concurrently. |  | 82.5 |  | 8 | 2 |  |  |  | 4 | 12 | 14 | 660 | 165 | 1155 | 0 | Jrosal
87 | 1 | PCB29 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | OFF-12V | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (6) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boards to cover MBARI vehicles and spares | WHOI needs to order blank boards and assemblies. |  | 10.4 |  | 4 | 1 |  |  |  | 2 | 6 | 7 | 41.6 | 10.4 | 72.8 | 0 | Jrosal
88 | 1 | PCB32 | 100221186rB | RF Multiplexer PCB | PCB MBARI Stock (8) |  | MBARI | 100221186rB |  | ASSY:Q-MB2K545 | No extra fabs needed | 1710901 (QTY:5) |  | 5 boads completed. Need to send back for rework to correct wronge IC installed. | WHOI needs to order blank boards and assemblies. |  |  | 123.12 | 4 | 1 |  |  |  | 1 | 5 | 6 | 492.48 | 123.12 | 738.72 | 0 | Jrosal
89 | 1 | PCB33 | 9602-LP | Iridium/GPS Tracker |  |  | NAL Research | 9602-LP |  | NAL17-0622-01 | 1710859 (QTY:4) |  |  | Received | WHOI already purchased. Received |  | 600 |  | 4 | 1 |  |  |  |  | 4 | 5 | 2400 | 600 | 3000 | 0 | Jrosal | Marie already purchased
90 | 1 | PCB34 | COR IBR600LPE-VZ | 3G/4G/WiFi Router w/ 170585-000 cable |  |  | Cradlepoint | COR IBR600LE-VZ |  | PWS_CradlePointRouterQuote.pdf | 1710862 (QTY:4) |  |  | Received | Sean will order 11/13 |  | 594 |  | 4 | 1 |  |  |  |  | 4 | 5 | 2376 | 594 | 2970 | 0 | Jrosal | Sent Marie quote for assembly
91 | 2 | PCB35,PCB37 | 10021057-BPC1 | MBARI Battery Pack Controller 2017-05-14-RevB sheets 1-11 | Circuits West/Indtec |  | MBARI | 10021057-BPC1 |  | FAB:53187 | 1710855 (QTY:14) | 1710965 (QTY:16) | E118804 (2) | FAB PO emailed 6/26. Assembly PO emailed 7/20. Trinh has boards. 16 boards received. | WHOI purchased blank PCBs. WHOI needs to pay for assembly @ $345 ea. | FAB: 5-Days | 93.34 |  | 8 | 2 |  | 2 |  | 8 | 16 | 18 | 746.72 | 186.68 | 1680.12 | 186.68 | Jrosal
92 | 2 | PCB36,PCB38 | XP-08SR | Ocean Server Battery Charger (Master/Slave) |  |  | Ocean Server | XP-08SR |  |  | 1711055 (QTY:12) |  |  | Request for quote sent 7/18. Received | WHOI purchased 3 units - received at MBARI |  | 1195.7 |  | 12 | 3 |  |  |  |  | 12 | 11 | 14348.4 | 3587.1 | 13152.7 | 0 | Jrosal
93 | 1 | PCB39 | 100221187rA | Dual UWB Antenna PCB Assembly | PCB MBARI Stock (5) |  | MBARI | 100221187rB |  | FAB:53250 ASSY:Q-MB2K545 | 1710858 (QTY:24) | 1710901 (QTY:25) | E118804 (1) | 5 boards complete (20 boards to go back for update to incorrect IC installed | WHOI purchased 1 blank PCB. WHOI needs to pay for 2 additional PCB + 3 x assembly. MBARI will provide 3 antenna assemblies to WHOI. | FAB: 7-Days | 76.96 | 86.15 | 4 | 1 |  | 3 |  | 21 | 25 | 26 | 652.44 | 163.11 | 4240.86 | 489.33 | Jrosal
94 | 1 | PUMP1 | Oil Pump | Oil Pump | [10 empty] | Sean will order 11/13 |  |  |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 0 | 0 | 0 | 0 | Mchaffey
95 | 1 | PressSens1 | PA-6ST | Keller PA-6ST 50 bar FS 3.5kohm 20% Pressure Sensor |  |  | Keller | PA-6ST | [6 empty] | Sean will order 11/13 |  |  |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 0 | 0 | 0 | 0 | Hobson
96 | 1 | P2 | MINK10-BCRL-DO | SeaCon MINK10(2#14,8#20)BCRL,DUAL O-RING |  |  | Brantner & Assoc (SeaCon) | MINK-10-L-BCR-DO |  |  | 1710898 |  |  | Ordered 5 6/29/17, received | OK, WHOI purchased |  | 416 |  | 4 | 1 |  |  | 1 | 1 | 5 | 7 | 2080 | 520 | 2912 | 0 | Mchaffey
97 | 3 | REF1 | DLSA-M | DLSA-M LOCKING SLEEVE |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17 | OK, WHOI purchased |  | 9 |  | 12 | 3 |  |  | 3 | 1 | 13 | 19 | 117 | 29.25 | 171 | 0 | Mchaffey
98 | 0 | REF2,REF3 | DLSA-F | DLSA-F LOCKING SLEEVE |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 5 6/29/17 | OK, WHOI purchased |  | 7.75 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 7.75 | 1.9375 | 7.75 | 0 | Mchaffey
99 | 1 | R1 | SP1-12 | Precision string potentiometer |  |  | Measurement Specialties | SP1-12 | [6 empty] | Sean will order 11/13 |  |  |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 0 | 0 | 0 | 0 | Mchaffey
100 | 1 | SW1 | PSW-524 | Pressure Switch |  |  | Omega | PSW-524 | [6 empty] | Sean will order 11/13 |  |  |  | 4 | 1 |  |  | 1 | 1 | 5 | 7 | 0 | 0 | 0 | 0 | Mchaffey
101 | 1 | S1 | BC14-42 | Nylon coated SST Burn Wire for drop weight release. Comes in 42 ft. coil. |  |  | Malin | BC14-42 | [6 empty] | MBARI to make using stock OK |  |  |  | 4 | 1 |  |  | 1 | 1 | 5 | 7 | 0 | 0 | 0 | 0 | Mchaffey
102 | 1 | S2 | RSBH2F | Drop Weight Release Sensor |  |  | Subconn | RSBH2F |  |  | 1711160 |  |  | Ordered 5 9/5/2017 | "OK, WHOI purchased, being installed" - I have not seen this item. |  | 113.5 |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 454 | 113.5 | 681 | 0 | Mchaffey
103 | 1 | S3 | FAS-015004 | ECO-PUCK BB2FL-MBA (470,650,CHL)(5,5,50), beveled and fitted with connector as shown in drawing 220468 and with fixed width data output. |  |  | Wet Labs | FAS-015004 | [10 empty] | 4 | 1 |  |  | 1 |  | 4 | 6 | 0 | 0 | 0 | 0 | Mchaffey | 2018 Purchase item after approved.
104 | 1 | S4 | GPCTD | Sea-Bird 350m Glider Payload CTD (GPCTD) for measuring conductivity, temperature, and pressure, Includes pump, AF24173 Anti |  |  | Sea-Bird Electronics Inc. | GPCTD.1301S | [8 empty] | 10438 |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 41752 | 10438 | 62628 | 0 | Mchaffey | 2018 Purchase item after approved.
105 | 1 | S5 | DAT OEM+ Transducer | Teledyne Benthos Medium Frequency remote transducer. Right angle connector on Transducer |  |  | Teledyne Benthos | DAT-903-MF5 | [8 empty] | 25000 |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 100000 | 25000 | 150000 | 0 | Mchaffey | 2018 Purchase item after approved.
106 | 1 | S6 | LI-192SA | LI-COR Underwater quantum sensor |  |  | LI-COR | LI-192SA | [8 empty] | 750 |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 3000 | 750 | 4500 | 0 | TBD | 2018 Purchase item after approved.
107 | 1 | S7 |  | Seabird DO sensor and cable |  |  | Sea-Bird Electronics Inc. | 43F.1113 | [8 empty] | 4561 |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 18244 | 4561 | 27366 | 0 | Mchaffey | 2018 Purchase item after approved.
|  |  | BB2FL-MBA (470,650,CHL)(5,5,50) | Puck Chl and OBS Fluorometer |  |  | Seabird/Wetlabs | FAS-015004 | [8 empty] | 8614.92
108 | 1 | S8 | Pathfinder DVL | RDI 600 kHz Pathfinder ROV version |  |  | Teledyne RDI | PATH-SC-XRT+ADCP | [8 empty] | 25000 |  | 4 | 1 |  |  | 1 |  | 4 | 6 | 100000 | 25000 | #REF! | #REF!
109 | 4 | SPARE PCB | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-4 | Non Configured | FAB:53397 ASSY:Q-MB2K550 | 1710912 (QTY:130) | 1710939 (20) |  | FAB PO emailed 7/10, ASSY PO emailed 7/13. Purchased enough boarsd to cover all vehicles and spares | WHOI needs to pay for blank boards and assemblies. |  | 10.4 |  | 16 | 4 |  | ? | 4 | 4 | 20 | 28 | 166.4 | 41.6 | 291.2 | #VALUE! | Jrosal
110 | 1 |  | CC141-SBSB-24 | Conformable Cable assembly 24in, DC-4 GHz, SMA Female Bulkhead - SMA Female Bulkhead. For antennae mold | MegaPhase | CC086-SBSB-24 |  |  |  | SQ171143-1 | 1711172 (QTY:8) |  |  | PO sent 6/28. Received 8 assemblies. Installed 1 into antenna. | WHOI purchased ? Units. Received at MBARI | 2017-07-27 | 60.68 |  | 4 | 1 |  |  | 1 | 4 | 8 | 10 | 242.72 | 60.68 | 606.8 | 0 | Jrosal
111 | 1 | Part appears in dwg 100221160-15-B and 100221189-07 | 100221160-15-B | Payload Cable |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 4 6/29/17 | OK, WHOI purchased - received at MBARI |  | 271.5 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 1357.5 | 339.375 | 1629 | 0 | Mchaffey
112 | 2 | A-200711-09_CS_LDA_Assmy Rev4. | MKS-310-FCR | MKS-310-FCR actuator bulkhead connector |  |  | Teledyne Impulse |  |  |  | 1710898 |  |  | Ordered 10 6/29/17 | OK, WHOI purchased - received at MBARI |  | 185.75 |  | 8 | 2 |  |  | 0 | 1 | 9 | 11 | 1671.75 | 417.9375 | 2043.25 | 0 | Mchaffey
113 | 1 | A-201500-17_DW_HrdWrAssem. | A-MLS-P | Impulse A-MLS-P plastic locking sleeve |  |  | Teledyne Impulse Inc. |  |  |  | PO-1711249 |  |  | Ordered 5 on 9/22/2017 | Check status |  | 5.25 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 26.25 | 6.5625 | 31.5 | 0 | Mchaffey
114 | 1 | A-201500-17_DW_HrdWrAssem. | RMA-FS | Impulse Single Pin Socket RMA-FS on 2 feet of 1N2T cable |  |  | Teledyne Impulse Inc |  |  |  | PO-1711249 |  |  | Ordered 5 on 9/22/2017 | Check status |  | 17 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 85 | 21.25 | 102 | 0 | Mchaffey
115 | 1 | A-201500-17_DW_HrdWrAssem. | A-FLS-P | Impulse A-FLS-P plastic locking sleeve |  |  | Teledyne Impulse Inc |  |  |  | PO-1711249 |  |  | Ordered 5 on 9/22/2017 | Check status |  | 5.25 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 26.25 | 6.5625 | 31.5 | 0 | Mchaffey
116 | 1 | A-201500-17_DW_HrdWrAssem. | RMA-MP | Impulse Single Pin Plug RMA-MP on 2 feet of 1N2T cable |  |  | Teledyne Impulse Inc |  |  |  | PO-1711249 |  |  | Ordered 5 on 9/22/2017 | Check status |  | 16.5 |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 82.5 | 20.625 | #REF! | 0 | Mchaffey
117 | 1 | A-201500-17_DW_HrdWrAssem. |  | LUG, RING, 18-22 AWG, #2 | [10 empty] | MBARI providing |  |  |  | 4 | 1 |  |  | 0 | 1 | 5 | 6 | 0 | 0 | 0 | 0 | Mchaffey
118 | 2 | A-200711-09_CS_LDA_Assmy Rev4. | RP-20-500 | P3 Ameriac RP-20 500Ohm Potentiometer | P3 America | [5 empty] | PO-1711001 |  |  | Ordered 10 on 7/28/2017 | Sean will order 11/13 |  | 36 |  | 8 | 0 |  |  | 0 | 1 | 9 | 1 | 324 | 81 | 36 | 0 | Hobson
93533.73
[28 empty] | 27784.73 |  |  |  | no payload sensors
Note on S62: chma: Falmat cable
Note on D105: chma: Edited qty. to correct numbers.
Note on D109: chma: Revised to #14 wire to conform to as-built wire.
Note on D120: chma: Order called out rev. A, not sure which rev. was built.

## BatterySystem_Copy
Battery system PCBs, batteries
Date: | 2023-11-13 |  | Q:\BillsOfMaterials\EE_BOM\[LRAUVBuild5MasterElectricalBOM_11_13_23.xlsx]Electrical
Item Number | Major Subsystem | Drawing Number | Qty | Part Number | Description | Author | Outside or Internal Build? | Lead Time Estimate
| Half-Pack (2x required for Full pack) quantities listed for Ful-Pack! | 10021057-HALF-PACK-ELECTRICAL | 2 | 10021057-BPC1-2017-05-14-RevB sheets 1-11 | Battery Pack Controller (integrates Ocean Server charger; 31 batteries, and connectivity to Mother Board) | Klimov
|  |  | 2 | XP-08SR | Ocean Server battery charger, stack of master and slave, 8 charge ports total | Ocean Server
|  |  | 62 | NH2034HD34 | Lithium battery 4s2p, NH2034 series, 14.4V, 6.8Ah, 98Wh | Inspired Energy
| Battery Pack charge path | 10021057-PIB1 RevA | 1 | 10021057-PIB1 sheet 1 | Power Interface Board (between AFT bulkhead and Battery Pack) | Klimov
Battery system wiring/ harnesses
Date: | 2023-11-13
Item Number | Major Subsystem | Drawing Number | Qty | Part Number | Description | Author | Outside or Internal Build? | Lead Time Estimate
| Aft Pack Interface Harnesses | 10021057-APACK-HARNESSES Rev D | 1 | 10021057-H01 sheet 1 | Aft Bulkhead Connector Main Umbilical Charge / Comm Harness | Klimov
|  |  | 1 | 10021057-H02 sheet 1 | Aft Bulkhead Connector Dropweight/ Boost Charge Harness | Klimov
|  |  | 2 | 10021057-H03 sheet 2 | Charge harnesses between Power Interface Board and FWD/AFT Half-Packs | Klimov
|  |  | 1 | 10021057-H04 sheet 3 | Discharge Harness (between FRW/AFT Half-Packs, and Mother Board) | Klimov
|  |  | 1 | 10021057-H05 sheet 4 | RS-232 to FRW Half-Pack (between FRW Half-Pack, and Mother Board) | Klimov
|  |  | 1 | 10021057-H06 sheet 4 | RS-232 to AFT Half-Pack (between AFT Half-Pack, and Mother Board) | Klimov
|  |  | 1 | 10021057-H07 sheet 4 | Control to Hal-Pack Harness (between FRW/AFT Half-Packs, and Mother Board) | Klimov
| Half-pack Harnesses Quantities listed for Full-pack! | 10021057-HALF-PACK-HARNESSES Rev B | 2 | 10021057-PORT1 sheet 1 | Port Harness 1 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT2 sheet 1 | Port Harness 2 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT3 sheet 1 | Port Harness 3 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT4 sheet 1 | Port Harness 4 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT5 sheet 2 | Port Harness 5 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT6 sheet 2 | Port Harness 6 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT7 sheet 2 | Port Harness 7 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-PORT8 sheet 2 | Port Harness 8 (between Ocean Server charger and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-CDC1 sheet 3 | Charge Distribution Cable1 (between Ocean Server and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-CDC2 sheet 3 | Charge Distribution Cable2 (between Ocean Server and Battery pack Controller) | Klimov
|  |  | 2 | 10021057-RS232 sheet 4 | Half-pack Serial Cable (between Ocean Server and Battery pack Controller) | Klimov

## DeckBox_Copy
LRAUV Charger Box System Bill of Materials
Item desription | Manufacturer | Mfg no. | Vendor | Vendor no. | qty |  |  | Ordered
4U rolling rack, roto-molded | SKB cases | SKBR4W | Sweetwater | SKBR4W | 1 |  | 199.99 | 2017-06-16
Power conditioner/outlet strip | Furman | M-8X2 | Sweetwater | FUM8X2 | 1 |  | 79 | 2017-06-16
2U rack chassis | circuitspecialists.com | ET2/35B | circuitspecialists.com | ET2/35B | 1 |  | 59 | 2017-06-16
Power supply w/GPIB | Ametek Sorenson | XG40-38MGA | Ward Davis Associates | XG40-38MGA | 1 |  | 2353
rack mount for power supply | Ametek Sorenson | RM-XG1 | Ward Davis Associates | RM-XG1 | 1 |  | 61
Rocker switch | E-Switch | R1966ABLKBLKIS | Digi-Key | EG1844-ND | 1 |  |  | 2017-06-16
24V panel LED grn | Dialight | 609-1222-140F | Digi-Key | 350-1892-ND | 1 |  |  | 2017-06-16
Panel Digital Ammeter | Murata Power Sol. | DCA5-20PC-1-DC4-RL-C | Digi-Key | 811-1089-ND | 1 |  |  | 2017-06-16
Panel Digital Voltmeter | Murata Power Sol. | DMS-20PC-1-DCM-C | Digi-Key | 811-1062-ND | 1 |  |  | 2017-06-16
Panel voltmeter bezel | Murata Power Sol. | DMS-BZL4-C | Digi-Key | 811-1128-ND | 1 |  |  | 2017-06-16
SPST Toggle switch | NKK Switches | WT11S-RO | Digi-Key | 360-1951-ND | 1 |  |  | 2017-06-16
12V panel LED yel | Dialight | 609-1322-130F | Digi-Key | 350-1897-ND | 1 |  |  | 2017-06-16
D-sub 9 serial connector | TE Connectivity | 1757820-1 | Digi-Key | A32575-ND | 1 |  |  | 2017-06-16
D-sub crimp socket | TE Connectivity | 205090-1 | Digi-Key | A2161-ND | 3 |  |  | 2017-06-16
Panel ethernet connector | Harting | 9454521504 | Digi-Key | 1195-3540-ND | 1 |  |  | 2017-06-16
Panel Ethernet connector | Harting | 9454521504 | Digi-Key | 1195-3540-ND | 1 |  |  | 2017-06-16
19C Panel Umbilical connector | Amphenol | MS3102E22-14P | PEI Genesis | MS3102E22-14P | 1 |  | 12.64 | 2017-06-16
10C Overdrive umbilical connector | Amphenol | MS3102E18-1P | PEI Genesis | MS3102E18-1P | 1 |  | 8.04 | 2017-06-16
2C Charge input connector | Amphenol | MS3102E20-23P | PEI Genesis | MS3102E20-23P | 1 |  | 11.88 | 2017-06-16
8C Auxilliary signals connector | Amphenol | MS3102E20-7P | PEI Genesis | MS3102E20-7P | 1 |  | 8.07 | 2017-06-16
AC power receptacle | Qualtek | 703W-00/06 | Digi-Key | Q334-ND | 1 |  |  | 2017-06-16
Fuse holder 15A, 250V | Cooper/Bussman | BK/HKP-HH-R | Digi-Key | 283-2849-ND | 1 |  |  | 2017-06-16
Fuse, 10A/250V, Slo | Cooper/Bussman | BK/MDA-10-R | Digi-Key | 283-2722-ND | 1 |  |  | 2017-06-16
Ethernet switch | BB Electronics | ESW 105 | Digi-Key | 1165-1042-ND | 1 |  |  | 2017-06-16
RS232 Isolator/repeater | BB Electronics | 232OPDR | Digi-Key | 1165-1001-ND | 1 |  |  | 2017-06-16
24V power supply | TDK Lambda | HWS150A24/HD | Digi-Key | 285-2346-ND | 1 |  |  | 2017-06-16
12V power supply | TDK Lambda | DSP10-12 | Digi-Key | 285-1225-ND | 1 |  |  | 2017-06-16
power line filter module | TDK Lambda | RSEN-2010D | Digi-Key | 285-2620-ND | 1 |  |  | 2017-06-16
50mV/50A shunt | Murata Power Sol. | 3020-01096-0 | Digi-Key | 811-1094-ND | 1 |  |  | 2017-06-16
Plastic DIN rail adapter |  |  | McMaster | 8961K32 | 1 |  | 2.07 | 2017-06-26
DIN end stop | Wago | 249-116 | On-Line Electronics | 249-116 | 6 |  | 0.87 | 2017-06-16 | 24
3-cond DIN terminal | Wago | 280-651 | On-Line Electronics | 280-651 | 15 |  | 1.9 | 2017-06-16 | 60
4-cond DIN terminal | Wago | 280-646 | On-Line Electronics | 280-646 | 5 |  | 1.94 | 2017-06-16 | 20
2-cond DIN termnal | Wago | 284-902 | On-Line Electronics | 284-902 | 2 |  | 3.71 | 2017-06-16 | 8
Separator/cap, sm | Wago | 280-313 | On-Line Electronics | 280-313 | 8 |  | 0.55 | 2017-06-16 | 32
Separator/cap, lg | Wago | 284-328 | On-Line Electronics | 284-328 | 2 |  | 0.73 | 2017-06-16 | 8
Jumper | Wago | 280-402 | On-Line Electronics | 280-402 | 8 |  | 0.5 | 2017-06-16 | 32
Portable cord 12/3 SEOOW 600V |  |  | McMaster | 7080K44 | 20 |  | 2.07 | 2017-06-26
Power plug NEMA 5-20 |  |  | McMaster | 7140K23 | 1 |  | 20.81 | 2017-06-26
Power cord 16AWG, 3ft |  |  | McMaster | 71535K43 | 1 |  | 4.82 | 2017-06-26
19C Umbilical inline connector | Amphenol | MS3106E22-14S | PEI Genesis | MS3106E22-14S | 1
Long bell housing | Amphenol | APH 10-580927-223 | PEI Genesis | APH 10-580927-223 | 1
Cable clamp | Amphenol | MS3057-12C | PEI Genesis | MS3057-12C | 1
Bushing | Amphenol | MS3420-8A | PEI Genesis | MS3420-8A | 1
Replacement for above 4 lines? | Amphenol | APH AIT6LC22-14S | PEI Genesis | APH AIT6LC22-14S | 1 |  | 55.19 | 2017-06-16 |  | Talk to Ben Rogers (408-435-1750) at PEI Genesis
10C Overdrive umbilical inline conn | Amphenol | MS3106E18-1S | PEI Genesis | MS3106E18-1S | 1 |  | 22.84 | 2017-06-16
2C Charge input inline connector | Amphenol | MS3106E20-23S | PEI Genesis | MS3106E20-23S | 1 |  | 29.58 | 2017-06-16
8C Auxilliary signals inline connector | Amphenol | MS3106R20-7S | PEI Genesis | MS3106R20-7S | 1 |  | 21.13 | 2017-06-16
Misc parts…
10-12AWG ring term, 1/4" std | TE Connectivity | 35110 | Digi-Key | A1083-ND | 2 |  |  | 2017-06-16
other terminals and ferrules and wire and such
35mm DIN rail, 8.00 inch
35mm DIN rail, 5.00 inch
35mm DIN rail, 2.50 inch
Aluminum angle, 1.25x2.0x3L
| LRAUV Charger Box System Bill of Materials |  | Q:\BillsOfMaterials\EE_BOM\[LRAUVBuild5MasterElectricalBOM_11_13_23.xlsx]Electrical
| Item desription | Manufacturer | Mfg no. | Vendor | Vendor no. | qty | Cost
| 4U rolling rack, roto-molded | SKB cases | SKBR4W | Amazon.com | SKBR4W | 1
| Power conditioner/outlet strip | Furman | M-8X2 | B&H Photo | FUM8X2 | 1
| 2U rack chassis | web-tronics.com | ET2/35B | web-tronics.com | ET2/35B | 1
| Power supply w/GPIB | Ametek Sorenson | XG40-38MGA | Ward Davis Associates | XG40-38MGA | 1 | 2353
| rack mount for power supply | Ametek Sorenson | RM-XG1 | Ward Davis Associates | RM-XG1 | 1
| Rocker switch | E-Switch | R1966ABLKBLKIS | Digi-Key | EG1844-ND | 1
| 24V panel LED grn | Dialight | 609-1222-140F | Digi-Key | 350-1892-ND | 1
| Panel Digital Ammeter | Murata Power Sol. | DCA5-20PC-1-DC4-RL-C | Digi-Key | 811-1089-ND | 1
| Panel Digital Voltmeter | Murata Power Sol. | DMS-20PC-1-DCM-C | Digi-Key | 811-1062-ND | 1
| Panel voltmeter bezel | Murata Power Sol. | DMS-BZL4-C | Digi-Key | 811-1128-ND | 1
| SPST Toggle switch | NKK Switches | WT11S-RO | Digi-Key | 360-1951-ND | 1
| 12V panel LED yel | Dialight | 609-1322-130F | Digi-Key | 350-1897-ND | 1
| D-sub 9 serial connector | TE Connectivity | 1757820-1 | Digi-Key | A32575-ND | 1
| Panel ethernet connector | Harting | 9454521504 | Digi-Key | 1195-3540-ND | 1
| Panel Ethernet connector | Harting | 9454521504 | Digi-Key | 1195-3540-ND | 1
| 19C Panel Umbilical connector | Amphenol | MS3102E22-14P | PEI Genesis | MS3102E-22-14P | 1
| 10C Overdrive umbilical connector | Amphenol | MS3102E18-1P | PEI Genesis | MS3102E-18-1P | 1
| Charge input connector | Amphenol | MS3102E20-23P | PEI Genesis | MS3102E20-23P | 1
| Auxilliary signals connector | Amphenol | MS3102E20-7P | PEI Genesis | MS3102E20-7P | 1
| AC power receptacle | Qualtek | 703W-00/06 | Digi-Key | Q334-ND | 1
| Fuse holder 15A, 250V | Cooper/Bussman | BK/HKP-HH-R | Digi-Key | 283-2849-ND | 1
| Fuse, 10A/250V, Slo | Cooper/Bussman | BK/MDA-10-R | Digi-Key | 283-2722-ND | 1
| Ethernet switch | BB Electronics | ESW 105 | Digi-Key | 1165-1042-ND | 1
| RS232 Isolator/repeater | BB Electronics | 232OPDR | Digi-Key | 1165-1001-ND | 1
| 24V power supply | TDK Lambda | HWS150A24/HD | Digi-Key | 285-2346-ND | 1
| 12V power supply | TDK Lambda | DSP10-12 | Digi-Key | 285-1225-ND | 1
| power line filter module | TDK Lambda | RSAN-2010D | Digi-Key | RSAN-2010D-ND | 1
| 50mV/50A shunt | Murata Power Sol. | 3020-01096-0 | Digi-Key | 811-1094-ND | 1
| Plastic DIN rail adapter |  |  | McMaster | 8961K32 | 1
| DIN end stop | Wago | 249-116 | On-Line Electronics |  | 6
| 3-cond DIN terminal | Wago | 280-651 | On-Line Electronics |  | 15
| 4-cond DIN terminal | Wago | 280-646 | On-Line Electronics |  | 5
| 2-cond DIN termnal | Wago | 284-902 | On-Line Electronics |  | 2
| Separator/cap, sm | Wago | 280-313 | On-Line Electronics |  | 8
| Separator/cap, lg | Wago | 284-328 | On-Line Electronics |  | 2
| Jumper | Wago | 280-402 | On-Line Electronics |  | 8
| Portable cord 12/3 SEOOW 600V |  |  | McMaster | 7080K44 | 20
| Power plug NEMA 5-20 |  |  | McMaster | 7140K23 | 1
| Power cord 16AWG, 3ft |  |  | McMaster | 71535K43 | 1
| 19C Umbilical inline connector | Amphenol | MS3106E22-14S | PEI Genesis | MS3106E22-14S | 1
| Long bell housing | Amphenol | APH 10-580927-223 | PEI Genesis | APH 10-580927-223 | 1
| Cable clamp | Amphenol | MS3057-12C | PEI Genesis | MS3057-12C | 1
| Bushing | Amphenol | MS3420-8A | PEI Genesis | MS3420-8A | 1
| Replacement for above 4 lines? | Amphenol | MS3106LC22-14S | PEI Genesis | MS3106LC22-14S | 1
| 10C Overdrive umbilical inline conn | Amphenol | MS3106E18-1S | PEI Genesis | MS3106E18-1S | 1
| 2C Charge input inline connector | Amphenol | MS3106E20-23S | PEI Genesis | MS3106E20-23S | 1
| 8C Auxilliary signals inline connector | Amphenol | MS3106R20-7S | PEI Genesis | MS3106R20-7S | 1
Misc parts…
| 10-12AWG ring term, 1/4" std | TE Connectivity | 35110 | Digi-Key | A1083-ND | 2
other terminals and ferrules and wire and such
35mm DIN rail, 8.00 inch
35mm DIN rail, 5.00 inch
35mm DIN rail, 2.50 inch
Aluminum angle, 1.25x2.0x3L

## MegaPhaseBOM
Item | Quantity per vehicle | Reference | Part | Description | Distributor | Distributor Number | Manufacturer | Manufacturer Number | Spares Qty. | Total Qty for N vehicles
34 | 1 | H34 | 10021161-9-H1 | Aft DGO-Iridium Coax Cable | MegaPhase |  | MBARI | 10021161-9-H1 | 1 | 10
35 | 1 | H35 | 10021161-9-H2 | Aft DGO-mux Coax Cable | MegaPhase |  | MBARI | 10021161-9-H2 | 1 | 10
36 | 1 | H36 | 10021161-9-H4 | Quadplexer to Iridium GPS Coax Cable | MegaPhase |  | MBARI | 10021161-9-H4 |  | 5
37 | 1 | H37 | 10021161-9-H6 | Quadplexer Cell Coax Cable | MegaPhase |  | MBARI | 10021161-9-H6 |  | 5
38 | 1 | H38 | 10021161-9-H5 | Quadplexer Wifi Coax Cable | MegaPhase |  | MBARI | 10021161-9-H5 |  | 5

## MCElectronicsBOM
Item | Quantity per vehicle | Reference | Part | Description | Fabricator | Distributor Number | Manufacturer | Manufacturer Number | Total Qty for N vehicles
2 | 1 | H1 | 10021057-H06 | RS-232 Half-Pack AFT Harness | MCElectronics |  | MBARI | 10021057-H06 | 5
3 | 2 | H2,H5 | 10021057-H03 | Power Interface Charge Harness | MCElectronics |  | MBARI | 10021057-H03 | 10
4 | 1 | H3 | 10021057-H04 | Motherboard Charge/Dischage Harness | MCElectronics |  | MBARI | 10021057-H04 | 5
5 | 1 | H4 | 10021057-H07 | Battery Pack Control Harness | MCElectronics |  | MBARI | 10021057-H07 | 5
6 | 1 | H6 | 10021057-H05 | RS-232 Half-Pack FRW Harness | MCElectronics |  | MBARI | 10021057-H05 | 5
7 | 1 | H7 | 10021057-H02 | Aft Bulkhead Charge Harness | MCElectronics |  | MBARI | 10021057-H02 | 5
8 | 1 | H8 | 10021161-12-H3 | Converter PWM Clock Sync Harness | MCElectronics |  | MBARI | 10021161-12-H3 | 5
9 | 1 | H9 | 10021161-12-H1 | Backplane Power Harness | MCElectronics |  | MBARI | 10021161-12-H1 | 5
10 | 1 | H10 | 10021161-12-H2 | Backplane Boost Harness | MCElectronics |  | MBARI | 10021161-12-H2 | 5
11 | 1 | H11 | 10021057-H01 | Aft Bulkhead Charge Harness (Main Umbilical) | MCElectronics |  | MBARI | 10021057-H01 | 5
12 | 1 | H12 | 10021161-7-H1 | MB Iridium Harness | MCElectronics |  | MBARI | 10021161-7-H1 | 5
13 | 1 | H13 | 10021161-7-H2 | Iridium Pwr LCB Harness | MCElectronics |  | MBARI | 10021161-7-H2 | 5
16 | 1 | H16 | 10021161-13-H1 | Forward Section Wire Harness | MCElectronics |  | MBARI | 10021161-13-H1 | 5
17 | 1 | H17 | 10021161-2-H1 | BLDC Motor Harness | MCElectronics |  | MBARI | 10021161-2-H1 | 5
18 | 1 | H18 | 10021161-4-H1 | Rudder Bulkhead Harness | MCElectronics |  | MBARI | 10021161-4-H1 | 5
19 | 1 | H19 | 10021161-5-H2 | VB Pressure Switch Harness | MCElectronics |  | MBARI | 10021161-5-H2 | 5
20 | 1 | H20 | 10021161-3-H1 | Elevator Bulkhead Harness | MCElectronics |  | MBARI | 10021161-3-H1 | 5
22 | 1 | H22 | 10021161-6-H2 | Mass Shifter Drive Harness | MCElectronics |  | MBARI | 10021161-6-H2 | 5
23 | 1 | H23 | 10021161-6-H3 | Mass Shifter Optical Switch Harness | MCElectronics |  | MBARI | 10021161-6-H3 | 5
24 | 1 | H24 | 10021161-14-H1 | Forward Bulkhead Harness | MCElectronics |  | MBARI | 10021161-14-H1 | 5
25 | 1 | H25 | 10021161-13-H3 | DAT Comms Harness | MCElectronics |  | MBARI | 10021161-13-H3 | 5
26 | 1 | H26 | 10021161-2-H2 | Thruster LCB Harness | MCElectronics |  | MBARI | 10021161-2-H2 | 5
27 | 1 | H27 | 10021161-13-H2 | DAT Modem Power Harness | MCElectronics |  | MBARI | 10021161-13-H2 | 5
28 | 1 | H28 | 10021161-4-H2 | Rudder LCB Harness | MCElectronics |  | MBARI | 10021161-4-H2 | 5
29 | 1 | H29 | 10021161-3-H2 | Elevator LCB Harness | MCElectronics |  | MBARI | 10021161-3-H2 | 5
30 | 1 | H30 | 10021161-5-H1 | VB Valve Motor Harness | MCElectronics |  | MBARI | 10021161-5-H1 | 5
31 | 1 | H31 | 10021161-6-H1 | Mass Shifter LCB Harness | MCElectronics |  | MBARI | 10021161-6-H1 | 5
32 | 1 | H32 | 10021161-8-H1 | Cradlepoint PWR LCB Harness | MCElectronics |  | MBARI | 10021161-8-H1 | 5
39 | 2 | H39,H50 | 10021057-PORT1 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT1 | 10
40 | 2 | H40,H51 | 10021057-PORT2 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT2 | 10
41 | 2 | H41,H52 | 10021057-PORT3 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT3 | 10
42 | 2 | H42,H53 | 10021057-PORT4 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT4 | 10
43 | 2 | H43,H54 | 10021057-PORT5 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT5 | 10
44 | 2 | H44,H55 | 10021057-PORT6 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT6 | 10
45 | 2 | H45,H56 | 10021057-PORT7 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT7 | 10
46 | 2 | H46,H57 | 10021057-PORT8 | Battery System Port Harness | MCElectronics |  | MBARI | 10021057-PORT8 | 10
47 | 2 | H47,H58 | 10021057-CDC1 | Charge Distribution Cables | MCElectronics |  | MBARI | 10021057-CDC1 | 10
48 | 2 | H48,H59 | 10021057-CDC2 | Charge Distribution Cables | MCElectronics |  | MBARI | 10021057-CDC2 | 10
49 | 2 | H49,H60 | 10021057-RS232 | Half-Pack Serial Cable | MCElectronics |  | MBARI | 10021057-RS232 | 10

## InternalWiring (ARCHIVE)
LRAUV Electrical Assembly BOM
Filename: | Q:\BillsOfMaterials\EE_BOM\[LRAUVBuild5MasterElectricalBOM_11_13_23.xlsx]Electrical
100221189-01 Revision: |  |  |  | = calculated values, do not edit
Bill Of Materials June 5,2017 14:58:02
Vehicle Build Quantity: |  | 5
Item | Quantity per vehicle | Reference | Part | Description | Distributor | Distributor Number | Manufacturer | Manufacturer Number | Configuration | Cost Each | Spares Qty. | Total Qty for N vehicles | Total Cost for N vehicles | Part order responsibility
1 | 62 | BATT1,BATT2,ETC. | NH2034HD34 | Lithium battery 4s2p, NH2034 series, 14.4V, 6.8Ah, 98Wh |  |  | Inspired Energy | NH2034HD34 |  | 0 |  | 310 | 0 | Jrosal
2 | 1 | H1 | 10021057-H06 | RS-232 Half-Pack AFT Harness |  |  | MBARI | 10021057-H06 |  |  |  | 5 | 0 | Jrosal
3 | 1 | H2 | 10021057-H03 | Power Interface Charge Harness |  |  | MBARI | 10021057-H03 |  |  |  | 5 | 0 | Jrosal
4 | 1 | H3 | 10021057-H04 | Motherboard Charge/Dischage Harness |  |  | MBARI | 10021057-H04 |  |  |  | 5 | 0 | Jrosal
5 | 1 | H4 | 10021057-H07 | Battery Pack Control Harness |  |  | MBARI | 10021057-H07 |  |  |  | 5 | 0 | Jrosal
6 | 1 | H5 | 10021057-H05 | RS-232 Half-Pack FRW Harness |  |  | MBARI | 10021057-H05 |  |  |  | 5 | 0 | Jrosal
7 | 1 | H6 | 10021057-H02 | Aft Bulkhead Charge Harness |  |  | MBARI | 10021057-H02 |  |  |  | 5 | 0 | Jrosal
8 | 1 | H7 | 10021161-12-H3 | Converter PWM Clock Sync Harness |  |  | MBARI | 10021161-12-H3 |  |  |  | 5 | 0 | Jrosal
9 | 1 | H8 | 10021161-12-H1 | Backplane Power Harness |  |  | MBARI | 10021161-12-H1 |  |  |  | 5 | 0 | Jrosal
10 | 1 | H9 | 10021161-12-H2 | Backplane Boost Harness |  |  | MBARI | 10021161-12-H2 |  |  |  | 5 | 0 | Jrosal
11 | 1 | H10 | 10021057-H01 | Aft Bulkhead Charge Harness (Main Umbilical) |  |  | MBARI | 10021057-H01 |  |  |  | 5 | 0 | Jrosal
12 | 1 | H11 | 10021161-7-H1 | MB Iridium Harness |  |  | MBARI | 10021161-7-H1 |  |  |  | 5 | 0 | Jrosal
13 | 1 | H12 | 10021161-7-H2 | Iridium Pwr LCB Harness |  |  | MBARI | 10021161-7-H2 |  |  |  | 5 | 0 | Jrosal
14 | 1 | H13 | 10021161-9-H3 | Iridium Motherboard Power Harness |  |  | MBARI | 10021161-9-H3 |  |  |  | 5 | 0 | Jrosal
15 | 1 | H13 | 10021161-9-H3 | Iridium to Motherboard Power Harness |  |  | MBARI | 10021161-9-H3 |  |  |  | 5 | 0 | Jrosal
16 | 1 | H14 | 10021161-8-H2 | Cradlepoint Ethernet Motherboard Harness |  |  | MBARI | 10021161-8-H2 |  |  |  | 5 | 0 | Jrosal
17 | 1 | H15 | 10021161-13-H1 | Forward Section Wire Harness |  |  | MBARI | 10021161-13-H1 |  |  |  | 5 | 0 | Jrosal
18 | 1 | H16 | 10021161-2-H1 | BLDC Motor Harness |  |  | MBARI | 10021161-2-H1 |  |  |  | 5 | 0 | Jrosal
19 | 1 | H17 | 10021161-2-H2 | Thruster LCB Harness |  |  | MBARI | 10021161-2-H2 |  |  |  | 5 | 0 | Jrosal
20 | 1 | H18 | 10021161-4-H1 | Rudder Bulkhead Harness |  |  | MBARI | 10021161-4-H1 |  |  |  | 5 | 0 | Jrosal
21 | 1 | H19 | 10021161-4-H2 | Rudder LCB Harness |  |  | MBARI | 10021161-4-H2 |  |  |  | 5 | 0 | Jrosal
22 | 1 | H20 | 10021161-5-H1 | VB Valve Motor Harness |  |  | MBARI | 10021161-5-H1 |  |  |  | 5 | 0 | Jrosal
23 | 1 | H21 | 10021161-5-H2 | VB Pressure Switch Harness |  |  | MBARI | 10021161-5-H2 |  |  |  | 5 | 0 | Jrosal
24 | 1 | H22 | 10021161-3-H1 | Elevator Bulkhead Harness |  |  | MBARI | 10021161-3-H1 |  |  |  | 5 | 0 | Jrosal
25 | 1 | H23 | 10021161-3-H2 | Elevator LCB Harness |  |  | MBARI | 10021161-3-H2 |  |  |  | 5 | 0 | Jrosal
26 | 1 | H24 | 10021161-5-H3 | VB Oil Pump Harness |  |  | MBARI | 10021161-5-H3 |  |  |  | 5 | 0 | Jrosal
27 | 1 | H25 | 10021161-6-H2 | Mass Shifter Drive Harness |  |  | MBARI | 10021161-6-H2 |  |  |  | 5 | 0 | Jrosal
28 | 1 | H26 | 10021161-6-H1 | Mass Shifter LCB Harness |  |  | MBARI | 10021161-6-H1 |  |  |  | 5 | 0 | Jrosal
29 | 1 | H27 | 10021161-6-H3 | Mass Shifter Optical Switch Harness |  |  | MBARI | 10021161-6-H3 |  |  |  | 5 | 0 | Jrosal
30 | 1 | H28 | 10021161-10-H1 | LCB Analog Pressure Sensor Assembly |  |  | MBARI | 10021161-10-H1 |  |  |  | 5 | 0 | Jrosal
31 | 1 | H29 | 10021161-14-H1 | Forward Bulkhead Harness |  |  | MBARI | 10021161-14-H1 |  |  |  | 5 | 0 | Jrosal
32 | 1 | H30 | 10021161-13-H2 | DAT Modem Power Harness |  |  | MBARI | 10021161-13-H2 |  |  |  | 5 | 0 | Jrosal
33 | 1 | H31 | 10021161-13-H3 | DAT Comms Harness |  |  | MBARI | 10021161-13-H3 |  |  |  | 5 | 0 | Jrosal
34 | 1 | H32 | 10021161-8-H1 | Cradlepoint PWR LCB Harness |  |  | MBARI | 10021161-8-H1 |  |  |  | 5 | 0 | Jrosal
35 | 1 | H33 | 10021161-9-H1 | Aft DGO-Iridium Coax Cable |  |  | MBARI | 10021161-9-H1 |  |  | 1 | 6 | 0 | Jrosal
36 | 1 | H34 | 10021161-9-H2 | Aft DGO-mux Coax Cable |  |  | MBARI | 10021161-9-H2 |  |  | 1 | 6 | 0 | Jrosal
37 | 1 | H35 | 10021161-9-H4 | Quadplexer to Iridium GPS Coax Cable |  |  | MBARI | 10021161-9-H4 |  |  |  | 5 | 0 | Jrosal
38 | 1 | H36 | 10021161-9-H6 | Quadplexer Cell Coax Cable |  |  | MBARI | 10021161-9-H6 |  |  |  | 5 | 0 | Jrosal
39 | 1 | H37 | 10021161-9-H5 | Quadplexer Wifi Coax Cable |  |  | MBARI | 10021161-9-H5 |  |  |  | 5 | 0 | Jrosal
40 | 2 | H38,H49 | 10021057-PORT1 | Battery System Port Harness |  |  | MBARI | 10021057-PORT1 |  |  |  | 10 | 0 | Jrosal
41 | 2 | H39,H50 | 10021057-PORT2 | Battery System Port Harness |  |  | MBARI | 10021057-PORT2 |  |  |  | 10 | 0 | Jrosal
42 | 2 | H40,H51 | 10021057-PORT3 | Battery System Port Harness |  |  | MBARI | 10021057-PORT3 |  |  |  | 10 | 0 | Jrosal
43 | 2 | H41,H52 | 10021057-PORT4 | Battery System Port Harness |  |  | MBARI | 10021057-PORT4 |  |  |  | 10 | 0 | Jrosal
44 | 2 | H42,H53 | 10021057-PORT5 | Battery System Port Harness |  |  | MBARI | 10021057-PORT5 |  |  |  | 10 | 0 | Jrosal
45 | 2 | H43,H54 | 10021057-PORT6 | Battery System Port Harness |  |  | MBARI | 10021057-PORT6 |  |  |  | 10 | 0 | Jrosal
46 | 2 | H44,H55 | 10021057-PORT7 | Battery System Port Harness |  |  | MBARI | 10021057-PORT7 |  |  |  | 10 | 0 | Jrosal
47 | 2 | H45,H56 | 10021057-PORT8 | Battery System Port Harness |  |  | MBARI | 10021057-PORT8 |  |  |  | 10 | 0 | Jrosal
48 | 2 | H46,H57 | 10021057-CDC1 | Charge Distribution Cables |  |  | MBARI | 10021057-CDC1 |  |  |  | 10 | 0 | Jrosal
49 | 2 | H47,H58 | 10021057-CDC2 | Charge Distribution Cables |  |  | MBARI | 10021057-CDC2 |  |  |  | 10 | 0 | Jrosal
50 | 2 | H48,H59 | 10021057-RS232 | Half-Pack Serial Cable |  |  | MBARI | 10021057-RS232 |  |  |  | 10 | 0 | Jrosal
51 | 1 | H60 | 100221160-03 | Overdrive Umbilical | [7 empty] | 5 | 0 | Mchaffey
52 | 1 | H61 | 100221164-04 | Overdrive Umbilical | [6 empty] | 1 | 6 | 0 | Mchaffey
53 | 1 | H62 | 100221164-11 | BBFL2 PUCK Wet Cable | [7 empty] | 5 | 0 | Mchaffey
54 | 1 | H63 | 10021076-B | Shore Power Umbilical | [6 empty] | 1 | 6 | 0 | Mchaffey
55 | 1 | H64 | 100221161-16 | Seabird CTD Wet Cable | [6 empty] | 4 | 9 | 0 | Mchaffey
56 | 1 | H65 | 100221160-05 | Antenna Wet Cable | [6 empty] | 1 | 6 | 0 | Mchaffey
57 | 1 | H66 | 100221164-12 | Benthos DAT Modem Wet Cable | [6 empty] | 1 | 6 | 0 | Mchaffey
58 | 1 | H67 | 100221160-09 | LICOR PAR Wet Cable | [6 empty] | 1 | 6 | 0 | Mchaffey
59 | 1 | H68 | 100221164-13 | Aanderra O2 Wet Cable | [7 empty] | 5 | 0
60 | 1 | H69 | 100221160-10 | Rowe DVL Wet Cable | [7 empty] | 5 | 0 | Mchaffey
61 | 1 | H70 | 100221160-06-H1 | Acuator Connector Harness | [6 empty] | 1 | 6 | 0 | Mchaffey
62 | 1 | H71 | 100221160-07 | Rudder Wet Cable | [6 empty] | 1 | 6 | 0 | Mchaffey
63 | 1 | H71 | 100221160-07 | Elevator Wet Cable | [7 empty] | 5 | 0 | Jrosal
64 | 1 | H72 | 100221160-06-H2 | Acuator Motor Harness | [6 empty] | 1 | 6 | 0 | Mchaffey
65 | 3 | P1,J1,J2 | MCBH12F-AS-90cm-COLORED | MCBH12F-AS-90cm-COLORED |  |  | Teledyne Impulse | MCBH12F-AS-90cm-COLORED |  |  | 1 | 16 | 0 | Mchaffey
66 | 6 | J3,J5,J6,J8,J9,J10 | MCBH8F-AS-120cm-22AWG-WHT | MCBH8F-AS-120cm-22AWG-WHT |  |  | Teledyne Impulse | MCBH8F-AS-120cm-22AWG-WHT |  |  | 1 | 31 | 0 | Mchaffey
67 | 2 | J4,J7 | MCBH12F-AS-120cm-22AWG-WHT | MCBH12F-AS-120cm-22AWG-WHT |  |  | Teledyne Impulse | MCBH12F-AS-120cm-22AWG-WHT |  |  |  | 10 | 0 | Jerickson
68 | 1 | MOTOR1 | Mass Shifter Drive | Mass shifter drive motor |  |  | Maxon | 266628 |  |  |  | 5 | 0 | Jerickson
69 | 1 | M1 | BLDC Motor | Thruster Motor |  |  | Applimotion | UTH-114-A-20-B-H-000 |  |  |  | 5 | 0 | Jerickson
70 | 1 | M2 | Maxon 221024 | Maxon 221024 plus 110340 Gear (ref) Valve Motor |  |  | Maxon | 221024 |  |  |  | 5 | 0 | Jerickson
71 | 1 | OP1 | Optical Switch | Mass shifter optical home switch | DigiKey | 365-1260-ND | Optek | OPB817Z |  |  |  | 5 | 0 | Jrosal
72 | 1 | PCB1 | 10021057-PIB1 | Power Interface PCB Assembly |  |  | MBARI | 10021057-PIB1 |  |  |  | 5 | 0 | Jrosal
73 | 1 | PCB2 | 11021173rA | Low Voltage Converter Board Assembly |  |  | MBARI | 11021173rA |  |  | 1 | 6 | 0 | Jrosal
74 | 1 | PCB3 | 10020881rB | Motherboard Assembly |  |  | MBARI | 10020881rB |  |  |  | 5 | 0 | Jrosal
75 | 1 | PCB4 | 11021164rA | Load Control Backplane |  |  | MBARI | 11021164rA |  |  |  | 5 | 0 | Jrosal
76 | 1 | PCB5 | HVC | High Voltage Converter Board Assembly |  |  | MBARI | Not Yet Avaliable |  |  |  | 5 | 0 | Jrosal
77 | 1 | PCB6 | PCM-040-332EUPR.A0 | Motherboard Processer SOM |  |  | PHYTEC | PCM-040-332EUPR.A0 |  |  | 1 | 6 | 0 | Jrosal
78 | 5 | PCB7,PCB9,PCB11,PCB12,PCB13 | EZSV23 WV | EZ Servo Motor Drive Board |  |  | AllMotion | EZSV23 WV |  |  |  | 25 | 0 | Jerickson
79 | 1 | PCB8 | 10020864rA | Maxon motor adaptor |  |  | MBARI | 10020864rA |  |  |  | 5 | 0 | Jrosal
80 | 1 | PCB10 | 10020689rA | MBARI 10020689, Motorized VB Iso Valve Control Board |  |  | MBARI | 10020689rA |  |  |  | 5 | 0 | Mchaffey
81 | 1 | PCB14 | DAT-903-MF5 | Teledyne Benthos Medium Frequency OEM DAT board set short chassis with remote transducer with right angle mount MCBH12MP. |  |  | Teledyne Benthos | DAT-903-MF5 |  |  |  | 5 | 0 | Jrosal
82 | 1 | PCB15 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-2 | 232-24V-5A |  |  | 5 | 0 | Jrosal
83 | 3 | PCB16,PCB19,PCB24 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-2 | 232-12V |  |  | 15 | 0 | Jrosal
84 | 6 | PCB17,PCB20,PCB23,PCB26,PCB27,PCB29 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-2 | 485-BATT-5A |  |  | 30 | 0 | Jrosal
85 | 2 | PCB18,PCB21 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-2 | 232-BATT-5A |  |  | 10 | 0 | Jrosal
86 | 1 | PCB22 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-2 | 232-5V |  |  | 5 | 0 | Jrosal
87 | 2 | PCB25,PCB30 | 10020568r1-0 | Load Control Board (Analog) |  |  | MBARI | 10020568r1-0 |  |  |  | 10 | 0 | Jrosal
88 | 1 | PCB28 | 10020358r3-2 | Load Control Board |  |  | MBARI | 10020358r3-2 | OFF-12 |  |  | 5 | 0 | Mchaffey
89 | 1 | PCB31 | 100221186rB | RF Multiplexer PCB |  |  | MBARI | 100221186rB |  |  |  | 5 | 0 | Mchaffey
90 | 1 | PCB32 | 9602-LP | Iridium/GPS Tracker |  |  | NAL Research | 9602-LP |  |  |  | 5 | 0 | Jrosal
91 | 1 | PCB33 | COR IBR600LPE-VZ | 3G/4G/WiFi Router |  |  | Cradlepoint | COR IBR600LE-VZ |  |  |  | 5 | 0 | Jrosal
92 | 2 | PCB34,PCB36 | 10021057-BPC1 | MBARI Battery Pack Controller 2017-05-14-RevB sheets 1-11 |  |  | MBARI | 10021057-BPC1 |  |  |  | 10 | 0 | Jrosal
93 | 2 | PCB35,PCB37 | XP-08SR | Ocean Server Battery Charger (Master/Slave) |  |  | Ocean Server | XP-08SR |  |  |  | 10 | 0 | Jerickson
94 | 1 | PCB38 | 100221187rA | Dual UWB Antenna PCB Assembly |  |  | MBARI | 100221187rA |  |  |  | 5 | 0 | Jrosal
95 | 1 | PUMP1 | Oil Pump | Oil Pump | [7 empty] | 5 | 0 | Mchaffey
96 | 1 | PressSens1 | PA-6ST | Keller PA-6ST 50 bar FS 3.5kohm 20% Pressure Sensor |  |  | Keller | PA-6ST |  |  |  | 5 | 0 | Mchaffey
97 | 1 | P2 | MINK10-BCRL-DO | SeaCon MINK10(2#14,8#20)BCRL,DUAL O-RING |  |  | Brantner & Assoc (SeaCon) | MINK-10-L-BCR-DO |  |  |  | 5 | 0 | Mchaffey
98 | 1 | REF1 | DLSA-M | DLSA-M LOCKING SLEEVE |  |  | Teledyne Impulse |  |  |  |  | 5 | 0 | Mchaffey
99 | 2 | REF2,REF3 | DLSA-F | DLSA-M LOCKING SLEEVE |  |  | Teledyne Impulse | DLSA-M |  |  |  | 10 | 0 | Mchaffey
100 | 1 | R1 | SP1-12 | String Pot |  |  | Measurement Specialties | SP1-12 |  |  |  | 5 | 0 | Mchaffey
101 | 1 | SW1 | PSW-524 | Pressure Switch |  |  | Omega | PSW-524 |  |  | 1 | 6 | 0 | Mchaffey
102 | 1 | S1 | BC19-42 | Drop Weight Burn Wire Release |  |  | Malin | BC19-42 |  |  | 1 | 6 | 0 | Mchaffey
103 | 1 | S2 | RSBH2F | Drop Weight Release Sensor |  |  | Subconn | RSBH2F |  |  |  | 5 | 0 | Mchaffey
104 | 1 | S3 | FAS-015004 | ECO-PUCK BB2FL-MBA (470,650,CHL)(5,5,50), beveled and fitted with connector as shown in drawing 220468 and with fixed width data output. |  |  | Wet Labs | FAS-015004 |  |  |  | 5 | 0 | Mchaffey
105 | 1 | S4 | GPCTD | Sea-Bird 350m Glider Payload CTD (GPCTD) for measuring conductivity, temperature, and pressure, Includes pump, AF24173 Anti |  |  | Sea-Bird Electronics Inc. |  |  |  |  | 5 | 0 | Mchaffey
106 | 1 | S5 | DAT TRANSDUCER | Teledyne Benthos Medium Frequency remote transducer. Right angle connector on Transducer |  |  | Teledyne Benthos | DAT-903-MF5 |  |  |  | 5 | 0 | Mchaffey
107 | 1 | S6 | LI-192SA | LI-COR Underwater quantum sensor |  |  | LI-COR | LI-192SA |  |  |  | 5 | 0 | Mchaffey
108 | 1 | S7 | 0 300 520 4831F | Aanderra Optode MkII, Dissolved Oxygen, with Wet mate bulkhead SubConn MCBH8M and Fast foil, range 0-500 uM, RS232 and 0-5V outputs, depth rating 2000m | [7 empty] | 5 | 0 | TBD
109 | 1 | S8 | TBD DVL/ADCP | TBD ADCP/DVL

## AntennaCost
Antenna System Parts
Component | PO Date | PO # | Vendor | Cost each | Total QTY for 3 units | Total cost
Casting of Antenna mast & Base | 2017-12-01 | 1711543 | Schmit Prototypes | 443.66 | 3 | 1330.98
Coax base cable stock | 2017-12-20 | 1711648 Rev. 1 | Insulated Wire Inc. | 44.78 | 3 | 134.34
Coax cable over-molding in PU | 2017-12-20 | 1711661 | Ocean Innovations | 29.33 | 3 | 87.99
Blank PCB |  |  |  | 76.96 | 2 | 153.92
PCB assembly |  |  |  | 86.15 | 3 | 258.45
Wet cable SMA connector installation |  |  |  | 50 | 3 | 150
DGO connector installation and over-molding |  |  |  | 606 | 3 | 1818 | Note: WHOI paid vendor directly for this item so cost is credited on MBARI provided parts.
|  |  | Total Antenna Material Cost Each | 1336.88 |  | 3933.68