## ME_BOM_ALL
Yellow highlight: Not fabricated yet
Orange highlight: on hold pending complete nose cone design
Assy. | Item No. | QTY. | Part Number | Description | Rev. | MFG | Vendor | Material | Note | Unit Cost | QTY. Cost | Provided to WHOI Build | PO Num. | Order Date | Order Recived | Lead time (week) | Status | Assigned
A-200502-08_TailControlAssem_V7. | 30 | 4 | 06003 DGN | Jilson Plastic Bearing |  | Jilson Group | https://www.amazon.com | ACETAL |  | 10 | 40 |  | cc | 2017-07-28 | 2017-08-05 |  |  | Hobson
A-200502-08_TailControlAssem_V7. | 25 | 1 | D8C | Cylinder Mag. Axially Magnetized 15.5 lbf. |  | K&J Magnetics | K&J Magnetics | N42 |  | 4.23 | 4.23 |  | cc | 2017-07-28 | 2017-08-05 |  |  | Hobson
A-200502-08_TailControlAssem_V7. | 2 | 4 | P-200950-10 | Fin Bearing Mount | C | MBARI | Larkin | Aluminum 6061-T6 |  | 667 | 2668 |  | PO-1710752 | 2017-06-01 | 2017-08-14 |  | po confirmed | Parker
A-200502-08_TailControlAssem_V7. | 1 | 1 | P-200627-08 | Foam Mount Plate | A | MBARI | Larkin | Aluminum 6061-T6 |  | 812 | 812 |  | PO-1710752 | 2017-06-01 | 2017-08-04 |  | po confirmed | Parker
A-200502-08_TailControlAssem_V7. | 32 | 4 | A-200xxx-09 | Pivot Bearing Assembly |  | MBARI | MBARI |  |  | 65 | 260 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. |  | 4 | P-200700-09 | CS Centering Sleeve | A | MBARI | MBARI | Black DELRIN |  | 320 | 1280 | y | [5 empty] | Parker
A-200502-08_TailControlAssem_V7. | 29 | 4 | A-200618-08 | Control Fin Assembly |  | MBARI | MBARI |  |  | 64.6 | 258.4 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 23 | 1 | P-201xxx-12 | Buss Wire - Grounding Wire Assem. |  | MBARI | MBARI |  |  |  | 0 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 22 | 1 | A-201xxx-13 | Zinc Anode - O-Ring Assembly |  | MBARI | MBARI |  |  | 12.75 | 12.75 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 21 | 1 | A-201798-16 | Antenna Rev. I | I | MBARI | MBARI |  |  |  | 0 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 15 | 1 | A-200924-10 | VB Bladder Assembly |  | MBARI | MBARI |  |  | 66.57 | 66.57 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 14 | 1 | A-201500-17 | Drop Weight Assembly Hard Parts | A | MBARI | MBARI | Material <not specified> |  |  | 0 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 11 | 2 | A-200711-09 | CS LDA Assembly Rev.4 | 4 | MBARI | MBARI | Material <not specified> |  | 1422.9 | 2845.8 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 9 | 2 | P-200702-09 | CS Fin Actuator Mount |  | MBARI | MBARI | Black DELRIN |  | 80 | 160 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 6 | 1 | P-200625-08 | Propeller_V4 (Thicker) |  | MBARI | MBARI | cast urethane |  | 364 | 364 | y | [5 empty] | Parker
A-200502-08_TailControlAssem_V7. | 5 | 1 | P-200682-09 | Tail Shell Lock Ring_V2 | B | MBARI | MBARI | BLACK DELRIN |  | 175 | 175 | [6 empty] | Parker
A-200502-08_TailControlAssem_V7. | 34 | 4 | 90967A210 | 17mm External Retaining Ring |  |  | McMaster-Carr | 1.4122 (X39CrMo17-1) |  | 1.03 | 4.12 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200502-08_TailControlAssem_V7. | 33 | 4 | 95611A037 | PVC Flat Washer |  |  | McMaster-Carr | PVC Rigid | Olander Hardware Kit - $96.85/KIT |  | 0 | [6 empty] | Chaffey
A-200502-08_TailControlAssem_V7. | 28 | 2 | 92185A540 | 1/4-20 x 3/4 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 27 | 4 | 90585A540 | 1/4-20 x 3/4L Flt Hd Sckt Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 26 | 2 | 97345A540 | 1/4 x 3/4 x #10-24 Soc Hd Shldr Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 20 | 4 | 90585A214 | #6-32 x 1/2 Flt Hd Soc Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 18 | 8 | 98164A107 | #6-32 x 3/8 Button Hd Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 17 | 8 | 90585A225 | #8-32 x 5/16 Flt Hd Soc Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 16 | 6 | 90585A038 | 1/4-20 x 7/16 Flt Hd Soc Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $96.85/KIT |  | 0
A-200502-08_TailControlAssem_V7. | 8 | 1 | 90715A130 | 1/4-28 Nylok Nut |  |  | McMaster-Carr | 316 S.S. | Olander Hardware Kit - $96.85/KIT |  | 0 | [6 empty] | Chaffey
A-200502-08_TailControlAssem_V7. | 7 | 1 | 91841A215 | 1/4-28 Hex Jamm Nut |  |  | McMASTER-CARR | 18-8 Stainless Steel | Olander Hardware Kit - $96.85/KIT |  | 0 | [6 empty] | Chaffey
A-200502-08_TailControlAssem_V7. | 24 | 1 | TAM-4310-3 | Argos/VHF Beacon |  |  | Telonics |  |  | 995 | 995 |  | PO-1711255 | 2017-09-26 |  | 5-6 weeks |  | Hobson
A-200502-08_TailControlAssem_V7. | 13 | 1 | A-200751-09 | Tail Shell Complete Assembly (Includes parts below) | E |  |  |  |  | 1725 | 1725 |  | PO-1711093 | 2017-08-17 |  | 10 weeks |  | Hobson
A-200751-09_Tail Shell Assembly |  | 2 | A-201671-14 | Tail Shell Assembly - Drop Weight Fence | E |  | Waterat |  |  |  | 0 |  | PO-1711093 | 2017-08-17 |  | 10 weeks |  | Hobson
A-200751-09_Tail Shell Assembly |  | 3 | A-201670-14 | Tail Shell Assembly - G-10 Fiber Nut Plates | E |  | Waterat |  |  |  | 0 |  | PO-1711093 | 2017-08-17 |  | 10 weeks |  | Hobson
A-200751-09_Tail Shell Assembly |  | 1 | A-200514-08 | Tail Shell Assembly - Bonded Mount Ring - Nose Shell | E |  | Vanderveer Industrial Plastics | G-10 Fiberglass |  | 518 | 518 |  | PO-1710983 | 2017-08-17 |  | 10 weeks |  | Hobson
A-200751-09_Tail Shell Assembly |  | 1 | A-200751-09 | Tail Shell Assembly - Hatch Assembly | E |  | Waterat | Carbon Epoxy |  |  | 0 |  | PO-1711093 | 2017-08-17 |  | 10 weeks |  | Hobson
A-200751-09_Tail Shell Assembly |  | 1 | A-200517-08 | Tail Shell Assembly - Tail Cone | E |  | Waterat | Carbon Epoxy |  |  | 0 |  | PO-1711093 | 2017-08-17 |  | 10 weeks |  | Hobson
A-200502-08_TailControlAssem_V7. | 3 | 1 | A-201916-17 | Tail Foam Assembly_V6 (Includes parts below) |  | MBARI | MBARI |  |  |  | 0 | [6 empty] | Parker
A-201916-17_TailFoamAssy_V6. |  | 12 | 95110A113 | #6-32 Flanged Insert |  |  | Doerksen | AISI 304 | Olander Hardware Kit - $26.40/KIT | 130 | 1560 | [6 empty] | Chaffey
A-201916-17_TailFoamAssy_V6. |  | 12 | 8668K92 | G-10 Garolite Tube 5/16 x 3/16 Substitute PN 92273A071 |  |  | McMaster-Carr | G-10 Fiberglass Epoxy Laminate Sheet |  | 1.62 | 19.44 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201916-17_TailFoamAssy_V6. |  | 1 | P-200497-17 | Tail Cone Foam Flotation _V6 (Build 5) |  |  | Ideal Instrument | 24 lb Foam |  | 1135.24 | 1135.24 |  | PO-1711171 | 2017-09-07 |  |  |  | Hobson
A-200618-08_Fin_Assem_V6. | 7 | 1 | 7889A44 | 1/8 Polyporpylene Welding Rod |  |  | McMaster-Carr | Polypropylene |  | 11.02 | 11.02 | y | cc | 2017-10-10 |  |  |  | Chaffey
A-200618-08_Fin_Assem_V6. | 5 | 4 | 92185A213 | #8-32 UNC-2A x 2 1/2 SOC HD CAP SCREW |  |  | McMaster-Carr | 316 SS |  | 0.77 | 3.08 | y | cc | 2017-10-10 |  |  |  | Chaffey
A-200618-08_Fin_Assem_V6. | 3 | 4 | P-201715-15 | Fin AxleTab_Ver.6 |  | MBARI | MBARI | 6AL-4V Titanium |  |  | 0 | y | [5 empty] | Parker
A-200618-08_Fin_Assem_V6. | 2 | 4 | P-201716-15 | Fin Axle_Ver.6 (Base Part) |  | MBARI | MBARI | 6AL-4V Titanium |  | 175 | 700 | y | [5 empty] | Parker
A-200618-08_Fin_Assem_V6. | 1 | 4 | P-200617-08 | Control Fin_V5 |  | MBARI | Xcentric Mold and Engineering | D90_Polyurethane | Tooling for Cast Urethane Control Fins - $1633.70 | 64.6 | 258.4 | y | PO-1710871 | 2017-06-28 |  |  |  | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 7 | 2 | WAK15 4mm-6mm #2112 | 4mm-6mm Flexible Shaft Coupling |  | Helical | Helic al | AL |  | 18 | 36 |  | PO-1711000 |  | 2017-09-10 |  |  | Hobson
A-200711-09_CS_LDA_Assmy Rev4. | 9 | 2 | WAK-15 3mm-4mm # 2105 | 3-4 mm Flex Shaft Coupling |  | Helical | Helical | AL |  | 18 | 36 |  | PO-1711000 |  | 2017-09-10 |  |  | Hobson
A-200711-09_CS_LDA_Assmy Rev4. | 25 | 2 | P-200952-10 | Tethys LDA Encoder Cap Retainer |  | MBARI | Larkin | 6061-T6 (SS) |  | 105 | 210 |  | PO-1710753 | 2017-06-01 | 2017-07-24 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 18 | 2 | P-200713-09 | Encoder Torque Arm | B | MBARI | Larkin | 6061-T6 AL |  | 97 | 194 |  | PO-1710753 | 2017-06-01 | 2017-07-24 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 15 | 2 | P-200708-09 | CS LDA Strong Back | C | MBARI | Larkin | 6061-T6 Alloy |  | 340 | 680 |  | PO-1710753 | 2017-06-01 | 2017-07-24 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 14 | 2 | P-201087-11 | LRAUV CS Motor Cap | A | MBARI | Larkin | 6061-T6 AL Clear Hard Anodize |  | 104 | 208 |  | PO-1710753 | 2017-06-01 | 2017-07-24 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 13 | 2 | P-201532-13 | Encoder Cap |  | MBARI | Larkin | 6061-T6 AL Clear Hard Anodize |  | 99 | 198 |  | PO-1710753 | 2017-06-01 | 2017-07-24 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 10 | 2 | P-200712-09 | Motor Mount Plate |  | MBARI | Larkin | 6061-T6 AL |  | 98 | 196 |  | PO-1710753 | 2017-06-01 | 2017-08-01 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 1 | 2 | 305844 | ECmax-16 5w Motor 283828-157:1 Gearbox- 118186 |  |  | MAXON | spare+1 |  | 217.3 | 434.6 |  | PO-1710720 | 2017-05-22 | 2017-06-08 |  | po confirmed | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 34 | 8 | 92185A077 | 2-56 x 1/4 SHCS |  |  | McMaster |  | Olander Hardware Kit - $25.75/KIT |  | 0
A-200711-09_CS_LDA_Assmy Rev4. | 24 | 12 | 90729A114 | 6-32x1/4 100 deg flat head screw |  |  | McMaster |  | Olander Hardware Kit - $25.75/KIT |  | 0
A-200711-09_CS_LDA_Assmy Rev4. | 22 | 6 | 90729A111 | 6-32x3/8 100 degree Flat Head |  |  | McMaster |  | Olander Hardware Kit - $25.75/KIT |  | 0
A-200711-09_CS_LDA_Assmy Rev4. | 21 | 2 | 6350K36 | 3/8"-5 Thread Flange Nut for Ultra-Precision Lead Screw |  |  | McMaster | Delrin AF |  | 23.47 | 46.94 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 17 | 16 | 92185A193 | 8-31 x 7/16 SST SHCS |  |  | McMaster | AISI 316 | Olander Hardware Kit - $25.75/KIT |  | 0 | [6 empty] | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 16 | 4 | 92125A050 | M2 x 4 mm FH screws |  |  | McMaster |  | Olander Hardware Kit - $25.75/KIT |  | 0 | [6 empty] | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 6 | 2 | 98394a431 | 16mm Internal Snap Ring |  |  | McMaster |  | Olander Hardware Kit - $25.75/KIT |  | 0 | [6 empty] | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 5 | 2 | 98317a214 | 6mm shaft externa snap ring |  |  | McMaster |  | Olander Hardware Kit - $25.75/KIT |  | 0 | [6 empty] | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 3 | 4 | 6153K113 | Open Ball Bearing for 5mm Shaft |  |  | McMaster |  |  | 11.85 | 47.4 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 38 | 4 | 90097A150 | Electrical-Insulating Sleeve Washer, Rolled-Collar, Number 8 Screw Size, |  |  | McMaster-Carr |  |  | 0.31 | 1.24 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 37 | 4 | 90295A340 | Nylon Washer |  |  | McMaster-Carr | Nylon 6/10 | Olander Hardware Kit - $25.75/KIT |  | 0 | [6 empty] | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 29 | 16 | 92185A107 | #4-40 x 1/4 5/16" Soc Hd Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $25.75/KIT |  | 0
A-200711-09_CS_LDA_Assmy Rev4. | 26 | 4 | 92185A108 | #4-40 x 3/8 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $25.75/KIT |  | 0
A-200711-09_CS_LDA_Assmy Rev4. | 19 | 4 | 90825A180 | 18-8 S.S. Sealing Pn Hd Phil Screw Buna-N O-Ring, 8-32 Thrd, 1/4" L |  |  | McMaster-Carr | AISI 304 | Olander Hardware Kit - $25.75/KIT |  | 0 | [6 empty] | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 2 | 2 | RP-20-500 | P3 Ameriac RP-20 500Ohm Potentiometer |  |  | P3 America |  | Reference (on elec. BOM) | 36 | 72 |  | PO-1711001 | 2017-07-28 |  | 8 weeks |  | Hobson
A-200711-09_CS_LDA_Assmy Rev4. | 23 | 4 | P-200710-09 | Oring Cap | A | MBARI | Prunella | Black Delrin |  | 14.8 | 59.2 | y | PO-1710814 | 2017-06-19 | 2017-08-28 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 20 | 2 | P-200706-09 | CS LDA Nut |  | MBARI | Prunella | Black Delrin |  | 30.55 | 61.1 | y | PO-1710814 | 2017-06-19 | 2017-08-28 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 12 | 2 | P-200705-09 | CS LDA Motor Body |  | MBARI | Prunella | Black Delrin |  | 144 | 288 | y | PO-1710814 | 2017-06-19 | 2017-08-28 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 11 | 2 | P-201091-11 Rev E | CS Actuator Encoder Body | E | MBARI | Prunella | Black Delrin |  | 108 | 216 | y | PO-1710814 | 2017-06-19 | 2017-08-28 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 8 | 4 | P-200707-09 | CS LDA Pivot Pin |  | MBARI | Prunella | 316 SST |  | 11.85 | 47.4 | y | PO-1710814 | 2017-06-19 | 2017-08-28 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 4 | 2 | P-200704-09 | CS LDA Leadscrew | C | MBARI | Prunella | 303 SST |  | 53.4 | 106.8 | y | PO-1710814 | 2017-06-19 | 2017-08-28 |  | po confirmed | Parker
A-200711-09_CS_LDA_Assmy Rev4. | 39 | 2 | SS-200-1-4ST | 1/8 Tube - SAE#4 |  |  | Swagelok | S.S 316 |  | 14.37 | 28.74 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 36 | 2 | SS-QM2-D-200 | Quick dis-connect |  |  | Swagelok |  |  | 46.24 | 92.48 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 35 | 2 | SS-T2-S-028 | 1/8 x .028 S.S. Tube |  |  | Swagelok | AISI 316 |  | 8.84 | 17.68 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 27 | 4 | SS-2-HPST | SAE-2 Solid Plug | 0 |  | Swagelok |  |  | 8.89 | 35.56 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 28 | 2 | MKS-310-FCR | 10 pin Bulkhead Electrical Connector |  |  | Teledyne Impulse | 0.01 | Reference (on elec. BOM) | 185.75 | 371.5 |  | PO-1710898 | 2017-06-29 |  |  |  | Chaffey
A-200711-09_CS_LDA_Assmy Rev4. | 33 | 4 | #2-013-70-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0413 | 0.1652 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 32 | 4 | #2-016-70-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0413 | 0.1652 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 31 | 4 | #2-024-70-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0641 | 0.2564 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Raanan
A-200711-09_CS_LDA_Assmy Rev4. | 30 | 4 | #2-010-70-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0219 | 0.0876 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Raanan
Pivot bearing assy. | 3 | 16 | 90585A202 | #4-40 x 3/8 Flt Hd Soc Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit |  | 0 | [6 empty] | Chaffey
Pivot bearing assy. | 2 | 4 | 6455K8 | R4 Deep Groove Ball Bearing |  |  | McMaster-Carr | Acetal w/glass balls |  | 8.15 | 32.6 |  | cc | 2017-10-10 |  |  |  | Chaffey
Pivot bearing assy. | 1 | 4 | P-200714-09 | Pivot Bearing Cup |  |  | MBARI | Black Delrin |  | 32.5 | 130 | [6 empty] | Parker
A-200731-09_ElevCrank_Rev.B | 6 | 2 | P-200494-08 | Bell Crank F-Dog Link |  | MBARI | MBARI | 6AL-4V Titanium |  | 35 | 70 | [6 empty] | Parker
A-200731-09_ElevCrank_Rev.B | 5 | 1 | P-200728-09 | Bell Crank Bridge |  | MBARI | MBARI | 6AL-4V Titanium |  | 55 | 55 | [6 empty] | Parker
A-200731-09_ElevCrank_Rev.B | 4 | 1 | P-200726-09 | Elevator Crank Plate |  | MBARI | MBARI | 6AL-4V Titanium |  | 50 | 50 | [6 empty] | Parker
A-200731-09_ElevCrank_Rev.B | 3 | 1 | P-200729-09 | CS-Crank Plate |  | MBARI | MBARI | 6AL-4V Titanium |  | 30 | 30 | [6 empty] | Parker
A-200731-09_ElevCrank_Rev.B | 2 | 1 | P-200730-09 | Bell Crank Plate |  | MBARI | MBARI | 6AL-4V Titanium |  | 30 | 30 | [6 empty] | Parker
A-200731-09_ElevCrank_Rev.B | 1 | 1 | P-200715-09 | CS Connector Sleeve |  | MBARI | MBARI | 6AL-4V Titanium |  | 115 | 115 | [6 empty] | Parker
A-200732-09_RudderCrank_Rev.B | 6 | 2 | P-200494-08 | Bell Crank F-Dog Link | A |  | MBARI | 6AL-4V Titanium |  | 35 | 70 | [6 empty] | Parker
A-200732-09_RudderCrank_Rev.B | 5 | 1 | P-200728-09 | Bell Crank Bridge |  |  | MBARI | 6AL-4V Titanium |  | 55 | 55 | [6 empty] | Parker
A-200732-09_RudderCrank_Rev.B | 4 | 1 | P-200727-09 | Rudder Crank Plate |  |  | MBARI | 6AL-4V Titanium |  | 50 | 50 | [6 empty] | Parker
A-200732-09_RudderCrank_Rev.B | 3 | 1 | P-200729-09 | CS-Crank Plate |  |  | MBARI | 6AL-4V Titanium |  | 30 | 30 | [6 empty] | Parker
A-200732-09_RudderCrank_Rev.B | 2 | 1 | P-200730-09 | Bell Crank Plate | A |  | MBARI | 6AL-4V Titanium |  | 30 | 30 | [6 empty] | Parker
A-200732-09_RudderCrank_Rev.B | 1 | 1 | P-200715-09 | CS Connector Sleeve |  |  | MBARI | 6AL-4V Titanium |  | 115 | 115 | [6 empty] | Parker
A-200924-10_ExtBladderAssem. | 11 | 4 | 91770A540 | 1/4-20 x 3/4 Truss Hd Phill Screw |  |  | McMaster-Carr | AISI 304 | Olander Hardware Kit - $17.10/KIT |  | 0 | [6 empty] | Parker
A-200924-10_ExtBladderAssem. | 10 | 4 | 90131A305 | Abrasion Resistant Rubber Washer 1/4 |  |  | McMaster-Carr | BUTYL | Olander Hardware Kit - $17.10/KIT |  | 0 | [6 empty] | Parker
A-200924-10_ExtBladderAssem. | 9 | 2 | #2-119-70N | O-RING |  |  | McMaster-Carr | BUNA - N |  |  | 0 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Raanan
A-200924-10_ExtBladderAssem. | 8 | 1 | P-200719-09 | HDPE Shieldv Wrap |  |  | MBARI | HDPE |  |  | 0 | y | [5 empty] | Chaffey
A-200924-10_ExtBladderAssem. | 7 | 1 | NNR-4-050-0100 | Semi-Rigid Nylon Tubing, 0.250 O.D. 0.150 I.D. |  | Parker- Hannifin | Lesman Instrument Company | Nylon |  |  | 0 | y | [5 empty] | Chaffey
A-200924-10_ExtBladderAssem. | 6 | 1 | NNR-4-050-0100 | Semi-Rigid Nylon Tubing, 0.250 O.D. 0.150 I.D. |  | Parker- Hannifin | Lesman Instrument Company | Nylon |  |  | 0 | y | [5 empty] | Chaffey
A-200924-10_ExtBladderAssem. | 5 | 2 | SS-400-2-4ST | Positionable Male Elbow (SAE/MS Straight Thread) - Fractional |  |  | Swagelok | SST |  | 23.04 | 46.08 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-200924-10_ExtBladderAssem. | 4 | 1 | SS-QC4-B-400 | SAE-4 port QD |  |  | Swagelok |  |  | 43.53 | 43.53 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-200924-10_ExtBladderAssem. | 3 | 2 | NNR-4-050-0100 | Semi-Rigid Nylon Tubing, saddle Bag Equalizer Tube |  | Parker- Hannifin | Lesman Instrument Company | Nylon |  |  | 0 | y | [5 empty] | Chaffey
A-200924-10_ExtBladderAssem. | 2 | 2 | P-200804-10 | Straight Pipe Plug Special | A |  | MBARI | DELRIN (Black ACETAL) |  | 38 | 76 | [6 empty] | Parker
A-200924-10_ExtBladderAssem. | 1 | 1 | CFT-18-MBARI-2 | 1 Litre Oil Bladder |  |  | Ready Containment | White Fuel |  | 329 | 329 |  | PO-1711159 | 2017-09-06 |  | 3 weeks |  | Hobson
A-201176-17_CompAssem_V2. | 14 | 1 | SS-QC4-B1-400 | Swagelok Q.D. |  |  |  | 316 SST |  |  | 0 | [6 empty] | Chaffey
A-201176-17_CompAssem_V2. | 13 | 1 | NNR-4-050-0100 | Semi-Rigid Nylon Tubing, 0.250 O.D. 0.150 I.D. |  | Parker- Hannifin | Lesman Instrument Company | Nylon |  |  | 0 | y | [5 empty] | Chaffey
A-201176-17_CompAssem_V2. | 12 | 4 | 92394A113 | #6-32 Thrd Insert |  |  | McMaster-Carr |  | Olander Hardware Kit - $20.00/KIT |  | 0 | [6 empty] | Chaffey
A-201176-17_CompAssem_V2. | 11 | 1 | SS-400-2-4ST | Swagelok Positionable Elbow 1/4" Tube |  |  | Swagelok | AISI 316 Annealed Stainless Steel Bar (SS) |  | 23.04 | 23.04 |  | PO-1710775 | 2017-06-08 |  |  |  | Raanan
A-201176-17_CompAssem_V2. | 10 | 1 | P-201119-17 | Tail Foam Block V2 |  |  | MBARI | 24 lb. foam |  | 438.15 | 438.15 |  | PO-1711171 | 2017-09-07 |  |  |  | Hobson
A-201176-17_CompAssem_V2. | 9 | 4 | 6-32 X 1.5" FH | 18-8 Stainless Steel - 82 Degree Head |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $20.00/KIT |  | 0 | [6 empty] | Chaffey
A-201176-17_CompAssem_V2. | 8 | 1 | #2-211-70N | O-RING |  |  | McMaster-Carr | BUNA - N |  |  | 0 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Chaffey
A-201176-17_CompAssem_V2. | 7 | 1 | 1544 | PEEK TUBING NATURAL 1/8" OD X .080" ID |  |  | Upchurch Scientific (IDEX Corporation) | Peek |  |  | 0 |  | CC | 2017-10-05 |  |  |  | Chaffey
A-201176-17_CompAssem_V2. | 6 | 2 | SS-QM2-B-200 | Mini QC to 1/8 Tube |  |  | Swagelok Inc. | AISI 316 Annealed Stainless Steel Bar (SS) |  | 60.53 | 121.06 |  | PO-1710775 | 2017-06-08 | 2017-07-01 |  |  | Raanan
A-201176-17_CompAssem_V2. | 5 | 1 | 1544 | PEEK TUBING NATURAL 1/8" OD X .080" ID |  |  | Upchurch Scientific (IDEX Corporation) | PEEK |  |  | 0 |  | CC | 2017-10-05 |  |  |  | Chaffey
A-201176-17_CompAssem_V2. | 4 | 2 | P-340 | FLANGELESS FERRULE, 1/4-28 FLAT-BOTTOM, 1/8" OD |  |  | Upchurch Scientific (IDEX Corporation) | TEFZEL |  |  | 0 |  | CC | 2017-10-05 |  |  |  | Chaffey
A-201176-17_CompAssem_V2. | 3 | 2 | P-330X | FLANGELESS NUT, 1/4-28 FLAT-BOTTOM, FOR 1/8" OD |  |  | Upchurch Scientific (IDEX Corporation) | PEEK |  |  | 0 |  | CC | 2017-10-05 |  |  |  | Chaffey
A-201176-17_CompAssem_V2. | 2 | 1 | P-201547-13 | PC1X Comp. Manifold (Modified) |  |  | MBARI | DELRIN |  |  | 0 | y | [5 empty] | Parker
A-201176-17_CompAssem_V2. | 1 | 1 | PC1X | Tecnadyne Compensaor PC1X |  |  | Tecnadyne Inc. | POM Delrin Homopolymer |  | 1203.05 | 1203.05 |  | PO-1710714 | 2017-05-19 | 2017-07-05 |  | po confirmed | Raanan
A-201500-17_DW_HrdWrAssem. | 44 | 2 | 90585A230 | 8-32 x 3/4 Flt Hd Soc Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 42 | 1 | 91735A003 | #2-56 UNC-2A x 1/8 |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 41 | 1 | A-MLS-P | Impulse A-MLS-P plastic locking sleeve |  |  | Teledyne Impulse Inc. |  | Reference (on elec. BOM) | 5.25 | 5.25 |  | PO-1711249 | 2017-09-22 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 40 | 1 | 19044-0064 | Crimp ring lug, 18-22 AWG, #2 |  |  | Molex/Mouser | copper | Reference (on elec. BOM) | 0.05 | 0.05 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 39 | 1 | RMA-FS | Impulse Single Pin RMA-FS on 2 feet of 1N2T cable |  |  | Teledyne Impulse Inc |  | Reference (on elec. BOM) | 17 | 17 |  | PO-1711249 | 2017-09-22 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 38 | 1 | A-FLS-P | Impulse A-FLS-P plastic locking sleeve |  |  | Teledyne Impulse Inc |  | Reference (on elec. BOM) | 5.25 | 5.25 |  | PO-1711249 | 2017-09-22 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 37 | 1 |  | Hot Glue (Shrink Tube Filler) | [6 empty] | 0 | [6 empty] | Chaffey
A-201500-17_DW_HrdWrAssem. | 36 | 1 |  | 3/16 Shrink Tube | [5 empty] | 5 | 5 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 35 | 1 |  | 1/8 inch Shrink Tube (Clear) | [5 empty] | 5 | 5 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 34 | 1 | RMA-MP | Impulse Single Pin Plug RMA-MP on 2 feet of 1N2T cable |  |  | Teledyne Impulse Inc |  | Reference (on elec. BOM) | 16.5 | 16.5 |  | PO-1711249 | 2017-09-22 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 33 | 1 | P-201630-14 | LRAUV DW Sensor Cable Brace |  |  | MBARI | Black Delrin |  | 12 | 12 | [6 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 31 | 2 | 92185A230 | #10-32 x 2-1/2 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 30 | 1 | 92185A227 | #10-32 x 1-1/4 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 29 | 1 | 92185A105 | #4-40 x 3/16 SOC HD CAP |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 28 | 1 | 94805A217 | Hex Jam Nut 3/8-24 |  |  | McMaster-Carr | 316 SST | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 27 | 8 | 90585A235 | #8-32 x 1-1/4 |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 26 | 1 | 92185A148 | #6-32 x 1.2 Soc Hd Cap |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 25 | 3 | 92185A147 | #6-32 x 3/8 SOC HD CAP SCREW |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 24 | 7 | 90585A204 | #4-40 x 1/2 Flt Hd Soc. Screw |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 23 | 1 | P-200792-11 | Tethys Lead Drop Weight |  |  | RotoMetals, San Leandro | Pure Lead |  | 25 | 25 | y | [5 empty] | Chaffey
A-201500-17_DW_HrdWrAssem. | 22 | 1 |  | 3/32 Shrink Tube (Clear) | [5 empty] | 5 | 5 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 21 | 1 | 17-1-B | MS51844-40 NicoPress copper oval sleeves for 1/32" wire |  |  |  |  | Reference (on elec. BOM) |  | 0 | y | [5 empty] | Chaffey
A-201500-17_DW_HrdWrAssem. | 19 | 1 | BC14-42 | Tethys Burn Wire, Nylon coated single strand SST leader |  |  | Malin | Nylon coated SST leader | Reference (on elec. BOM) |  | 0 | y | [5 empty] | Chaffey
A-201500-17_DW_HrdWrAssem. | 19 | 1 | 94564A047 | #10-32 x 1/2 Flt Pt Set Screw |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 18 | 1 | P-201155-11 | Drop Weight Adjustment Guide Rev.A | C |  | MBARI | POM Delrin (Black) |  | 60 | 60 | [6 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 17 | 1 | P-201153-11 | Drop Weight Support Plate |  |  | MBARI | Black Delrin (ACETAL) |  | 35 | 35 | [6 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 16 | 1 | P-201154-11 | Drop Weight Cross Bar |  |  | MBARI | DELRIN (Black ACETAL) |  | 30 | 30 | [6 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 15 | 1 | 90715A115 | #10-32 NYLOK NUT |  |  | McMaster-Carr | 316 S.S. | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 14 | 1 |  | #4-40 x 3/4 Flt Hd Soc Screw |  |  | McMaster-Carr | 316 S.S. | Olander Hardware Kit - $52.075/KIT |  | 0
A-201500-17_DW_HrdWrAssem. | 13 | 1 | 1692K13 | conical compression spring, drop weight magnet |  |  | McMaster-Carr | 302 S.S. |  | 2.74 | 2.74 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 12 | 1 | 5688K51 | Ultra-High-Temperature Magnetic Button |  |  | McMaster-Carr | AlNiCo |  | 3.02 | 3.02 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 11 | 1 | P-201161-11 | Magnet Support Lever | A |  | MBARI | ABS |  | 28.5 | 28.5 | [6 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 10 | 1 | RSIL-2-M | connector part of wet cable PN 100221164-04_LRAUVAftYCable |  |  | Teledyne Impulse Inc |  | Reference (on elec. BOM) |  | 0 | [6 empty] | Chaffey
A-201500-17_DW_HrdWrAssem. | 9 | 1 | RSBH2F | Connectorized Reed Switch |  |  | Subconn |  | Reference (on elec. BOM) | 113.5 | 113.5 |  | PO-1711160 | 2017-09-05 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 8 | 1 | P-200797-09 | Tethys DW sensor plate |  |  | MBARI | Black Delrin |  | 21.5 | 21.5 | y | [5 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 7 | 2 | P-201152-11 | Drop Weight Spring Piston |  |  | MBARI | 316 SS |  | 45 | 90 | y | [5 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 6 | 2 | 1986K114 | 302 SST Spring 2.5" L, .469" OD, .054" Wire Dia. |  |  | McMaster-Carr | AISI 302 (Full Hard) |  | 1.31 | 2.62 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201500-17_DW_HrdWrAssem. | 5 | 1 | P-200801-09 | Burn Wire Ground Point |  |  | MBARI | 316 SST |  | 22 | 22 | y | [5 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 4 | 1 | P-200796-09 | DW Crossbar Strb | A |  | MBARI | Black Delrin |  | 31.25 | 31.25 | y | [5 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 3 | 1 | P-200795-09 | Tethys DW Cross Plate Port | A |  | MBARI | Black Delrin |  | 32 | 32 | y | [5 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 2 | 1 | P-200794-09 | Tethys Bladder Mount Aft | B |  | MBARI | Black UHMW |  | 172.5 | 172.5 | y | [5 empty] | Parker
A-201500-17_DW_HrdWrAssem. | 1 | 1 | P-200793-09 | Tethys Bladder Mount | B |  | MBARI | Black UHMW |  | 180 | 180 | y | [5 empty] | Parker
A-201798-16_Antenna Rev.I. | 8 | 4 | 92185A215 | 10-24 x 1.5 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $14.50/KIT |  | 0 | [6 empty] | Chaffey
A-201798-16_Antenna Rev.I. | 7 | 1 | 98380A467 | Dowel Pin |  |  | McMaster-Carr | 416 S.S. | Olander Hardware Kit - $14.50/KIT |  | 0 | [6 empty] | Chaffey
A-201798-16_Antenna Rev.I. | 6 | 1 | 99362A600 | Threaded Insert |  |  | McMaster-Carr | 360 Brass | Olander Hardware Kit - $14.50/KIT |  | 0 | [6 empty] | Chaffey
A-201798-16_Antenna Rev.I. | 5 | 2 | 97395A453 | 1/8 Dowel Pin x 1-1/4 L |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $14.50/KIT |  | 0 | [6 empty] | Chaffey
A-201798-16_Antenna Rev.I. | 1 | 1 | A-201798-16 | Molded Antenna Mast Assembly | J |  | Schmidt Prototypes | filled urethane | Cast part around RF antenna PCB with SMA Well | 409 | 409 | y | [5 empty] | Hobson
A-201798-16_Antenna Rev.I. | 2 | 1 | P-200772-09 | Antenna Base Clamp | I |  | MBARI | BLACK DELRIN |  |  | 0 | y | [5 empty] | Parker
P-200770-15_ForewardBaseAssy_W.Rev.I. | 4 | 1 | P-201775-16 | SMA Well |  |  | MBARI | ABS |  | 32 | 32 | y | [5 empty] | Parker
[7 empty] | Doerksen |  |  | 53
[7 empty] | Doerksen |  |  | 48
A-200503-17_ThrusterMotorAssy_Build5. | 10 | 1 | P-200532-08 | Thruster Motor Press Tube | A | MBARI | Doerksen | 6061-T6 Alloy | ordered w/ PressHull_EndDome_AFT (P-200466-08) | 77 | 77 |  | PO-1710718 | 2017-05-19 |  |  | po sent | Parker
A-200503-17_ThrusterMotorAssy_Build5. | 8 | 3 | #00608-CBCBT | Deep Groove Ceramic Bearing |  | Jilson | Amazon |  | Ceramic skate bearing VXB #608 | 9.95 | 29.85 |  | CC | 2017-08-03 | 1900-01-07 |  |  | Hobson
A-200503-17_ThrusterMotorAssy_Build5. | 2 | 1 | MTC-1.0-005 | Magnetic Coupling Outer Cup |  |  | Doerksen |  | Price reflected in A-200508-17 | 151 | 151 |  | CC | 2017-07-10 |  |  |  | Raanan
A-200503-17_ThrusterMotorAssy_Build5. | 7 | 1 | P-200531-08 | Thrust Bearing Mount | B | MBARI | Doerksen | POM Delrin Homopolymer |  | 222 | 222 | y | PO-1710811 |  | 2017-08-04 |  |  | Parker
A-200503-17_ThrusterMotorAssy_Build5. | 3 | 1 | P-200530-08 | Mag. Coupling Shroud | B | MBARI | MBARI | PEEK | A&D | 525 | 525 |  | PO-1710811 |  | 2017-08-04 |  |  | Parker
A-200503-17_ThrusterMotorAssy_Build5. | 15 | 4 | 92185A540 | 1/4-20 x 3/4 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $8.50/KIT |  | 0
A-200503-17_ThrusterMotorAssy_Build5. | 14 | 2 | 92605A538 | M5 0.4 x 10mmL |  |  | McMaster-Carr | 316 S.S. | Olander Hardware Kit - $8.50/KIT |  | 0
A-200503-17_ThrusterMotorAssy_Build5. | 12 | 6 | 92185A147 | #6-32 x 3/8 SOC HD CAP SCREW |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $8.50/KIT |  | 0
A-200503-17_ThrusterMotorAssy_Build5. | 11 | 6 | 92185A108 | #4-40 x 3/8 SOC HD CAP SCREW |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $8.50/KIT |  | 0
A-200503-17_ThrusterMotorAssy_Build5. | 9 | 1 | 98394A440 | Internal retaining ring, DIN 1.4122 SST, for 22 mm ID |  |  | McMaster-Carr | 420 S.S. |  | 1.86 | 1.86 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200503-17_ThrusterMotorAssy_Build5. | 13 | 2 | #2-049-70-N | O-RING |  |  |  | BUNA - N |  |  | 0 | [6 empty] | Chaffey
A-200503-17_ThrusterMotorAssy_Build5. | 5 | 2 | #2-029-70-N | O-RING |  |  |  | BUNA - N |  |  | 0 | [6 empty] | Chaffey
A-200503-17_ThrusterMotorAssy_Build5. | 4 | 1 | #2-026-70-N | O-RING |  |  |  | BUNA - N |  |  | 0 | [6 empty] | Chaffey
A-200503-17_ThrusterMotorAssy_Build5. | 6 | 1 | A-200567-08 | Composite Propeller Shaft Assembly (includes parts below) | A | MBARI | Doerksen |  |  |  | 0 | [6 empty] | Parker
A-200567-08_PropShaftAssem_RevA | 5 | 1 | P-200574-08 | Prop shaft Cross Pin | A | MBARI | MBARI | 6AL-4V Titanium |  | 20 | 20 | y | [5 empty] | Parker
A-200567-08_PropShaftAssem_RevA | 3 | 1 | P-200568-08 | Prop shaft AFT Journal | B | MBARI | MBARI | Titanium Gr2 |  | 156.25 | 156.25 | y | [5 empty] | Parker
A-200567-08_PropShaftAssem_RevA | 2 | 1 | P-200566-08 | Prop shaft FWD Journal | F | MBARI | MBARI | 6AL-4V Titanium |  | 185 | 185 | y | [5 empty] | Parker
A-200567-08_PropShaftAssem_RevA | 1 | 1 | 8668K11 | Garolite Tube 5/16" OD X 3/16" ID, 1/16" Wall Thick, 21" Length | - |  | McMaster-Carr | Garolite G-10 laminate |  | 26.09 | 26.09 | y | cc | 2017-10-10 |  |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 10 | 1 | P-200512_08 | Motor Stator Retainer | A | MBARI | A & D Precision Inc. | 6061-T6 Alloy |  | 825 | 825 |  | PO-1710811 | 2017-06-19 | 2017-08-08 |  |  | Parker
A-200508-17_MotorAssem_Build5. | 7 | 1 | P-200510-08 | Motor Rotor Shaft | A | MBARI | A & D Precision Inc. | Plain Carbon Steel |  | 375 | 375 |  | PO-1710811 | 2017-06-19 |  |  |  | Parker
A-200508-17_MotorAssem_Build5. | 5 | 1 | P-200509-08 | GlueOn Rotor Hub | - | MBARI | A & D Precision Inc. | Plain Carbon Steel |  | 280.5 | 280.5 |  | PO-1710811 | 2017-06-19 | 2017-08-08 |  |  | Parker
A-200508-17_MotorAssem_Build5. | 3 | 6 | P-200511-08 | Stator Retainer Clip | - | MBARI | A & D Precision Inc. | 6061-T6 Alloy |  | 26.5 | 159 |  | PO-1710811 | 2017-06-19 | 2017-08-08 |  |  | Parker
A-200508-17_MotorAssem_Build5. | 2 | 1 | P-200462-08 | Thruster Motor Rear End Cap | B | MBARI | A & D Precision Inc. | 6061-T6 Alloy |  | 825 | 825 |  | PO-1710811 | 2017-06-19 |  |  |  | Parker
A-200508-17_MotorAssem_Build5. | 4 | 1 | UTH114A20BH000 | Motor Rotor (UTH-114-A-20-B-H-00) |  | Applimotion | Celera Motion |  |  | 1850 | 1850 |  | PO-1710809 |  |  |  |  | Raanan
A-200508-17_MotorAssem_Build5. | 19 | 1 | MTC-1.0 | Magnetic Coupling Inner Plug |  |  | Magnetic Technologies LTD. |  |  | 355 | 355 |  | PO-1710917 | 2017-07-10 |  |  |  | Raanan
A-200508-17_MotorAssem_Build5. | 18 | 1 | 6679K13 | Dry-Running Sleeve Bearing with Steel Shell |  |  | McMaster-Carr | PTFE-Lined TIN Bronze |  | 2.58 | 2.58 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 16 | 4 | 90585A202 | #4-40 UNC-2A x 3/8 Flt Hd Soc Screw |  |  | McMaster-Carr | 316 SS |  | 0.2 | 0.8 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 17 | 6 | 92185A115 | #4-40 x 1.0 SocHdCap |  |  | McMaster-Carr | 316 SS | Olander Hardware Kit - $16.78/KIT |  | 0
A-200508-17_MotorAssem_Build5. | 15 | 6 | 90585A205 | #4-40 UNC-2A x 5/8 Flt Hd Soc Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $16.78/KIT |  | 0
A-200508-17_MotorAssem_Build5. | 13 | 1 | 90967A155 | External Retaining Ring, DIN 1.4122 SST, for 9 mm OD |  |  | McMaster-Carr | 420 S.S. |  | 0.83 | 0.83 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 11 | 3 | 9513K18 | Gray Plastic 5" x 20" Shim Sheet, 0.0075" Thick |  |  | McMaster-Carr | Polyester |  | 3.45 | 10.35 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 9 | 2 | 7804K118 | SST Ball Bearing, Shielded, 9 mm Shaft Diameter, 17 mm OD |  |  | McMaster-Carr |  |  | 7.41 | 14.82 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 8 | 1 | 91458A14 | Locktite 242 Blue |  |  | McMaster-Carr |  |  |  | 0 | [6 empty] | Chaffey
A-200508-17_MotorAssem_Build5. | 6 | 1 | 7467A51 | ScotchWeld DP420 |  |  | McMaster-Carr |  |  |  | 0 | [6 empty] | Chaffey
A-200508-17_MotorAssem_Build5. | 12 | 2 | VHM-17 | Spring Ring |  |  | Smalley |  |  | 0.099206 | 0.19841 |  | CC | 2017-07-10 | 2017-07-10 |  |  | Chaffey
A-200508-17_MotorAssem_Build5. | 14 | 1 | #2-017-90-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0466 | 0.0466 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Chaffey
A-201667-14_DAT-FoamAssem_V2. | 4 | 1 | MCBH12F | Subconn Micro-12 Plug |  |  | Subconn |  | Reference (on elec. BOM) |  | 0
A-201667-14_DAT-FoamAssem_V2. | 3 | 1 | B270-471 | Benthos DAT |  |  | Teledyne Benthos |  | Reference (on elec. BOM) |  | 0
A-201690-16_PayloadLongNoseShellAssem_Rev.A. | 3 | 1 | A-201464-16 | Pay Load Towing Bail Assembly |  |  | MBARI |  |  |  | 0 | [6 empty] | Parker
A-201690-16_PayloadLongNoseShellAssem_Rev.A. | 1 | 1 | P-200516-08 | Nose Shell | B |  | Waterat | Generic Carbon Epoxy |  | 1850 | 1850 | [6 empty] | Hobson
A-201816-16_PAR-Assem_V3. | 7 | 4 | 92185A148 | #6-32 x 1/2L SocHd Cap Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $12.52/KIT |  | 0
A-201816-16_PAR-Assem_V3. | 6 | 1 | P-201687-16 | PAR Assembly Bracket | B |  | MBARI | ABS |  |  | 0 | [6 empty] | Parker
A-201816-16_PAR-Assem_V3. | 5 | 1 | 1/4 x 5/8L x #10-32 | Soc Hd Shldr Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $12.52/KIT |  | 0
A-201816-16_PAR-Assem_V3. | 4 | 1 | 92185A992 | 316 S.S. 10-32 x 1 Soc Hd Cap |  |  | McMaster-Carr |  | Olander Hardware Kit - $12.52/KIT |  | 0
A-201816-16_PAR-Assem_V3. | 3 | 1 | P-201400-12 | PAR Jacking Lever |  |  | MBARI | Gr. 2 Titanium |  |  | 0 | [6 empty] | Parker
A-201816-16_PAR-Assem_V3. | 2 | 1 | A-201xxx-16 | LICOR PAR - MOD3 |  |  | LICOR / MBARI | Material <not specified> | Reference (on elec. BOM) |  | 0
A-201816-16_PAR-Assem_V3. | 1 | 1 | P-201873-16 | LiCor PAR Jacking Block V4 |  |  | MBARI | ABS |  |  | 0 | [6 empty] | Parker
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 19 | 3 | 92185A198 | #8-32 x 7/8 Socket Head CAp Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $18.50/KIT |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 18 | 2 | 90585A230 | #8-32x.75 Flat Head Socket screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $18.50/KIT |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 17 | 1 | 9334T64 | Polyethylene Tubing (Silver Liner), 3/8" ID, 1/2" OD |  |  | McMaster-Carr |  |  | 2.77 | 2.77 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 16 | 1 | 9334T64 | Polyethylene Tubing (Silver Liner), 3/8" ID, 1/2" OD |  |  | McMaster-Carr |  |  | 2.77 | 2.77 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 15 | 1 | P-201738-15 | Seabird pump bracket |  |  | mbari | H6K PP like |  |  | 0 | [6 empty] | Parker
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 14 | 1 | M5 | SeaBird Submersible Pump |  |  | SeaBird | Material <not specified> | Reference (on elec. BOM) |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 13 | 1 | A-201776-16 | Piped_D.O._Assembly V2 |  |  | MBARI |  |  |  | 0 | [6 empty] | Parker
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 11 | 1 | CPC_EW-06360-97 | Quick-Disconnect Elbow x 3/8 Tube |  |  | Cole Palmer | POM Acetal Copolymer |  |  | 0 | [6 empty] | Chaffey
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 10 | 1 | P-201742-15 | CTD Mount Nut Plate |  |  |  | 6AL-4V Titanium |  |  | 0 | [6 empty] | Chaffey
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 9 | 1 | 96126A169 | 1/4 x 5/8 x 10-32 Soc Shldr Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $18.50/KIT |  | 0 | [6 empty] | Chaffey
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 8 | 6 | 3573A15 | 1/4" screw size bellville spring washer |  |  | McMaster-Carr | Acetal Plastic |  |  | 0 | [6 empty] | Chaffey
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 7 | 4 | 92185A148 | #6-32 x 1/2L SocHd Cap Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $18.50/KIT |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 6 | 1 | P-201712-15 | CTD Nose Bracket |  |  | MBARI | ABS |  |  | 0 | [6 empty] | Parker
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 5 | 1 | GPCTD.x30x | Glider Payload CTD (GPCTD) 350m | A |  | SeaBird Scientific |  | Reference (on elec. BOM) |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 4 | 1 | UAT-376 | Pinger Xducer |  |  | Benthos |  | Reference (on elec. BOM) |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 3 | 1 | A-201523-13 | Neil Brown CTD Assembly V5 |  |  | MBARI |  |  |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 2 | 1 | ECO-MB@-220604 | Eco Puck Flourometer Assembly |  |  | WET Labs |  | Reference (on elec. BOM) |  | 0
A-201917-17_SeaBird_ROWE_Payload Sensor Assembly. | 1 | 1 | A-201777-16 | SeaBird-ROWE Sensor Frame Assembly |  |  | MBARI |  |  |  | 0
A-201776-16_D.O.Assem_V2. | 6 | 1 | 96367A657 | PEEK phillips round head screw, 10-32 x 3/8" L |  |  | McMaster-Carr | PEEK |  | 5.67 | 5.67 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201776-16_D.O.Assem_V2. | 5 | 1 | 4330F | Shallow water / Fast response optode |  |  | Aanderaa |  | Reference (on elec. BOM) |  | 0
A-201776-16_D.O.Assem_V2. | 4 | 1 | #2-127-70-N | O-RING |  |  |  | BUNA - N |  |  | 0 | [6 empty] | Chaffey
A-201776-16_D.O.Assem_V2. | 3 | 1 | 9675T740 | Elbow 3/8 Tube to 3/8 NPT-M |  |  | McMaster-Carr | PE High Density |  | 2.68 | 2.68 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201776-16_D.O.Assem_V2. | 2 | 1 | 9675T570 | 3/8 Tube Barb to 3/8 NPTM |  |  | McMaster-Carr | PE High Density |  | 2.1 | 2.1 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201776-16_D.O.Assem_V2. | 1 | 1 | P-201699-15 | Anderra DO Cover_V3 | A |  | MBARI | POM Delrin (Black) |  |  | 0 | [6 empty] | Parker
A-201902-17_PressHullAssem_BUILD_5. | 21 | 1 | xxxxxxxxxxx | Benthos DAT Board Set |  |  | Benthos Inc. |  | Reference (on elec. BOM) |  | 0
A-201902-17_PressHullAssem_BUILD_5. | 23 | 1 | P-201707-17 | DAT Boardset Bracket, PORT BUILD5 |  | MBARI | Doerksen Precision Products, Inc. | 6061-T6 Alloy |  | 125 | 125 |  | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 22 | 1 | P-201708-17 | Bracket, DAT Boardset, starbd BUILD5 |  | MBARI | Doerksen Precision Products, Inc. | 6061-T6 Alloy |  | 125 | 125 |  | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 17 | 1 | P-201701-15 | Amphenol Back Shell Clamp Block Top |  | MBARI | Doerksen Precision Products, Inc. | ABS |  | 151 | 151 |  | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 16 | 1 | P-201700-15 | Amphenol backshell wire clamp Base | A | MBARI | Doerksen Precision Products, Inc. | ABS |  | 185 | 185 |  | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 13 | 1 | P-201546-13 | Amphenol-Bracket_(TVP-19-88) |  | MBARI | Doerksen Precision Products, Inc. | 5052 - (H34) |  | 127 | 127 | y | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 11 | 1 | P-201542-13 | OpticalSwitchBrkt_V5 | B | MBARI | Doerksen Precision Products, Inc. | Aluminum 6061-T6 |  | 242 | 242 |  | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 3 | 2 | P-200752-09 | Battery Stop Bracket |  | MBARI | Doerksen Precision Products, Inc. | Aluminum 6061-T6 |  | 219 | 438 |  | PO-1710807 | 2017-06-20 | 2017-07-12 |  |  | Parker
A-201902-17_PressHullAssem_BUILD_5. | 4 | 1 | Series 6T | Keller Pressure Sensor |  |  | Keller America | AISI 316 | Reference (on elec. BOM) | 120 | 120 |  | PO-1711087 | 2017-08-17 | 2017-09-27 | 5 weeks |  | Hobson
A-201902-17_PressHullAssem_BUILD_5. | 26 | 3 | 90715A115 | #10-32 NYLOK NUT |  |  | McMaster-Carr | 316 S.S. |  | 0.23 | 0.69 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 25 | 3 | 98164A106 | #6-32 x 1/4 Soc Button Hd Screw |  |  | McMaster-Carr | AISI 316 |  | 0.09 | 0.27 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 24 | 4 | 92185A190 | #8-32 x 1/4 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.13 | 0.52 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 20 | 4 | 92185A121 | #4-40 x 1-1/2 Socket Head Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.59 | 2.36 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 19 | 2 | 92185A113 | #4-40 x 7/8 Socket Head Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.23 | 0.46 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 18 | 4 | 94615A112 | #4-40 Brass Shoulder Thrd Insert |  |  | McMaster-Carr | Brass |  | 0.21 | 0.84 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 7 | 2 | 92185A537 | 1/4-20 x 1/2 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.3 | 0.6 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 35 | 6 |  | "P" Clamp |  |  |  | Nylon |  |  | 0
A-201902-17_PressHullAssem_BUILD_5. | 10 | 4 | 561-P440-1.5 | #4-40 x 1.25 Nylon Pan Hd Phill Screw |  |  | Mouser | Nylon 6/10 |  | 0.26 | 1.04 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201902-17_PressHullAssem_BUILD_5. | 9 | 4 | #6-32xp25 | #4 x 3/4 StandOff | [5 empty] | 0.5 | 2 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-200467-17_PressHull_BUILD_5 | 40 | 1 | 701-00006 | Pressure Relief Valve |  | DeepSea Power & Light | DeepSea Power & Light | 6AL-4V Titanium |  | 280 | 280 |  | PO-1710759 | 2017-06-05 | 2017-06-14 |  | po sent | Raanan
A-200467-17_PressHull_BUILD_5 | 3 | 1 | P-200626-08 | PressHull_EndDome_FWD | G | MBARI | El Camino Machine & Welding, LLC | 6061-T6 Alloy |  | 7753.465 | 7753.465 |  | PO-1710718 | 2017-05-19 |  |  | po confirmed | Parker
A-200467-17_PressHull_BUILD_5 | 2 | 1 | P-200466-08 | PressHull_EndDome_AFT | C | MBARI | El Camino Machine & Welding, LLC | Material <not specified> |  | 7753.465 | 7753.465 |  | PO-1710718 | 2017-05-19 |  |  | po confirmed | Parker
A-200467-17_PressHull_BUILD_5 | 6 | 1 | A-200579-14 | Internal Elect./Batt Chassis_WELMENT_V3 | D | MBARI | Larkin |  | Lot Charge | 2670 | 2670 |  | PO-1710756 | 2017-06-02 | 2017-07-24 |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 29 | 2 | P-200882-10 | Grounding Spring_V3 | A | MBARI | Sierra Precision | Beryllium-Copper CDA172 |  | 53.55 | 107.1 |  | PO-1710942 | 2017-07-13 |  |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 1 | 1 | P-200465-08 | Seamless Drawn Alum Tube (12 x .5) | C | MBARI | Rhinestahl AMG | 6061-T6 Alloy |  | 3246 | 3246 |  | PO-1710928 | 2017-07-11 |  |  |  | Parker
A-200467-17_PressHull_BUILD_5 |  | 2 | P-201645-14 | TETHYS - LRAUV Tube End Protection |  | MBARI | Rhinestahl AMG |  |  | 564 | 1128 |  | PO-1710928 | 2017-07-11 |  |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 39 | 1 | 5533K433 | PVDF Compression Tube Fitting |  |  | McMaster-Carr | PVDF - Kynar |  | 2.92 | 2.92 |  | CC | 2017-05-30 | 2017-05-31 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 36 | 1 | 92174A440 | 1/2-20 Hex Nut |  |  | McMaster-Carr | Brass |  | 0.755 | 0.755 |  | CC | 2017-05-30 | 2017-05-31 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 30 | 2 | 92185A190 | #8-32 x 1/4 SOC HD CAP |  |  | MCMASTER-CARR | 316 SS |  | 0.132 | 0.264 |  | CC | 2017-05-30 | 2017-05-31 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 28 | 2 | 93996A710 | 3/16 x 1/8L Soc Shldr Screw x 8-32 |  |  | McMaster-Carr | AISI 304 |  | 3.13 | 6.26 |  | CC | 2017-05-30 | 2017-05-31 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 27 | 4 | 94051A220 | 1/4 Flat Washer |  |  | McMaster-Carr | Titanium Gr2 |  | 1.91 | 7.64 |  | CC | 2017-05-30 | 2017-05-31 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 24 | 4 | 90545A029 | 1/4-20 Hex Nut |  |  | McMaster-Carr | Titanium Gr2 |  | 2.57 | 10.28 |  | CC | 2017-05-30 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 43 | 1 | 2-014 | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0428 | 0.0428 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 42 | 4 | 93190A540 | 1/4-20 UNC-2A x 3/4 Hex Hd Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.1924 | 0.7696 |  | CC | 2017-05-31 | 2017-05-31 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 35 | 1 | #2-020-70-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0567 | 0.0567 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 34 | 1 | 3-905 | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0398 | 0.0398 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 33 | 1 | #2-015 | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0436 | 0.0436 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 19 | 2 | #2-017-70-N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 0.0466 | 0.0932 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 5 | 2 | #2-277-70N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 2.152 | 4.304 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 4 | 2 | #2-276-70N | O-RING |  |  | McMaster-Carr | BUNA - N |  | 2.128 | 4.256 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 38 | 1 | 365-1260-ND | Optical Interruptor Switch - OPB817 |  | OPTEK | DigiKey |  |  | 3.7 | 3.7 |  | CC | 2017-05-31 | 2017-06-07 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 25 | 8 | PCC_C21-003 | Bellville spring washer |  |  | Product Component Parts | DELRIN |  | 0.0845 | 0.676 |  | CC | 2017-06-05 | 2017-06-12 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 26 | 4 | C27460 | Nylon Shoulder Bushing |  |  | Product Components Corp. | Nylon 6/10 |  | 0.076 | 0.304 |  | CC | 2017-06-05 | 2017-06-12 |  |  | Raanan
A-200467-17_PressHull_BUILD_5 | 41 | 16 | A-201xxx-16 | #8 Helicoil / G10 Thread Repair Plug |  | MBARI | Prunella |  |  | 7.5 | 120 | y | PO-1710819 | 2017-06-20 |  |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 32 | 1 | P-201623-14 | LRAUV MINK Adapter |  | MBARI | Prunella | 316 SST |  | 143.1 | 143.1 |  | PO-1710819 | 2017-06-20 | 2017-08-28 |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 18 | 1 | P-200686-09 | ISUS Adaptor Custom Jamm Nut | A | MBARI | Prunella | Aluminum 6061-T6 |  | 74.1 | 74.1 | y | PO-1710819 | 2017-06-20 | 2017-08-28 |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 17 | 1 | P-201705-15 | ISUS_Probe_BulkHd Blank |  | MBARI | Prunella | Titanium 6AL-4V |  | 198.6 | 198.6 |  | PO-1710819 | 2017-06-20 | 2017-08-28 |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 8 | 3 | P-201709-15 | DGO Adaptor (SAE #6) |  | MBARI | Prunella | 6AL-4V Titanium |  | 67.5 | 202.5 |  | PO-1710819 | 2017-06-20 | 2017-08-28 |  |  | Parker
A-200467-17_PressHull_BUILD_5 | 23 | 1 | SS-400-2-4ST | 1/4 Tube - 1/4 Tube Stub |  |  | Swagelok |  |  | 23.04 | 23.04 |  | PO-1710740 Rev. 2 | 2017-05-30 | 2017-06-14 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 22 | 2 | SS-4-TA-7-4RP | Female Adapter (ISO Parallel Thread) - Fractional |  |  | Swagelok |  |  | 19.22 | 38.44 |  | PO-1710740 Rev. 1 | 2017-05-30 | 2017-06-14 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 21 | 1 | SS-400-3 | 1/4 Tube "T" |  |  | Swagelok | AISI 316 |  | 27.01 | 27.01 |  | PO-1710740 Rev. 0 | 2017-05-30 | 2017-06-14 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 20 | 1 | SS-4-TA-1-4ST | 4 SAE to 1/4 Tube Adaptor |  |  | Swagelok | AISI 316 |  | 9.04 | 9.04 |  | PO-1710740 Rev. 1 | 2017-05-30 | 2017-06-14 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 | 11 | 1 | SS-400-1-4ST | Male SAE/MS Straight Thread |  |  | Swagelok | 316 S.S. |  | 10.66 | 10.66 |  | PO-1710740 Rev. 1 | 2017-05-30 | 2017-06-14 |  | po confirmed | Raanan
A-200467-17_PressHull_BUILD_5 |  | 1 |  | Paint |  | MBARI | WaterRat |  |  | 525 | 525
A-201xxx-13_ZincAnodeAssem | 3 | 5 | #2-013 | O-RING |  |  | McMaster-Carr | BUNA - N | Part of A-200467-17_PressHull_BUILD_5 | 0.0413 | 0.2065 |  | CC | 2017-05-31 | 2017-06-01 |  |  | Raanan
A-201xxx-13_ZincAnodeAssem | 2 | 5 | 93025A961 | 1/4-20 Brass Stud x 1.00 |  |  | McMaster-Carr | Brass | Part of A-200467-17_PressHull_BUILD_5 | 1 | 5 |  | CC | 2017-06-05 |  |  |  | Raanan
A-201xxx-13_ZincAnodeAssem | 1 | 5 | P-201030-11 | Zinc Anode from Bar Stock | A | MBARI | Prunella | Zinc - 99.6% | Part of A-200467-17_PressHull_BUILD_5 | 36 | 180 | y | PO-1710819 | 2017-06-20 | 2017-08-28 |  |  | Parker
A-200579-14_InternalChassis_V3.Rev.D | 6 | 4 | P-201326-12 | Chassis Tie Rod End Fix | - | MBARI | Larkin | Titanium 6AL-4V | Lot Price - reflected in assy. |  | 0 |  | PO-1710756 | 2017-06-02 | 2017-07-24 |  |  | Parker
A-200579-14_InternalChassis_V3.Rev.D | 5 | 4 | P-200569-08 | Chassis TieRod | C | MBARI | Larkin | 6061-T6 Alloy | Spare +2 |  | 0 |  | PO-1710756 | 2017-06-02 | 2017-07-24 |  |  | Parker
A-200579-14_InternalChassis_V3.Rev.D | 3 | 1 | P-200881-14 | New Chassis Rail Box Truss_V3 |  | MBARI | Larkin | 6061-T6 Alloy |  |  | 0 |  | PO-1710756 | 2017-06-02 | 2017-07-24 |  |  | Parker
A-200579-14_InternalChassis_V3.Rev.D | 2 | 4 | P-200425-07 | Adaptor Lug_Chassis-End Cap | - | MBARI | Larkin | Aluminum 7075-T6 | Spare +2 |  | 0 |  | PO-1710756 | 2017-06-02 | 2017-07-24 |  |  | Parker
A-200579-14_InternalChassis_V3.Rev.D | 1 | 4 | P-201471-12 | Chassis Rod End |  | MBARI | Larkin | 6061-T6 Alum. |  |  | 0 |  | PO-1710756 | 2017-06-02 | 2017-07-24 |  |  | Parker
A-200579-14_InternalChassis_V3.Rev.D | 7 | 4 | 96095A155 | Gr 2 Titanium Threaded Stud |  |  | McMaster-Carr | Titanium Gr2 |  | 36.21 | 144.84 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200579-14_InternalChassis_V3.Rev.D | 4 | 6 | 92185A194 | 8-32 x 1/2 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 3.15 | 18.9 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200579-14_InternalChassis_V3.Rev.D | 8 | 8 | #2-109-70-N | O-RING |  |  |  | BUNA - N |  | 0.02 | 0.16 |  | CC | 2017-06-01 | 2017-06-02 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 7 | 1 | 223-1661-ND | String Pot - SP1-12 |  | Celesco Technologies | Digikey |  | Spare +1 | 175.35 | 175.35 |  | CC | 2017-06-07 | 2017-06-13 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 6 | 1 | MS204XDOPT - MGCS04S | Gear Pump 12V |  |  | Clark Solutions Inc. |  |  | 398.8 | 398.8 |  | PO-1710851 | 2017-06-26 | 2017-07-07 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 15 | 1 | P-201493-13 | String Pot Adjuster | A |  | MBARI | ABS |  |  | 0 | [6 empty] | Parker
A-201330-12_VB-Sys_V2 | 9 | 1 | A-200991-11 | LRAUV VB Sys. Valve Assembly |  |  | MBARI |  |  | 1841.9237 | 1841.9237
A-201330-12_VB-Sys_V2 | 2 | 1 | A-200620-08 | VB-Reservoir |  |  | MBARI |  |  | 3073.5494 | 3073.5494
A-201330-12_VB-Sys_V2 | 1 | 1 | P-201331-12 | Mounting Plate for VB-Reservoir | A | MBARI | National Fabtronix, Inc | 5052-(H34) Alum. |  | 236.38 | 236.38 | y | PO-1710931 | 2017-07-12 | 2017-07-24 |  |  | Parker
A-201330-12_VB-Sys_V2 | 14 | 2 | 90257A411 | #10-32 Hex Nut |  |  | McMaster-Carr | AISI 316 |  | 0.0729 | 0.1458 |  | CC | 2017-06-07 | 2017-06-09 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 19 | 4 | 92185A | #4-40x.375 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 |  | 0.3352 | 1.3408 |  | CC | 2017-06-07 | 2017-06-09 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 18 | 2 | 92185A190 | #8-32 x 1/4 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.132 | 0.264 |  | CC | 2017-06-07 | 2017-06-09 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 20 | 6 | 92185A194 | #8-32 x 1/2 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 |  | 0.126 | 0.756 |  | CC | 2017-06-07 | 2017-06-09 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 13 | 2 | 92185A989 | #10-32 x 1/2 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 |  | 0.1704 | 0.3408 |  | CC | 2017-06-07 | 2017-06-09 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 5 | 1 | PSW-534 | Omega Pressure Switch |  | Omega Enggineering Inc | Omega |  | Reference (on elec. BOM) | 143 | 143 |  | cc | 2017-08-30 | 2017-08-05 |  |  | Hobson
A-201330-12_VB-Sys_V2 | 12 | 1 | 1/4 Inch Tube x .035 wall | Reservoir - Pump Tube |  |  | Swagelok | 316 SS |  | 1.124 | 1.124 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 11 | 1 | SS-400-1-2 | 1/4 Tube - 1/8 NPTM |  |  | Swagelok | 316 S.S. |  | 8.18 | 8.18 |  | PO-1710775 | 2017-06-08 | 2017-06-12
A-201330-12_VB-Sys_V2 | 10 | 1 | 1/4 Inch Tube x .035 wall | Pump - Valve Tube |  |  | Swagelok | 316 SS |  | 1.124 | 1.124 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 8 | 1 | 1/4 Inch Tube x .035 wall | Valve - Dome Tube |  |  | Swagelok |  |  | 1.124 | 1.124 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 4 | 1 | SS-4-TA-7-2 | 1/8NPTFemale Adapter (Tapered Thread) - 1/4Tube |  |  | Swagelok | 316 SS |  | 9.53 | 9.53 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 3 | 1 | SS-400-3TST | 1/4Tube-#4SAE street "T" |  |  | Swagelok | 316 S.S. |  | 49.36 | 49.36 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 17 | 1 | SS-400-9 | 1/4 x 1/4 Tube Elbow |  |  | Swagelok | AISI 316 |  | 19.22 | 19.22 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-201330-12_VB-Sys_V2 | 16 | 1 | SS-4-TA-1-2 | 1/4 Tube Stub to 1/8 NPT |  |  | Swagelok | AISI 316 |  | 6.68 | 6.68 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-200620-08_VB-Resrvoir | 7 | 1 | P-200624-08 | Piston Shaft Tube End | B | MBARI | A & D Precision Inc | Aluminum 6061-T6 |  | 165 | 165 |  | PO-1710925 | 2017-07-11 | 2017-08-08 |  |  | Parker
A-200620-08_VB-Resrvoir | 5 | 1 | P-200643-08 | Curved Lip Piston Retainer Plate |  | MBARI | A & D Precision Inc | ABS |  | 420 | 420 |  | PO-1710925 | 2017-07-11 | 2017-08-08 |  |  | Parker
A-200620-08_VB-Resrvoir | 3 | 1 | P-200642-08 | VB res. Cap | B | MBARI | A & D Precision Inc | POM Delrin Homopolymer |  | 787.5 | 787.5 |  | PO-1710925 | 2017-07-11 | 2017-08-08 |  |  | Parker
A-200620-08_VB-Resrvoir | 1 | 1 | P-200652-09 | Cylinder-End | C | MBARI | A & D Precision Inc | ABS |  | 855 | 855 |  | PO-1710925 | 2017-07-11 | 2017-08-08 |  |  | Parker
A-200620-08_VB-Resrvoir | 6 | 1 | 1A-375x375 | Class 1A Diaphragm |  |  | Bellofram | Code #59 (Nitrile) | Unit Cost for odering QT. 10 | 65.87 | 65.87 |  | PO-1710712 | 2017-05-19 | 2017-06-28 |  | po sent | Raanan
A-200620-08_VB-Resrvoir | 9 | 1 | #4011 | COMP. SPRING Open |  |  | Century Spring | Hard Drawn Wire |  | 36.806 | 36.806 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 4 | 1 | P-200619-08 | Bellofram Piston | B | MBARI | MBARI | ABS -plus |  |  | 0 | [6 empty] | Parker
A-200620-08_VB-Resrvoir | 2 | 1 | P-200591-08 | Cylinder Body for VB | C |  | Doerksen Precision Products, Inc. | POM Delrin Homopolymer |  | 675 | 675 |  | PO-1710953 | 2017-07-14 | 2017-08-16 |  |  | Parker
A-200620-08_VB-Resrvoir | 14 | 6 | 92185A148 | #6-32 x 1/2 Soc Hd Cap |  |  | McMaster-Carr | AISI 316 |  | 0.1024 | 0.6144 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 13 | 2 | 7889A44 | Torpedo Lock, welding rod |  |  | McMaster-Carr | Polypropylene 1/8 x 5.875 |  | 11.02 | 22.04 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 12 | 1 | 90575A410 | Fully Threaded Stud |  |  | McMaster-Carr | 316 SS |  | 0.841 | 0.841 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 11 | 1 | #2447K110 | Rod End #10-32 |  |  | Mcmaster-Carr | Zinc Plated Steel |  | 6.72 | 6.72 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 10 | 2 | 6377K61 | Sleeve Bearing |  |  | McMaster-Carr | Rulon J |  | 15.49 | 30.98 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 8 | 1 | 89785K849 | Piston Shaft Tube |  |  | McMaster-Carr | 316 S.S. (A213) |  | 11.16 | 11.16 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200620-08_VB-Resrvoir | 15 | 1 | SS-400-2-4ST | 1/4 Tube - SAE#4 Elbow |  |  | Swagelok |  |  | 23.04 | 23.04 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-200991-11_ValveAssem | 8 | 1 | P-201351-12 | Valve Base |  | MBARI | A & D Precision Inc. | Aluminum 6061-T6 |  | 570 | 570 |  | PO-1710813 | 2017-06-19 | 2017-08-08 |  |  | Parker
A-200991-11_ValveAssem | 6 | 1 | P-201067-11 | Mag-Pole Piece |  | MBARI | A & D Precision Inc. | AISI 1010 Hot Rolled Steel Bar |  | 187.5 | 187.5 |  | PO-1710813 | 2017-06-19 |  |  |  | Parker
A-200991-11_ValveAssem | 4 | 1 | P-201066-11 | Magnet Carrier |  | MBARI | A & D Precision Inc. | PEEK |  | 315 | 315 |  | PO-1710813 | 2017-06-19 | 2017-08-08 |  |  | Parker
A-200991-11_ValveAssem | 1 | 1 | P-200992-11 | Valve Mount Rib | B | MBARI | A & D Precision Inc. | Aluminum 6061-T6 |  | 277.5 | 277.5 |  | PO-1710813 | 2017-06-19 | 2017-08-08 |  |  | Parker
A-200991-11_ValveAssem | 5 | 1 | D101-N52 | NdFeB Magnet |  |  | K&J Magnetics | NdFeB - N52 |  | 0.14 | 0.14 |  | CC | 2017-06-22 |  |  |  | Raanan
A-200991-11_ValveAssem | 2 | 1 | REmax221024_110340 | Re-max21, CLL 3.5W |  |  | Maxon |  |  | 207.7 | 207.7 |  | PO-1710720 | 2017-05-22 | 2017-07-06 |  | po confirmed | Raanan
A-200991-11_ValveAssem | 19 | 1 | 10020689ra | VB Valve Control Board |  |  | MBARI |  | Reference (on elec. BOM) |  | 0 | [6 empty] | Rosal
A-200991-11_ValveAssem | 3 | 1 | P-200986-11 | Shaft Coupling_LRAUV | A |  | Doerksen Precision Products, Inc. | Aluminum 6061-T6 |  | 213 | 213 |  | PO-1710952 | 2017-07-14 | 2017-08-16 |  |  | Parker
A-200991-11_ValveAssem | 9 | 1 | P-201302-12 | Panel Mount Bracket |  |  | MBARI | 5052-(H34) Alloy |  |  | 0 | [6 empty] | Parker
A-200991-11_ValveAssem | 17 | 2 | 91375A105 | #4-40x.1875 Cup Pt Set Screw |  |  | McMaster-Carr |  |  | 0.1 | 0.2 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 16 | 2 | 94639A202 | #4 nylon Washer |  |  | McMaster-Carr |  |  | 0.09 | 0.18 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 15 | 2 | 96110A008 | #4-40 Threaded Bushing |  |  | McMaster-Carr | Nylon 6/6 |  | 1.06 | 2.12 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 14 | 4 | 91500A126 | #4-40 x 3/8 Flt Hd Phil |  |  | McMaster-Carr | AISI 316 |  | 0.092 | 0.368 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 13 | 4 | 91735A102 | #4-40 x 1/4 Pan Hd Phil |  |  | McMaster-Carr | AISI 316 |  | 0.0746 | 0.2984 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 12 | 2 | 92185A190 | #8-32 x 1/4 SOC HD CAP |  |  | McMaster-Carr | 316 SS |  | 0.132 | 0.264 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 11 | 3 | 92010A | M2.5x6 FLT HD Phillips (Metric) |  |  | McMaster-Carr | 18-8 Stainless Steel |  | 0.0419 | 0.1257 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 10 | 1 | 92845A190 | Dog Pt. Sckt Set Screw |  |  | McMaster-Carr | 18-8 S.S. |  | 0.198 | 0.198 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 7 | 1 | 98195A520 | SpringPinCoiled 1/8x0.750 |  |  | McMaster-Carr | 18-8 S.S. |  | 0.4952 | 0.4952 |  | CC | 2017-06-22 | 2017-06-23 |  |  | Raanan
A-200991-11_ValveAssem | 18 | 1 | SS-4P4T | NUPRO BALL VALVE 1/4T-1/4T |  |  | SWAGELOK |  |  | 68.8 | 68.8 |  | PO-1710775 | 2017-06-08 | 2017-06-12 |  |  | Raanan
A-200991-11_ValveAssem | 20 | 1 | 10020864rA | Maxon21_tcb (MBARI built connector adapter) |  |  | MBARI |  | Reference (on elec. BOM) |  | 0 | y | [5 empty] | Rosal
A-201541-13_SecBattAssem_V3.3 | 14 | 1 | P-201702-15 | Nook Ball Screw Aft Cover |  | MBARI | SAE Engineering, Inc. | ABS |  | 104.5 | 104.5 |  | PO-1710984 | 2017-07-27 |  |  |  | Parker
A-201541-13_SecBattAssem_V3.3 | 12 | 8 | 92185A144 | #6-32 x 1/4 SocHd Cap |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $40.81/KIT |  | 0
A-201541-13_SecBattAssem_V3.3 | 11 | 24 | 92185A106 | #4-40 x 1/4 SOC HD Cap SCREW |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $40.81/KIT |  | 0
A-201541-13_SecBattAssem_V3.3 | 10 | 12 | 36-8400-ND | #4-40 x 3/8 Standoff |  |  | Keystone / Digikey | Aluminum 6061-T6 |  | 0.55 | 6.6 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201541-13_SecBattAssem_V3.3 | 9 | 2 | P-201583-13 | WireGuard_V3.3 | B | MBARI | SAE Engineering, Inc. | 5052-(H34) Alloy |  | 35.79 | 71.58 |  | PO-1710984 | 2017-07-27 | 2017-08-29 |  |  | Parker
A-201541-13_SecBattAssem_V3.3 | 8 | 2 | P-201582-13 | Secondary Battery Shear Plate Assembly |  | MBARI | SAE Engineering, Inc. |  |  | 49.82 | 99.64 |  | PO-1710984 | 2017-07-27 | 2017-08-29 |  |  | Parker
A-201541-13_SecBattAssem_V3.3 | 7 | 1 | 8627K159 | 1/2 x 1/16wall ACETAL Tube x 36" long (raw stock) |  | MBARI | McMaster-Carr | DELRIN (ACETAL) |  | 2.93 | 2.93 |  | PO-1710984 | 2017-07-27 |  |  |  | Parker
A-201541-13_SecBattAssem_V3.3 | 6 | 6 | 92395A113 | #6-32 Brass Press-Fit Expansion Insert |  |  | McMaster-Carr | Brass |  | 0.06 | 0.36 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201541-13_SecBattAssem_V3.3 | 5 | 4 | 94435A336 | #10-32 Threaded Rod |  |  | McMaster-Carr | Aluminum 6061-T6 | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201541-13_SecBattAssem_V3.3 | 4 | 8 | 90715A115 | #10-32 NYLOK NUT |  |  | McMaster-Carr | 316 S.S. | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201541-13_SecBattAssem_V3.3 | 3 | 8 |  | #10 SAE FLAT WASHER |  |  | McMaster-Carr | 316 S.S. | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201541-13_SecBattAssem_V3.3 | 1 | 1 | P-201540-13 | Battery Pack Support Plate | B | MBARI | SAE Engineering, Inc. | ABS |  | 719.44 | 719.44 |  | PO-1710984 | 2017-07-27 | 2017-08-31 |  |  | Parker
A-201534-13_CombinedCircuitBrdAssem | 6 | 4 | 36-1894-ND | #4_female-female stand off x 5/8 L |  |  | Keystone / Digikey | 6061-T6 Aluminum |  | 0.55 | 2.2 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201534-13_CombinedCircuitBrdAssem | 5 | 4 | 91780A534 | #4_Stand Off x 5/8 L (3/16 Hex) |  |  | McMaster-Carr | 6061-T6 Aluminum |  | 0.55 | 2.2 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201534-13_CombinedCircuitBrdAssem | 4 | 4 | 91780A525 | #4_Stand Off x 1/4 L (3/16 Hex) |  |  | McMaster-Carr | 6061-T6 Aluminum |  | 0.41 | 1.64 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201534-13_CombinedCircuitBrdAssem | 3 | 4 | 91772A122 | #4-40 UNC x 1 3/8 LOng |  |  | McMaster-Carr | 18-8 S.S. |  | 0.08 | 0.32 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201621-14_BlkHdAssem_V3.3 | 4 | 24 | 92395A112 | #4-40 Brass Press-Fit expansion Insert |  |  | McMaster-Carr | Brass |  | 0.05 | 1.2 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201621-14_BlkHdAssem_V3.3 | 3 | 12 | 92185A110 | #4-40 x 1/2 Soc Hd Cap Screw |  |  | McMaster-Carr | AISI 316 |  | 0.15 | 1.8 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201621-14_BlkHdAssem_V3.3 | 2 | 2 | P-201537-13 | Battery Pack Support Plate | F | MBARI | SAE Engineering, Inc. | ABS |  | 488.16 | 976.32 |  | PO-1710948 | 2017-07-27 | 2017-08-31 |  |  | Parker
A-201906-17_InspEnBatts_V3.3 | 16 | 12 | 7566K13 | Cradle Clamp #8 |  |  | McMaster-Carr | Nylon 6/10 |  | 0.11 | 1.32 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201906-17_InspEnBatts_V3.3 | 12 | 12 | 36-2201-ND | #4_female-female stand Off x 1/4 L |  |  | Keystone / Digikey | 6061-T6 Aluminum |  | 0.5 | 6 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201906-17_InspEnBatts_V3.3 | 5 | 8 | 455 | #10 Phenolic Stand-off x 1/2 |  |  | Mouser/Keystone Electronics | Phenolic |  | 0.45 | 3.6 |  | cc | 2017-10-11 |  |  |  | Chaffey
A-201906-17_InspEnBatts_V3.3 | 8 | 4 | P0200563 right | BattPackWheelAssem_Mirror |  |  | MBARI |  |  | 38.62 | 154.48 |  | 1710984 |  | 2017-08-29 |  |  | Parker
A-201906-17_InspEnBatts_V3.3 | 6 | 2 | P-201538-13 | Battery Pack Bulkhead Plate | B |  | SAE Engr. | POM Delrin Homopolymer |  | 340 | 680 |  | 1710984 |  | 2017-08-31 |  |  | Parker
A-201906-17_InspEnBatts_V3.3 | 20 | 8 | 91735A102 | #4-40 x 1/4 Pan Hd Phil |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 18 | 12 | 92395A112 | #4-40 Brass Press-Fit expansion Insert |  |  | McMaster-Carr | Brass |  | 0.05 | 0.6 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201906-17_InspEnBatts_V3.3 | 17 | 12 | 91735A192 | #8-32 x 3/8 Pan Hd Phill Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 15 | 8 | 92395A113 | #6-32 Brass Press-Fit Expansion Insert |  |  | McMaster-Carr | Brass |  | 0.06 | 0.48 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201906-17_InspEnBatts_V3.3 | 14 | 8 | 92395A319 | 6-32 x 1/4 Insert |  |  | McMaster-Carr | Brass | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 13 | 12 | 91841A005 | #4-40 HEX NUT |  |  | McMASTER-CARR | 18-8 Stainless Steel | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 11 | 12 | 90295A059 | #4 Nylon Washer |  |  | McMaster-Carr | Nylon 6/10 | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 10 | 12 | 93250A002 | #4-40 UNC-2A Threaded Rod x 12 inch |  |  | McMaster-Carr | 304 SS | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 9 | 16 | 90585A212 | Flt Hd Soc Screw #6-32 x 3/8 |  |  | McMaster-Carr |  | Olander Hardware Kit - $40.81/KIT |  | 0 | [6 empty] | Chaffey
A-201906-17_InspEnBatts_V3.3 | 4 | 12 | P-201632-14 / 8627K129 | 3/16 x 1/32wall ACETAL Tube x 10.462 long | B |  | McMaster-Carr | DELRIN (ACETAL) | Olander Hardware Kit - $40.81/KIT |  | 0 |  |  |  | 2017-08-29 |  |  | Chaffey
A-201906-17_InspEnBatts_V3.3 | 19 | 2 | P-201728-15 | Battery Controller-Shield |  | MBARI | SAE Engineering, Inc. | FR4 Fiberglass Epoxy Laminate Sheet |  | 54.38 | 108.76 |  | PO-1710984 | 2017-07-27 | 2017-08-31 |  |  | Parker
A-201906-17_InspEnBatts_V3.3 | 7 | 4 | P-200563-08 left | IdlerWheelAssem |  | MBARI | SAE Engineering, Inc. |  |  | 38.62 | 154.48 | y | PO-1710984 | 2017-07-27 | 2017-08-29 |  |  | Parker
A-201906-17_InspEnBatts_V3.3 | 3 | 2 | P-201539-13 | Battery Pack Support Plate Half | C | MBARI | SAE Engineering, Inc. | ABS |  | 430.06 | 860.12 |  | PO-1710984 | 2017-07-27 | 2017-08-31 |  |  | Parker
A-201906-17_InspEnBatts_V3.3 |  | 8 | A 7ZB5-URG07537 | Idler Roller |  | Stock Drive Products | Stock Drive Products | Urethane | Ordered 13 on 10/17 | 15.86 | 126.88 |  |  | 2017-10-17 |  |  |  | Parker
A-201907-17_FlagAssem_V2 | 2 | 1 | 2449K110 | fiber-reinforced nylon clevis rod end |  |  | McMaster-Carr |  |  | 3.25 | 3.25 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201907-17_FlagAssem_V2 | 3 | 1 | P-201543-13 | Optical Flag_V5 | A | MBARI | SAE Engineering, Inc. | 6061-T6 Alloy |  | 86.46 | 86.46 |  | PO-1710948 | 2017-07-27 | 2017-08-29 |  |  | Parker
A-201907-17_FlagAssem_V2 | 1 | 1 | P-201633-14 | Flag Mount Plt |  | MBARI | SAE Engineering, Inc. | Aluminum 6061-T6 |  | 28.38 | 28.38 |  | PO-1710948 | 2017-07-27 | 2017-08-29 |  |  | Parker
A-201907-17_FlagAssem_V2 | 4 | 1 | 90585A287 | #10-32 x 3/8 FltHd Screw |  |  | McMaster-Carr | AISI 316 |  | 0.3 | 0.3 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201567-14_Complete Drive Assembly_V4.Rev.A | 2 | 1 | WAL 15-3-4 | Motor Shaft Coupling |  |  | Helical Products | S.S. 17-4 PH |  |  | 0 |  | 1711000 Rev. 1 | 2017-08-01 | 2017-09-10 | 5 weeks |  | Hobson
A-201567-14_Complete Drive Assembly_V4.Rev.A | 3 | 1 | 110138/110357/MR-201935 | Maxon Motor-Gearbox 84:1 |  |  | MAXON |  |  | 261.15 | 261.15 |  | PO-1710720 | 2017-05-22 | 2017-07-06 |  | po confirmed | Raanan
A-201567-14_Complete Drive Assembly_V4.Rev.A | 8 | 1 | P-201561-14 | Gimbal Drive Yoke_V4 | A |  | MBARI | 6061-T6 Alloy |  | 217.5 | 217.5 | y | PO-1710811 | 2017-06-19 | 2017-08-04 |  |  | Parker
A-201567-14_Complete Drive Assembly_V4.Rev.A | 7 | 1 | P-201562-13 | Motor Drive Mount V2 |  |  | MBARI | 6061-T6 Alloy |  | 202.5 | 202.5 | y | PO-1710811 | 2017-06-19 | 2017-08-04 |  |  | Parker
A-201567-14_Complete Drive Assembly_V4.Rev.A | 5 | 1 | P-200560-08 | Mount Flange for Nook Ball Nut | B |  | MBARI | 6061-T6 Alloy |  | 157 | 157 | y | PO-1710811 | 2017-06-19 | 2017-08-04 |  |  | Parker
A-201567-14_Complete Drive Assembly_V4.Rev.A | 10 | 2 | 97345A163 | 1/4 x 5/16 #10-24 x 3/8L SocHdSldrScrew |  |  | McMaster-Carr | AISI 316 |  | 3.77 | 7.54 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201567-14_Complete Drive Assembly_V4.Rev.A | 9 | 4 | 92185A993 | #10-32 x 1/25 SOC HD CAP SCREW |  |  | McMaster-Carr | AISI 316 |  | 0.56 | 2.24 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201567-14_Complete Drive Assembly_V4.Rev.A | 6 | 2 | 92845A110 | #4-40 x 3/16 Dog Point Set Screw |  |  | McMaster-Carr | 18 - 8 S.S. |  | 0.2 | 0.4 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201567-14_Complete Drive Assembly_V4.Rev.A | 4 | 2 | 92010A001 | Flat HD Phillips Screw |  |  | McMaster-Carr | 18-8 SS M2 X 4 |  | 0.04 | 0.08 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201567-14_Complete Drive Assembly_V4.Rev.A | 1 | 1 | ECS-08010-RAEL-4L-270 / ECN- 08010-RZN/S | NOOK Ball Screw Assembly |  |  | NOOK Industries |  |  | 1012.31 | 1012.31 |  | PO-1710715 | 2017-05-18 | 2017-07-19 |  | po confirmed | Raanan
3 way mux assy | 1 | 1 | 3 way mux box | 11021197 |  | MBARI | Doerksen Precision Products, Inc. |  |  | 185 | 185 | y | PO-1710867 | 2017-06-29 | 2017-07-21 |  |  | Parker
4 way mux assy | 4 | 1 | 3 way mux cover | 11021198 |  | MBARI | Doerksen Precision Products, Inc. |  |  | 124 | 124 | y | PO-1710867 | 2017-06-29 | 2017-07-21 |  |  | Parker
A-201882-17_RF chassis_V2 | 12 | 4 | 90295A100 | #8 Nylon Washer |  |  | McMaster-Carr | Nylon 6/10 |  | 0.07 | 0.28 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201882-17_RF chassis_V2 | 11 | 4 | 91500A084 | #12-56 x 1/4 Phil Flt Hd Screw |  |  | McMaster-Carr | AISI 316 |  | 0.09 | 0.36 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201882-17_RF chassis_V2 | 3 | 3 | 90585A200 | #4-40 UNC-2A x 1/4L Flt Sckt Hd Cap |  |  | McMaster-Carr | AISI 316 |  | 0.22 | 0.66 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201882-17_RF chassis_V2 | 1 | 1 | A-201654-16 | CradlePoint-NAL Bracket Asembly |  | MBARI | Nationial Fabtronix, Inc. |  |  | 378.69 | 378.69 | y | PO-1710873 | 2017-06-28 | 2017-07-11 |  |  | Parker
A-201904-17_LoadContAssem_V2 | 5 | 1 | P-201677-14 | Load Control Retaining Bar_LONG |  | MBARI | A & D Precision Inc. | BLACK DELRIN (Acetal) |  | 210 | 210 | y | PO-1710811 | 2017-06-19 | 2017-08-04 |  |  | Parker
A-201904-17_LoadContAssem_V2 | 2 | 1 | A-201675-14 | Load Control Bracket Assembly |  | MBARI | A & D Precision Inc. |  |  | 87.25 | 87.25 | y | PO-1710811 | 2017-06-19 | 2017-08-04 |  |  | Parker
A-201904-17_LoadContAssem_V2 | 4 | 1 | P-201772-15 | Load Control Backplane Isolator Brd |  | MBARI | A & D Precision Inc. | G-10 Fiberglass Laminate Sheet |  | 295 | 295 | y | PO-1710811 | 2017-06-19 | 2017-08-04 |  |  | Parker
A-201904-17_LoadContAssem_V2 | 6 | 1 | P-201679-14 | LOAD CONT. CARD GUIDE - PORT_V2 |  |  | MBARI | H6K PP like |  | 106 | 106 | [6 empty] | Parker
A-201904-17_LoadContAssem_V2 | 8 | 8 | 90585A229 | #8-32 UNC-2A x 5/8 Flt Soc Hd Screw |  |  | McMaster-Carr | AISI 316 | Olander Hardware Kit - $7.00/KIT |  | 0
A-201904-17_LoadContAssem_V2 | 9 | 1 | P-201679-14 | Card Guide_Port_V2_MIRROR |  |  |  | H6K PP like |  | 106 | 106 | [6 empty] | Parker
A-201904-17_LoadContAssem_V2 | 7 | 1 | #8-32xp25 | #8 Thrd StandOff | [6 empty] | 0
A-201908-17_Port_EZSV_Assem_Rev.A. | 5 | 8 | 93135A112 | #4-40 x 5/8 UNC-2A Slot Pan Hd Screw |  |  | McMaster-Carr | Nylon 6/10 | Olander Hardware Kit - $9.65/KIT |  | 0
A-201908-17_Port_EZSV_Assem_Rev.A. | 4 | 8 | 94812A200 | #4-40 UNC-2B Hex Nut |  |  | McMaster-Carr | Nylon 6/10 | Olander Hardware Kit - $9.65/KIT |  | 0
A-201908-17_Port_EZSV_Assem_Rev.A. | 3 | 16 | 94639A610 | #4 3/16 x 1/8 StandOff |  |  | McMaster-Carr | Nylon 6/6 |  | 0.07 | 1.12 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201908-17_Port_EZSV_Assem_Rev.A. | 1 | 1 | P-200697 | EZ-servo_DoubleBracket | A |  | MBARI | 6061-T6 Aluminum |  | 22.5 | 22.5 | y | [5 empty] | Parker
A-201908-17_STBD_EZSV_Assem. | 5 | 8 | 93135A108 | #4-40 x 3/8 UNC-2A Slot Pan Hd Screw |  |  | McMaster-Carr | Nylon 6/10 | Olander Hardware Kit - $9.65/KIT |  | 0
A-201908-17_STBD_EZSV_Assem. | 4 | 8 | 94812A200 | #4-40 UNC-2B Hex Nut |  |  | McMaster-Carr | Nylon 6/10 | Olander Hardware Kit - $9.65/KIT |  | 0
A-201908-17_STBD_EZSV_Assem. | 3 | 8 | 94639A610 | #4 3/16 x 1/8 StandOff |  |  | McMaster-Carr | Nylon 6/6 |  | 0.07 | 0.56 |  | cc | 2017-10-10 |  |  |  | Chaffey
A-201908-17_STBD_EZSV_Assem. | 1 | 1 | P-200697 | EZ-servo_DoubleBracket | A |  | MBARI | 6061-T6 Aluminum |  | 22.5 | 22.5 | y | [5 empty] | Parker
Antenna and base |  | 1 | 17016 | GLOSS ORANGE SPRAY PAINT |  |  | ACE HDWR | [10 empty] | Hobson
76766.6638
Note on D42: chma: Substituted McMaster Carr PN 92273A071
Note on D73: chma: Increased length from 1/4" to 5/16".
Note on D167: chma: Revised to #14 (0.033 dia.) as per as-built.
Note on E301: chma: Substituted a 1.5 Inch screw. chma:
Note on M396: chma: WHOI also ordered and we received these parts so it should come off the list and we will have one extra.