2017_09_28 LRAUV Build Meeting Notes

Present: Brett, Jon, Mike P., Mark C.

Agenda + Notes:

Action items before next meeting:

- Mike P. getting bell cranks re-quoted and ordering.

- Mark C. to get build schedule into MS project.

- Mark C. following up on battery PCB status.

- Brett following up with WHOI on BOM and their parts status.

Action items from last meeting:

- Brett was going to existing VB inventory before additional parts for 2 more assemblies were ordered. Done – Brett checked inventory and enough parts (pumps, motors & brackets OK) to complete two VB systems was located.

- Mike P. following up on drop weight sub-assembly and identifying all sub-assembly parts that can be made in house. Done – parts that make more sense to build internally will be done in-house. NOTE FROM MEETING, String pot adjustment part is printed in crystal not ABS!

- Mark to confirm minimum sensors needed for vehicle final integration and sea trials. (AHRS).

Only AHRS is need for sea trials, all other sensors can be integrated later.

- Mike P. to meet with Ray and decide which remaining parts to build in-house. Same as 2 above.

Other items:

- What are the remaining long lead time items that are not on order?

  - Mechanical items.

    - Unit 3 & 4 VB system parts. See 1 above

    - Nose cones. Pending formal definition of sensor payloads for each vehicle. Mark will build lead-time into schedule for final completion.

    - ?? – No other items were identified.

  - Electrical - specifically what pcb's are not yet ready for fabrication? This list is from Jose. Mark will follow-up and incorporate these items into the schedule.

    - High Voltage Converter Board.

    - Load Control Backplane.

    - Analog Load Control Board.

    - Boards that need to go back for rework:

      - RF Multiplexer board.

      - There is currently a 7week lead on the filter chip part.

      - Antennae (20 out of 25 boards).  Needs the same chip as the MUX board.

- What items are being held back by pending design changes?

  - E.G. antenna mount base. Pending of re-design for new beacon shape.

  - Nose cones. See above.

  - What else? Design for rudder/elevator bell crank modified for more readily available thinner material. Mike getting re-quoted.

  - No other items identified.

- Early look at the build schedule. Still pending. Mark will add fabrication of 3 more assembly frames, 4 “rolley” carts and 4 launch carts to build schedule and Que. WHOI parts will be handled by Brett.

- Battery assembly should start as soon as parts are here to allow for maintaining a minimum charge on the battery modules before vehicle completion and regular use. Mark will follow up with Jose to check on battery PCB status.

- Apparently WHOI is working from a BOM in bit bucket. Not sure if it is the current version. Brett will follow up.