2017_11_09 LRAUV Build Agenda

1. What are the remaining long lead time items that are not on order? 

a. Mechanical items.
i. Nose cones. Pending formal definition of sensor payloads for each vehicle. Brett has been working on the configuration and thinks that he is close to a final nose cone configuration for each of the three vehicles.
ii. Antenna molding. Pending ECO extending length of antenna. Jose checking cables and Brett will set new length based on available cable length. Also pending receipt of remaining filter chip parts although some units can be molded from existing stock.
iii. Antenna mount base. Pending of re-design for new beacon shape. Estimated time of about a month to test new beacon and re-design base.

b. Electrical – status of PCB's needed for LRAUV build:
i. High Voltage Converter Board. Ed working on completing the design.
ii. Load Control Backplane. In layout with Jose.
iii. Analog Load Control Board. In layout with Jose.
iv. Load Control boards. Arriving this week and Ken Heller checking out.
v. Boards that need to go back for rework:
1. RF Multiplexer board. Pending filter chip delivery.
2. Antenna (20 out of 25 boards).  Pending filter chip delivery.

2. Battery build up status (Denis, Jose).
a. What about WHOI mechanical parts? Mechanical parts are not complete. Will inventory when Amy on site (see below).
b. All mechanical parts and PCB’s are in and the boards are being checked out by Denis and Ken Heller.
c. Jose will fabricate upgraded minor harness (not sure details of which one).
d. Jose checking on delivery of main harness components from outside vendor MC Electronics.

3. WHOI BUSINESS: Amy visiting from WHOI November 13th for one week to work on their inventory and build.
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