LRAUV Build Meeting Notes - January 10, 2018

Brett, Jose, Jim S., Mike P., Mark C. (notes)

Major Action items:

Jose Rosal – Get firm delivery date from vendor on delivery for end bell wiring, main wiring harness first article, thruster motor wiring, etc. Send out Analog Load Control board for stuffing. Assemble Load Control Backplane.

Jim Scholfield – Check valve part inventory with Mark.

Mike Parker – Machine outstanding parts. Identify painting vendor.

Brett Hobson – Pass painting spec. to Mike. Antenna test mold.

Mark Chaffey – Battery safety guide for building G. Follow up on WHOI battery controller board status.

- Overall schedule picture as illustrated in project – what’s critical path. Antenna fab. right now.

- WHOI battery PCB’s status. Mark will follow up.

- What can Amy and Shawn do if they come out in 2 weeks? TBD, probably should delay until all of their parts have arrived – especially the end bells.

- Current task list:

| Task Name | Finish Date | Slack | Percent Complete | Resource Names |
| --- | --- | --- | --- | --- |
| A-200467-17_PressHull_BUILD_5 | 3/23/2018 | 93d | 37% |  |
| FWD dome wiring Waiting for delivery from vendor, Jose following up. | 1/15/2018 | 54.5d | 0% | Jose Rosal |
| Assemble A-200579-14_InternalChassis_V3 | 1/25/2018 | 54.5d | 25% | Jim Scholfield |
| AFT dome wiring Waiting for delivery from vendor, Jose following up. | 1/15/2018 | 62d | 0% | Jose Rosal |
| A-201330-12_VB-Sys_V2 | 1/18/2018 | 59d | 65% |  |
| A-200620-08_VB-Resrvoir # built up complete, one article missing the valve and valve PCB. All need to have motor adapter PCB added to motors, Jim to take to Jose. | 1/10/2018 | 65.75d | 50% | Jim Scholfield |
| P-201775-16 Valve Panel Mount Bracket fabrication Need to check inventory. ESP took some and was going to replace. | 1/18/2018 | 59d | 70% |  |
| A-200991-11_ValveAssem final assembly One valve assembly incomplete. Jim & Mark following up. | 1/18/2018 | 59d | 50% | Jim Scholfield |
| A-201541-13_SecBattAssem_V3.3 | 2/6/2018 | 46d | 43% |  |
| Test half-pak battery modules In progress. One set of batteries complete. | 1/15/2018 | 46d | 75% | Denis Klimov,Ken Heller |
| Degauss half-pak battery modules In progress. | 1/23/2018 | 46d | 0% |  |
| A-201882-17_RF chassis_V2 | 1/11/2018 | 64d | 88% |  |
| Test 3 way mux assembly Final box assembly pending receive outstanding mechanical hardware. Then do to Craig for testing. Brent suggested Mark take charge of RF assembly, accepted. | 1/11/2018 | 64d | 0% | Craig Okuda |
| A-201904-17_LoadContAssem_V2 | 2/23/2018 | 33d | 33% |  |
| Receive all mechanical parts | 1/9/2018 | 66.5d | 95% | Mike Parker |
| Load control backplane complete Boards are in-house, need assembly and testing. | 1/15/2018 | 35d | 75% | Jose Rosal |
| Analog load control board complete Need to be sent out for assembly. Small change to BOM in progress. | 2/14/2018 | 40.75d | 25% | Jose Rosal |
| Complete high voltage converter PCB assembly Design nearly complete, finalizing part database. | 2/23/2018 | 33d | 0% | Ed Mellinger |
| A-201908-17_Stbd & Port_EZSV_Assem_Rev.A Checking with Mike P. on plate fabrication. Also Jose to check if servos are received. | 1/10/2018 | 65d | 0% | Jim Scholfield |
| A-200567-08_PropShaftAssem Mike has parts and will start fabrication. | 1/19/2018 | 78d | 0% | Mike Parker |
| A-200503-08_ThrusterMotorAssy_V3 Pending receipt of motors back from wiring vendor. | 1/19/2018 | 58d | 0% | Jim Scholfield |
| Assemble internal chassis components for harness fit Pending receipt of 1st article from wiring vendor. | 1/22/2018 | 35d | 0% | Jim Scholfield |
| Paint aluminum pressure hulls Vendor not identified. Mike P. will look for vendor. Brett to supply Mike with hull paint specification. | 2/15/2018 | 119d | 0% | Water Rat Mike P. |
| A-200502-08_TailControlAssem_V7 | 5/9/2018 | 0d | 28% |  |
| A-200618-08_Fin_Assem_V6, receive fin axles Mike to fabricate. | 1/18/2018 | 79.75d | 75% | Mike Parker |
| A-200618-08_Fin_Assem_V6, receive final molded fins Done | 2/1/2018 | 69d | 0% | Mike Parker |
| A-200711-09_CS_LDA_Acuator wiring and assembly 2 units complete, balance In progress. | 1/29/2018 | 72d | 50% | Jose Rosal,Jim Scholfield |
| A-200731-09_ElvCrnk/A-200732-09_RuddrCrnk fabrication Parts out to fabricate with El Camino machine. Mike P. plans on welding WHOI parts in-house. | 1/22/2018 | 77d | 0% | Machine Shop |
| Bond A-200751-09_HATCH_TailShellAssem, fabricate hatch Part of tail shell below. | 1/9/2018 | 86d | 0% | Water Rat Brett |
| A-200751-09_TailShellAssem, fabricate shell Brett has identified new vendor who is building up 1st article for inspection. If OK will fabricate remaining shells in about a week. | 3/30/2018 | 28d | 0% | Water Rat Brett |
| A-200924-10_ExtBladderAssem Bladders received. Mike P. machining qty. 10, 10-MBARI, 2-WHOI. | 1/22/2018 | 77d | 0% | Jim Scholfield |
| Receive A-201916-17_TailFoamAssy_V6 Shipped last week from vendor. | 1/29/2018 | 0d | 50% |  |
| A-201798-16_Antenna Rev.I | 5/9/2018 | 0d | 31% |  |
| Solder in coax to Antenna PCB In tech build que. | 1/10/2018 | 57d | 0% | Jose Rosal |
| Complete test molding First article received. Material not stiff enough. 2nd test molding will be done to improve stiffness. | 1/10/2018 | 57d | 95% | Brett Hobson |
| Mold antennas Pending above. | 2/7/2018 | 57d | 0% | Brett Hobson |
| Over mold antenna coax with Poly U Coax cable at Falmat in build que. | 2/9/2018 | 0d | 20% | Mark Chaffey |
| A-xxxxxx-xx_PayLoad-ShortNose (Kemp) | 8/15/2018 | 0d | 0% |  |
| Specify shortnose payload design Brett’s been doing much work on this. Plans on reviewing all nose configurations in several weeks. Kemp short nose configuration would be part of this review. | 1/11/2018 | 49.5d | 0% | Brett Hobson |
| Fabricate AHRS housing In progress. | 2/8/2018 | 59.5d | 0% | Machine Shop |
| Fabricate or locate all shortnose parts Pending review and BOM. | 2/22/2018 | 49.5d | 0% | Brett Hobson,Jon Erickson |
| AUV 5,6,7 science payload Systems | 5/23/2018 | 60d | 2% |  |
| Specify AUV 5,6,7 science payload design See shortnose design above. | 1/12/2018 | 63.25d | 50% | Brett Hobson |
| Complete design drawings for science payload | 2/9/2018 | 63.25d | 0% | Brett Hobson,Jon Erickson |