LRAUV Build Meeting Notes- February 22, 2018

Present: 	Jim S., Mike P., Paul C., Jose, Ken Heller, Denis, Mark C. (notes).

Major Action items:

Jose Rosal – Deliver end bells to building G. Continue fit and mods to main wiring harnesses. Need to check for full battery pak wiring harnesses.

Mike Parker – Machine prop shaft and fin mounts + weld.

Brett Hobson – Design configuration for Mathieu and WHOI LRAUV nose cones.

Mark Chaffey – Present battery safety guide to residents of building G. Print guide and post on wall.

- Current task list:

| Task Name | Finish Date | Slack | Percent Complete | Resource Names |
| --- | --- | --- | --- | --- |
| A-200467-17_PressHull_BUILD_5 | 3/23/2018 | 93d | 37% |  |
| FWD dome wiring Received. | 1/15/2018 | 54.5d | 100% | Jose Rosal |
| Assemble A-200579-14_InternalChassis_V3 | 1/25/2018 | 54.5d | 25% | Jim Scholfield |
| AFT dome wiring Received. | 1/15/2018 | 62d | 100% | Jose Rosal |
| A-201330-12_VB-Sys_V2 | 1/18/2018 | 59d | 100% |  |
| A-200620-08_VB-Resrvoir All built up complete, currently in leak test. All motor adapter PCB added to motors. Done. | 1/10/2018 | 65.75d | 100% | Jim Scholfield |
| P-201775-16 Valve Panel Mount Bracket fabrication Done. BTW this is the wrong PN. | 1/18/2018 | 59d | 100% |  |
| A-200991-11_ValveAssem final assembly All six valves assembled (4 MBARI + 2 WHOI) and five have been checked out. | 1/18/2018 | 59d | 100% | Jim Scholfield |
| A-201541-13_SecBattAssem_V3.3 | 2/6/2018 | 46d | 43% |  |
| Test half-pak battery modules In progress. One full battery assembly complete. Three more half paks passed testing. Three half paks need debugging and two paks waiting for test. Ken Heller last day is next Thursday. We are short rollers and shoulder screws. Mark will order. Half pak and full pak wiring harnesses are thought to be complete – Jose checking. | 1/15/2018 | 46d | 75% | Denis Klimov,Ken Heller |
| Degauss half-pak battery modules In progress. | 1/23/2018 | 46d | 0% |  |
| A-201882-17_RF chassis_V2 | 1/11/2018 | 64d | 88% |  |
| Test 3 way mux assembly Final box assembly done. Craig testing done. | 1/11/2018 | 64d | 100% | Craig Okuda |
| A-201904-17_LoadContAssem_V2 | 2/23/2018 | 33d | 33% |  |
| Receive all mechanical parts | 1/9/2018 | 66.5d | 95% | Mike Parker |
| Load control backplane complete Boards are in assembly (outside vendor). | 1/15/2018 | 35d | 75% | Jose Rosal |
| Analog load control board complete Boards are in assembly (outside vendor). | 2/14/2018 | 40.75d | 75% | Jose Rosal |
| Complete high voltage converter PCB assembly Design complete, in layout. | 2/23/2018 | 33d | 65% | Ed Mellinger |
| A-201908-17_Stbd & Port_EZSV_Assem_Rev.A Plate fabrication done. Servos are received. | 1/10/2018 | 65d | 100% | Jim Scholfield |
| A-200567-08_PropShaftAssem Mike has parts and fabrication pending. | 1/19/2018 | 78d | 50% | Mike Parker |
| A-200503-08_ThrusterMotorAssy_V3 All assembly and wiring done for five units. Paul is going to chase threads. | 1/19/2018 | 58d | 100% | Jim Scholfield |
| Assemble internal chassis components for harness fit Harness fit nearly complete. Some in-house modifications still pending as components are added. | 1/22/2018 | 35d | 85% | Jim Scholfield |
| Paint aluminum pressure hulls Done. | 2/15/2018 | 119d | 100% | Water Rat Mike P. |
| A-200502-08_TailControlAssem_V7 | 5/9/2018 | 0d | 28% |  |
| A-200618-08_Fin_Assem_V6, receive fin axles Mike fabrication pending. | 1/18/2018 | 79.75d | 75% | Mike Parker |
| A-200618-08_Fin_Assem_V6, receive final molded fins Done. | 2/1/2018 | 69d | 100% | Mike Parker |
| A-200711-09_CS_LDA_Acuator wiring and assembly Nine units complete and ready for Ben to test. Two units in assembly. | 1/29/2018 | 72d | 80% | Jose Rosal,Jim Scholfield |
| A-200731-09_ElvCrnk/A-200732-09_RuddrCrnk fabrication Parts done. Mike P. welding WHOI parts pending. | 1/22/2018 | 77d | 70% | Machine Shop |
| A-200751-09_TailShellAssem, fabricate shell New vendor (Pleskunas Design LLC) has completed first article and it passed inspection. We have ordered two more and WHOI is ordering two (one for us). Delivery will be about a month. | 3/30/2018 | 28d | 25% | Water Rat Pleskunas Design LLC |
| A-200924-10_ExtBladderAssem Bladders received. Mike P. machining qty. 10, 10-MBARI, 2-WHOI, of the custom plug insert. Done | 1/22/2018 | 77d | 100% | Jim Scholfield |
| Receive A-201916-17_TailFoamAssy_V6 All Received. | 1/29/2018 | 0d | 100% |  |
| A-201798-16_Antenna Rev.I | 5/9/2018 | 0d | 31% |  |
| Solder in coax to Antenna PCB Done. | 1/10/2018 | 57d | 100% | Jose Rosal |
| Complete test molding First article received. Material not stiff enough. 2nd test molding will be done to improve stiffness. | 1/10/2018 | 57d | 100% | Brett Hobson |
| Mold antennas Pending above. | 2/7/2018 | 57d | 100% | Brett Hobson |
| Over mold antenna coax with Poly U Done. In transit to SMA connector installer. | 2/9/2018 | 0d | 100% | Mark Chaffey |
| A-xxxxxx-xx_PayLoad-ShortNose (Kemp) | 8/15/2018 | 0d | 0% |  |
| Specify shortnose payload design Brett’s been doing much work on this. Plans on reviewing all nose configurations in several weeks. Kemp short nose configuration would be part of this review. | 1/11/2018 | 49.5d | 0% | Brett Hobson |
| Fabricate AHRS housing No update. | 2/8/2018 | 59.5d | 0% | Machine Shop |
| Fabricate or locate all shortnose parts Pending review and BOM. | 2/22/2018 | 49.5d | 0% | Brett Hobson,Jon Erickson |
| AUV 5,6,7 science payload Systems | 5/23/2018 | 60d | 2% |  |
| Specify AUV 5,6,7 science payload design See shortnose design above. | 1/12/2018 | 63.25d | 50% | Brett Hobson |
| Complete design drawings for science payload | 2/9/2018 | 63.25d | 0% | Brett Hobson,Jon Erickson |

Other items:

- Jim has all five mass shifters assembled and ready.