LRAUV Build Meeting Agenda - January 10, 2018

- Overall schedule picture as illustrated in project – what’s critical path.

- WHOI battery PCB’s status.

- What can Amy and Shawn do if they come out in 2 weeks?

- Current task list:

| Task Name | Start Date | Finish Date | Slack | Percent Complete | Resource Names |
| --- | --- | --- | --- | --- | --- |
| A-200467-17_PressHull_BUILD_5 | 9/27/2017 | 3/23/2018 | 93d | 37% |  |
| FWD dome wiring | 10/11/2017 | 1/15/2018 | 54.5d | 0% | Jose Rosal |
| Assemble A-200579-14_InternalChassis_V3 | 11/15/2017 | 1/25/2018 | 54.5d | 25% | Jim Scholfield |
| AFT dome wiring | 10/11/2017 | 1/15/2018 | 62d | 0% | Jose Rosal |
| A-201330-12_VB-Sys_V2 | 9/27/2017 | 1/18/2018 | 59d | 65% |  |
| A-200620-08_VB-Resrvoir | 9/27/2017 | 1/10/2018 | 65.75d | 50% | Jim Scholfield |
| P-201775-16 Valve Panel Mount Bracket fabrication | 10/31/2017 | 1/18/2018 | 59d | 70% |  |
| A-200991-11_ValveAssem final assembly | 9/27/2017 | 1/18/2018 | 59d | 50% | Jim Scholfield |
| A-201541-13_SecBattAssem_V3.3 | 9/27/2017 | 2/6/2018 | 46d | 43% |  |
| Test half-pak battery modules | 11/17/2017 | 1/15/2018 | 46d | 75% | Denis Klimov,Ken Heller |
| Degauss half-pak battery modules | 1/16/2018 | 1/23/2018 | 46d | 0% |  |
| A-201882-17_RF chassis_V2 | 11/10/2017 | 1/11/2018 | 64d | 88% |  |
| Test 3 way mux assembly | 1/5/2018 | 1/11/2018 | 64d | 0% | Craig Okuda |
| A-201904-17_LoadContAssem_V2 | 9/27/2017 | 2/23/2018 | 33d | 33% |  |
| Receive all mechanical parts | 9/27/2017 | 1/9/2018 | 66.5d | 95% | Mike Parker |
| Load control backplane complete | 11/10/2017 | 1/15/2018 | 35d | 75% | Jose Rosal |
| Analog load control board complete | 11/10/2017 | 2/14/2018 | 40.75d | 25% | Jose Rosal |
| Complete high voltage converter PCB assembly | 1/1/2018 | 2/23/2018 | 33d | 0% | Ed Mellinger |
| A-201908-17_Stbd & Port_EZSV_Assem_Rev.A | 11/3/2017 | 1/10/2018 | 65d | 0% | Jim Scholfield |
| A-200567-08_PropShaftAssem | 1/8/2018 | 1/19/2018 | 78d | 0% | Mike Parker |
| A-200503-08_ThrusterMotorAssy_V3 | 1/8/2018 | 1/19/2018 | 58d | 0% | Jim Scholfield |
| Assemble internal chassis components for harness fit | 1/16/2018 | 1/22/2018 | 35d | 0% | Jim Scholfield |
| Paint aluminum pressure hulls | 1/5/2018 | 2/15/2018 | 119d | 0% | Water Rat |
| A-200502-08_TailControlAssem_V7 | 9/27/2017 | 5/9/2018 | 0d | 28% |  |
| A-200618-08_Fin_Assem_V6, receive fin axles | 9/27/2017 | 1/18/2018 | 79.75d | 75% | Mike Parker |
| A-200618-08_Fin_Assem_V6, receive final molded fins | 1/5/2018 | 2/1/2018 | 69d | 0% | Mike Parker |
| A-200711-09_CS_LDA_Acuator wiring and assembly | 11/10/2017 | 1/29/2018 | 72d | 50% | Jose Rosal,Jim Scholfield |
| A-200731-09_ElvCrnk/A-200732-09_RuddrCrnk fabrication | 1/9/2018 | 1/22/2018 | 77d | 0% | Machine Shop |
| Bond A-200751-09_HATCH_TailShellAssem, fabricate hatch | 1/9/2018 | 1/9/2018 | 86d | 0% | Water Rat |
| A-200751-09_TailShellAssem, fabricate shell | 1/8/2018 | 3/30/2018 | 28d | 0% | Water Rat |
| A-200924-10_ExtBladderAssem | 1/9/2018 | 1/22/2018 | 77d | 0% | Jim Scholfield |
| Receive A-201916-17_TailFoamAssy_V6 | 10/20/2017 | 1/29/2018 | 0d | 50% |  |
| A-201798-16_Antenna Rev.I | 9/27/2017 | 5/9/2018 | 0d | 31% |  |
| Solder in coax to Antenna PCB | 1/8/2018 | 1/10/2018 | 57d | 0% | Jose Rosal |
| Complete test molding | 12/19/2017 | 1/10/2018 | 57d | 95% | Brett Hobson |
| Mold antennas | 1/11/2018 | 2/7/2018 | 57d | 0% | Brett Hobson |
| Over mold antenna coax with Poly U | 1/1/2018 | 2/9/2018 | 0d | 20% | Mark Chaffey |
| A-xxxxxx-xx_PayLoad-ShortNose (Kemp) | 9/27/2017 | 8/15/2018 | 0d | 0% |  |
| Specify shortnose payload design | 9/27/2017 | 1/11/2018 | 49.5d | 0% | Brett Hobson |
| Fabricate AHRS housing | 1/11/2018 | 2/8/2018 | 59.5d | 0% | Machine Shop |
| Fabricate or locate all shortnose parts | 1/11/2018 | 2/22/2018 | 49.5d | 0% | Brett Hobson,Jon Erickson |
| AUV 5,6,7 science payload Systems | 9/27/2017 | 5/23/2018 | 60d | 2% |  |
| Specify AUV 5,6,7 science payload design | 9/27/2017 | 1/12/2018 | 63.25d | 50% | Brett Hobson |
| Complete design drawings for science payload | 1/12/2018 | 2/9/2018 | 63.25d | 0% | Brett Hobson,Jon Erickson |