## Year 1
MBARI - WBS
PROJECT TITLE |  | Sample |  |  |  |  | PRINCIPAL INVESTIGATOR | [7 empty] | Andrea Fassbender
PROJECT MANAGER | [6 empty] | DATE - VERSION | [7 empty] | 13 April 2017 - Ver. 1
[7 empty] | 1st qtr | [11 empty] | 2nd Qtr | [11 empty] | 3rd Qtr | [11 empty] | 4th Qtr
WBS NUMBER | TASK TITLE | TASK RESOURCES | TECHNICIAN RESOURCES | MACHINE SHOP | DURATION | PCT OF TASK COMPLETE | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Project Requirements |  |  |  | WKS
1.1 | Assemble requirements and verify |  |  |  |  | 0% | bar: Jan 1 to Jan 2
1.1.1 | Decision on Equilibration vs Extraction | ME, EE, SE, SciTech |  |  | 2 | 0% | bar: Jan 1 to Jan 3
1.2 | Design new system architecture block diagram | ME, EE, SE, SciTech |  |  | 4 | 0% | bar: Jan 2 to Jan 4
1.3 | Concept of operations |  |  |  |  | 0% | bar: Jan 3 to Feb 2
1.3.1 | Mooring opertaions | ME, EE, SE, SciTech |  |  |  | 0% | bar: Jan 4 to Feb 2
1.3.2 | Wave glider operations | ME, EE, SE, SciTech |  |  |  | 0% | bar: Jan 4 to Feb 2
1.4 | Build system engineering specifications |  |  |  |  | 0% | bar: Feb 2 to Feb 4
1.4.1 | Detailed Techical Specifications | ME, EE, SE, SciTech |  |  |  | 0% | bar: Feb 3 to Mar 1
2 | Concept Design
2.1 | Systems block diagram - updated | ME, EE, SE, SciTech |  |  |  | 0% | bar: Mar 1 to Mar 2
2.2 | Research Components
2.2.1 | Valves | ME, SciTech |  |  |  | 0% | bar: Mar 2 to Mar 3
2.2.2 | Computer | EE, SE |  |  |  | 0% | bar: Mar 2 to Apr 1
2.2.3 | Commuincations | EE, SE |  |  |  | 0% | bar: Mar 4 to Apr 2
2.2.4 | Wave glider available configurations (w power) | ME, EE |  |  |  | 0% | bar: Mar 2 to Mar 4
2.2.5 | Components still TBD for eval | ME, EE, SE, SciTech |  |  |  | 0% | bar: Mar 2 to Apr 2
2.3 | Revised system documents
2.3.1 | Power budget calcs/spreadsheet | ME, EE, SE |  |  |  | 0% | bar: Apr 1 to Apr 2
2.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0% | bar: Apr 1 to Apr 2
2.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0% | bar: Apr 1 to Apr 3
2.4 | PreliminaryTest Plans
2.4.1 | Bench testing plan (cold/heat) | ME, EE, SE, SciTech |  |  |  | 0% | bar: Apr 4 to May 1
2.4.2 | Tank testing plan (water may not be suitable) | ME, EE, SE, SciTech |  |  |  | 0% | bar: Apr 4 to May 1
2.4.3 | At sea testing (boat & mooring) | ME, EE, SE, SciTech |  |  |  | 0% | bar: Apr 4 to May 1
2.5 | Concept design review
2.5.1 | Science slides | Sci Tech w/ PI |  |  |  | 0% | bar: May 2
2.5.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0% | bar: May 2
2.5.3 | ME detail slides | ME |  |  |  | 0% | bar: May 2
2.5.4 | EE detail slides | EE |  |  |  | 0% | bar: May 2
2.5.5 | SE detail slides | SE |  |  |  | 0% | bar: May 2
3 | Preliminary Design
3.1 | Systems block diagram - updated |  |  |  |  | 0% | bar: May 3 to June 1
3.2 | Research Components
3.2.1 | Valves | ME, SciTech |  |  |  | 0% | bar: May 4 to June 2
3.2.2 | Computer | EE, SE |  |  |  | 0% | bar: June 1 to June 3
3.2.3 | Commuincations | EE, SE |  |  |  | 0% | bar: June 1 to June 3
3.2.4 | Wave glider available configurations (w power) | ME, EE, SE, SciTech |  |  |  | 0% | bar: June 1 to June 4
3.2.5 | Components still TBD for eval | ME, EE, SE, SciTech |  |  |  | 0% | bar: June 3 to Jul 1
3.3 | Revised system documents
3.3.1 | Power budget calcs/spreadsheet | ME, EE, SE, SciTech |  |  |  | 0% | bar: June 4 to Jul 1
3.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0% | bar: June 4 to Jul 1
3.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0% | bar: June 4 to Jul 2
3.4 | Equilibrator / Extractor Design
3.4.1 | Equilibrator / Extractor Tube Design | ME, SciTech |  |  |  | 0% | bar: Jul 2 to Aug 1
3.4.2 | Intake design | ME, SciTech |  |  |  | 0% | bar: Jul 2 to Aug 1
3.4.3 | Air Sampler Design | ME, SciTech |  |  |  | 0% | bar: Jul 4 to Aug 2
3.4.4 | Internal Flow Design | ME, SciTech |  |  |  | 0% | bar: Jul 4 to Aug 2
3.4.4 | Licor 460/480 Purchase (or alternative) | Sci Tech |  |  |  | 0% | bar: June 4
3.5 | Commnications Sub-system Design
3.5.1 | Communications Housing Design | ME |  |  |  | 0% | bar: Aug 2 to Aug 4
3.5.2 | Intrenal Electronics - Wiring Diagram | EE |  |  |  | 0% | bar: Aug 3 to Sep 1
3.5.3 | Internal Electrnoics Rack | ME, EE |  |  |  | 0% | bar: Aug 3 to Sep 1
3.5.4 | Communicaions Elex Purchase w. Antennea | EE, SE |  |  |  | 0% | bar: Aug 3 to Sep 1
3.5.5 | Connectors Purchase | ME, EE |  |  |  | 0% | bar: Sep 1 to Sep 2
3.6 | Main Electronics Design
3.6.1 | Housing | ME |  |  |  | 0% | bar: Sep 1 to Sep 3
3.6.2 | Comonent rack | ME, EE |  |  |  | 0% | bar: Sep 1 to Sep 3
3.6.3 | Computer Selection | EE, SE |  |  |  | 0% | bar: Sep 1 to Sep 3
3.6.4 | Power Supply (possible custom for fit and power) | EE, SE(maybe) |  |  |  | 0% | bar: Aug 4 to Sep 4
3.6.4 | Connectors Purchase | ME, EE |  |  |  | 0% | bar: Sep 1 to Sep 2
3.7 | Power System Design
3.7.1 | Battery Selection | ME, EE, SE |  |  |  | 0% | bar: Aug 1 to Aug 4
3.7.2 | Charging System | ME, EE, SE |  |  |  | 0% | bar: Aug 3 to Sep 3
3.7.3 | Housing | ME |  |  |  | 0% | bar: Sep 1 to Sep 3
3.7.4 | Comonent rack | ME, EE |  |  |  | 0% | bar: Sep 1 to Sep 3
3.7.5 | Computer Selection and purchase | EE, SE |  |  |  | 0% | bar: Sep 1 to Sep 3
3.7.6 | Power Management Board | EE, SE(maybe) |  |  |  | 0% | bar: Aug 4 to Sep 4
3.7.7 | Connectors Purchase | ME, EE |  |  |  | 0% | bar: Sep 1 to Sep 2
3.8 | Callibration System
3.8.1 | Bench Test of Licor stabililty with Temp | Me, Sci Tech |  |  |  | 0% | bar: Nov 1 to Nov 4
3.8.2 | Results into look up table for SE to implement (TBD) | ME, SciTech |  |  |  | 0% | bar: Nov 3 to Dec 1
3.8.3 | Design of Calibration Gas system | ME |  |  |  | 0%
3.8.4 | Purchase gas tank | SciTech |  |  |  | 0%
3.8.5 | Purchase gas components | SciTech |  |  |  | 0%
3.9 | Preliminary Design Review
3.9.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
3.9.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
3.9.3 | ME detail slides | ME |  |  |  | 0%
3.9.4 | EE detail slides | EE |  |  |  | 0%
3.9.5 | SE detail slides | SE |  |  |  | 0%
3.9.6 | Updated Test Plans | ME, EE, SE, SciTech |  |  |  | 0%
3.1 | Purchase long lead items | ME, EE, SE, SciTech |  |  |  | 0%
3.11 | Bench Testing |  |  |  |  | 0%
3.11.1 | Gas Extraction Method | ME, EE, SE, SciTech |  |  |  | 0%
3.11.2 | Test of Purchased Equipment | ME, EE, SE, SciTech |  |  |  | 0%
0%

## Year 2
MBARI - WBS
PROJECT TITLE |  | Sample |  |  |  |  | PRINCIPAL INVESTIGATOR | [7 empty] | Andrea Fassbender
PROJECT MANAGER | [6 empty] | DATE - VERSION | [7 empty] | 13 April 2017 - Ver. 1
[7 empty] | 1st qtr | [11 empty] | 2nd Qtr | [11 empty] | 3rd Qtr | [11 empty] | 4th Qtr
WBS NUMBER | TASK TITLE | TASK RESOURCES | TECHNICIAN RESOURCES | MACHINE SHOP | DURATION | PCT OF TASK COMPLETE | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Project Requirements |  |  |  | WKS
1.1 | Assemble requirements and verify |  |  |  |  | 0%
1.1.1 | Decision on Equilibration vs Extraction | ME, EE, SE, SciTech |  |  | 2 | 0% | bar: Jan 1 to Jan 2
1.2 | Design new system architecture block diagram | ME, EE, SE, SciTech |  |  | 4 | 0% | bar: Jan 2 to Jan 4
1.3 | Concept of operations |  |  |  |  | 0%
1.3.1 | Mooring opertaions | ME, EE, SE, SciTech |  |  |  | 0% | bar: Jan 4 to Feb 2
1.3.2 | Wave glider operations | ME, EE, SE, SciTech |  |  |  | 0% | bar: Jan 4 to Feb 2
1.4 | Build system engineering specifications |  |  |  |  | 0%
1.4.1 | Detailed Techical Specifications | ME, EE, SE, SciTech |  |  |  | 0%
0%
2 | Concept Design
2.1 | Systems block diagram - updated | ME, EE, SE, SciTech |  |  |  | 0%
2.2 | Research Components |  |  |  |  | 0%
2.2.1 | Valves | ME, SciTech |  |  |  | 0%
2.2.2 | Computer | EE, SE |  |  |  | 0%
2.2.3 | Commuincations | EE, SE |  |  |  | 0%
2.2.4 | Wave glider available configurations (w power) | ME, EE |  |  |  | 0%
2.2.5 | Components still TBD for eval | ME, EE, SE, SciTech |  |  |  | 0%
2.3 | Revised system documents |  |  |  |  | 0%
2.3.1 | Power budget calcs/spreadsheet | ME, EE, SE |  |  |  | 0%
2.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
2.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0%
2.4 | PreliminaryTest Plans |  |  |  |  | 0%
2.4.1 | Bench testing | ME, EE, SE, SciTech |  |  |  | 0%
2.4.2 | Tank testing | ME, EE, SE, SciTech |  |  |  | 0%
2.4.3 | At sea testing | ME, EE, SE, SciTech |  |  |  | 0%
2.5 | Concept design review |  |  |  |  | 0%
2.5.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
2.5.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
2.5.3 | ME detail slides | ME |  |  |  | 0%
2.5.4 | EE detail slides | EE |  |  |  | 0%
2.5.5 | SE detail slides | SE |  |  |  | 0%
0%
3 | Preliminary Design
3.1 | Systems block diagram - updated |  |  |  |  | 0%
3.2 | Research Components |  |  |  |  | 0%
3.2.1 | Valves | ME, SciTech |  |  |  | 0%
3.2.2 | Computer | EE, SE |  |  |  | 0%
3.2.3 | Commuincations | EE, SE |  |  |  | 0%
3.2.4 | Wave glider available configurations (w power) | ME, EE, SE, SciTech |  |  |  | 0%
3.2.5 | Components still TBD for eval | ME, EE, SE, SciTech |  |  |  | 0%
3.3 | Revised system documents |  |  |  |  | 0%
3.3.1 | Power budget calcs/spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
3.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
3.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0%
3.4 | Equilibrator / Extractor Design |  |  |  |  | 0%
3.4.1 | Equilibrator / Extractor Tube Design | ME, SciTech |  |  |  | 0%
3.4.2 | Intake design | ME, SciTech |  |  |  | 0%
3.4.3 | Air Sampler Design | ME, SciTech |  |  |  | 0%
3.4.4 | Internal Flow Design | ME, SciTech |  |  |  | 0%
3.4.4 | Licor 460/480 Purchase (or alternative) | Sci Tech |  |  |  | 0%
3.5 | Commnications Sub-system Design |  |  |  |  | 0%
3.5.1 | Communications Housing Design | ME |  |  |  | 0%
3.5.2 | Intrenal Electronics - Wiring Diagram | EE |  |  |  | 0%
3.5.3 | Internal Electrnoics Rack | ME, EE |  |  |  | 0%
3.5.4 | Communicaions Elex Purchase w. Antennea | EE, SE |  |  |  | 0%
3.5.5 | Connectors Purchase | ME, EE |  |  |  | 0%
3.6 | Main Electronics Design |  |  |  |  | 0%
3.6.1 | Housing | ME |  |  |  | 0%
3.6.2 | Comonent rack | ME, EE |  |  |  | 0%
3.6.3 | Computer Selection | EE, SE |  |  |  | 0%
3.6.4 | Power Supply (possible custom for fit and power) | EE, SE(maybe) |  |  |  | 0%
3.6.4 | Connectors Purchase | ME, EE |  |  |  | 0%
3.7 | Power System Design |  |  |  |  | 0%
3.7.1 | Battery Selection | ME, EE, SE |  |  |  | 0%
3.7.2 | Charging System | ME, EE, SE |  |  |  | 0%
3.7.3 | Housing | ME |  |  |  | 0%
3.7.4 | Comonent rack | ME, EE |  |  |  | 0%
3.7.5 | Computer Selection and purchase | EE, SE |  |  |  | 0%
3.7.6 | Power Management Board | EE, SE(maybe) |  |  |  | 0%
3.7.7 | Connectors Purchase | ME, EE |  |  |  | 0%
3.8 | Callibration System |  |  |  |  | 0%
3.8.1 | Bench Test of Licor stabililty with Temp | Me, Sci Tech |  |  |  | 0%
3.8.2 | Results into look up table for SE to implement (TBD) | ME, SciTech |  |  |  | 0%
3.8.3 | Deisng of Calibration Gas system | ME |  |  |  | 0%
3.8.4 | Purchase gas tank | SciTech |  |  |  | 0%
3.8.5 | Purchase gas components | SciTech |  |  |  | 0%
3.9 | Preliminary Design Review |  |  |  |  | 0%
3.9.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
3.9.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
3.9.3 | ME detail slides | ME |  |  |  | 0%
3.9.4 | EE detail slides | EE |  |  |  | 0%
3.9.5 | SE detail slides | SE |  |  |  | 0%
3.9.6 | Updated Test Plans | ME, EE, SE, SciTech |  |  |  | 0%
3.1 | Purchase long lead items | ME, EE, SE, SciTech |  |  |  | 0%
0%
4 | Critical Design Update Drawings and Build
4.1 | Systems block diagram - update per Prelim review |  |  |  |  | 0%
4.2 | Purchase Components |  |  |  |  | 0%
4.2.1 | Valve(s) | ME, SciTech |  |  |  | 0%
4.2.2 | Computer | EE, SE |  |  |  | 0%
4.2.3 | Commuincations | EE, SE |  |  |  | 0%
4.2.4 | Components still TBD for assembly and test | ME, EE, SE, SciTech |  |  |  | 0%
4.2.5 | Materials for build, assembly and test | ME, EE, SE, SciTech |  |  |  | 0%
4.3 | Revise system documents per Prelim review |  |  |  |  | 0%
4.3.1 | Power budget calcs/spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
4.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
4.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0%
4.4 | Equilibrator / Extractor Build |  |  |  |  | 0%
4.4.1 | Equilibrator / Extractor Tube Build | ME, SciTech |  |  |  | 0%
4.4.2 | Intake Build | ME, SciTech |  |  |  | 0%
4.4.3 | Air Sampler Build | ME, SciTech |  |  |  | 0%
4.4.4 | Internal Flow Build | ME, SciTech |  |  |  | 0%
4.5 | Commnications Sub-system Design |  |  |  |  | 0%
4.5.1 | Communications Housing Build | ME |  |  |  | 0%
4.5.2 | Intrenal Electronics - Wiring Diagram Update | EE |  |  |  | 0%
4.5.3 | Internal Electrnoics Rack Build | ME, EE |  |  |  | 0%
4.5.4 | Communicaions Elex w. Antennea Test | EE, SE |  |  |  | 0%
4.5.5 | Wiring Harness Build | ME, EE |  |  |  | 0%
4.6 | Main Electronics Build |  |  |  |  | 0%
4.6.1 | Housing Build | ME |  |  |  | 0%
4.6.2 | Comonent rack Build | ME, EE |  |  |  | 0%
4.6.3 | Computer - Bench test | EE, SE |  |  |  | 0%
4.6.4 | Power Supply - Build or Buy | EE, SE(maybe) |  |  |  | 0%
4.6.4 | Wiring Harness Build | ME, EE |  |  |  | 0%
4.7 | Power System Build |  |  |  |  | 0%
4.7.1 | Battery Purchase (may be done if long lead) | ME, EE, SE |  |  |  | 0%
4.7.2 | Charging System - Build or Buy | ME, EE, SE |  |  |  | 0%
4.7.3 | Housing Build | ME |  |  |  | 0%
4.7.4 | Comonent rack build | ME, EE |  |  |  | 0%
4.7.5 | Computer - Bench test | EE, SE |  |  |  | 0%
4.7.6 | Power Management Board | EE, SE(maybe) |  |  |  | 0%
4.7.7 | Wiring Harness Build | ME, EE |  |  |  | 0%
4.8 | Callibration System |  |  |  |  | 0%
4.8.1 | Bench Test sub-system and environmental tests | Me, Sci Tech |  |  |  | 0%
4.8.2 | ResultsSe code and test (TBD) | ME, SciTech |  |  |  | 0%
4.8.3 | Assemble Gas system components | ME |  |  |  | 0%
4.8.4 | Bench Test of Calibration Gas system | SciTech |  |  |  | 0%
4.9 | Critical Design Review |  |  |  |  | 0%
4.9.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
4.9.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
4.9.3 | ME detail slides | ME |  |  |  | 0%
4.9.4 | EE detail slides | EE |  |  |  | 0%
4.9.5 | SE detail slides | SE |  |  |  | 0%
4.9.6 | Updated Test Plans | ME, EE, SE, SciTech |  |  |  | 0%
0%
5 | System Integration and Test
5.1 | Full System Integration | ME, EE, SE, SciTech |  |  |  | 0%
5.2 | Dry Lab Testing - verify operation and software | ME, EE, SE, SciTech |  |  |  | 0%
5.3 | Wet Testing - likely test in tank | ME, EE, SE, SciTech |  |  |  | 0%
5.4 | Small Boat Test - overboard in sea water | ME, EE, SE, SciTech |  |  |  | 0%
5.5 | System Integration to test Mooring |  |  |  |  | 0%
5.5.1 | Reconfigure for Mooring Space (TBD) | ME, EE, SE, SciTech |  |  |  | 0%
5.5.2 | Dry Test | ME, EE, SE, SciTech |  |  |  | 0%
5.5.3 | Wet Test - test tank or dock | ME, EE, SE, SciTech |  |  |  | 0%
5.5.4 | Load for deployment | ME, EE, SE, SciTech |  |  |  | 0%
5.5.5 | At sea deployment - duration ~ 6 mos. | ME, EE, SE, SciTech |  |  |  | 0%
0%
6 | Test Results Reporting
6.1. | System Technical Publication | ME, EE, SE, SciTech |  |  |  | 0%
6.2 | System Science Publication | ME, EE, SE, SciTech |  |  |  | 0%
0%
7 | Future Proposal - Wave Glider Deployment
7.1 | Proposal Abstract | ME, EE, SE, SciTech |  |  |  | 0%
7.2 | Full Proposal | ME, EE, SE, SciTech |  |  |  | 0%
0%

## Year 3
MBARI - WBS
PROJECT TITLE |  | Sample |  |  |  |  | PRINCIPAL INVESTIGATOR | [7 empty] | Andrea Fassbender
PROJECT MANAGER | [6 empty] | DATE - VERSION | [7 empty] | 13 April 2017 - Ver. 1
[7 empty] | 1st qtr | [11 empty] | 2nd Qtr | [11 empty] | 3rd Qtr | [11 empty] | 4th Qtr
WBS NUMBER | TASK TITLE | TASK RESOURCES | TECHNICIAN RESOURCES | MACHINE SHOP | DURATION | PCT OF TASK COMPLETE | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Project Requirements |  |  |  | WKS
1.1 | Assemble requirements and verify |  |  |  |  | 0%
1.1.1 | Decision on Equilibration vs Extraction | ME, EE, SE, SciTech |  |  | 2 | 0% | bar: Jan 1 to Jan 2
1.2 | Design new system architecture block diagram | ME, EE, SE, SciTech |  |  | 4 | 0% | bar: Jan 2 to Jan 4
1.3 | Concept of operations |  |  |  |  | 0%
1.3.1 | Mooring opertaions | ME, EE, SE, SciTech |  |  |  | 0% | bar: Jan 4 to Feb 2
1.3.2 | Wave glider operations | ME, EE, SE, SciTech |  |  |  | 0% | bar: Jan 4 to Feb 2
1.4 | Build system engineering specifications |  |  |  |  | 0%
1.4.1 | Detailed Techical Specifications | ME, EE, SE, SciTech |  |  |  | 0%
0%
2 | Concept Design
2.1 | Systems block diagram - updated | ME, EE, SE, SciTech |  |  |  | 0%
2.2 | Research Components |  |  |  |  | 0%
2.2.1 | Valves | ME, SciTech |  |  |  | 0%
2.2.2 | Computer | EE, SE |  |  |  | 0%
2.2.3 | Commuincations | EE, SE |  |  |  | 0%
2.2.4 | Wave glider available configurations (w power) | ME, EE |  |  |  | 0%
2.2.5 | Components still TBD for eval | ME, EE, SE, SciTech |  |  |  | 0%
2.3 | Revised system documents |  |  |  |  | 0%
2.3.1 | Power budget calcs/spreadsheet | ME, EE, SE |  |  |  | 0%
2.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
2.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0%
2.4 | PreliminaryTest Plans |  |  |  |  | 0%
2.4.1 | Bench testing | ME, EE, SE, SciTech |  |  |  | 0%
2.4.2 | Tank testing | ME, EE, SE, SciTech |  |  |  | 0%
2.4.3 | At sea testing | ME, EE, SE, SciTech |  |  |  | 0%
2.5 | Concept design review |  |  |  |  | 0%
2.5.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
2.5.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
2.5.3 | ME detail slides | ME |  |  |  | 0%
2.5.4 | EE detail slides | EE |  |  |  | 0%
2.5.5 | SE detail slides | SE |  |  |  | 0%
0%
3 | Preliminary Design
3.1 | Systems block diagram - updated |  |  |  |  | 0%
3.2 | Research Components |  |  |  |  | 0%
3.2.1 | Valves | ME, SciTech |  |  |  | 0%
3.2.2 | Computer | EE, SE |  |  |  | 0%
3.2.3 | Commuincations | EE, SE |  |  |  | 0%
3.2.4 | Wave glider available configurations (w power) | ME, EE, SE, SciTech |  |  |  | 0%
3.2.5 | Components still TBD for eval | ME, EE, SE, SciTech |  |  |  | 0%
3.3 | Revised system documents |  |  |  |  | 0%
3.3.1 | Power budget calcs/spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
3.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
3.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0%
3.4 | Equilibrator / Extractor Design |  |  |  |  | 0%
3.4.1 | Equilibrator / Extractor Tube Design | ME, SciTech |  |  |  | 0%
3.4.2 | Intake design | ME, SciTech |  |  |  | 0%
3.4.3 | Air Sampler Design | ME, SciTech |  |  |  | 0%
3.4.4 | Internal Flow Design | ME, SciTech |  |  |  | 0%
3.4.4 | Licor 460/480 Purchase (or alternative) | Sci Tech |  |  |  | 0%
3.5 | Commnications Sub-system Design |  |  |  |  | 0%
3.5.1 | Communications Housing Design | ME |  |  |  | 0%
3.5.2 | Intrenal Electronics - Wiring Diagram | EE |  |  |  | 0%
3.5.3 | Internal Electrnoics Rack | ME, EE |  |  |  | 0%
3.5.4 | Communicaions Elex Purchase w. Antennea | EE, SE |  |  |  | 0%
3.5.5 | Connectors Purchase | ME, EE |  |  |  | 0%
3.6 | Main Electronics Design |  |  |  |  | 0%
3.6.1 | Housing | ME |  |  |  | 0%
3.6.2 | Comonent rack | ME, EE |  |  |  | 0%
3.6.3 | Computer Selection | EE, SE |  |  |  | 0%
3.6.4 | Power Supply (possible custom for fit and power) | EE, SE(maybe) |  |  |  | 0%
3.6.4 | Connectors Purchase | ME, EE |  |  |  | 0%
3.7 | Power System Design |  |  |  |  | 0%
3.7.1 | Battery Selection | ME, EE, SE |  |  |  | 0%
3.7.2 | Charging System | ME, EE, SE |  |  |  | 0%
3.7.3 | Housing | ME |  |  |  | 0%
3.7.4 | Comonent rack | ME, EE |  |  |  | 0%
3.7.5 | Computer Selection and purchase | EE, SE |  |  |  | 0%
3.7.6 | Power Management Board | EE, SE(maybe) |  |  |  | 0%
3.7.7 | Connectors Purchase | ME, EE |  |  |  | 0%
3.8 | Callibration System |  |  |  |  | 0%
3.8.1 | Bench Test of Licor stabililty with Temp | Me, Sci Tech |  |  |  | 0%
3.8.2 | Results into look up table for SE to implement (TBD) | ME, SciTech |  |  |  | 0%
3.8.3 | Deisng of Calibration Gas system | ME |  |  |  | 0%
3.8.4 | Purchase gas tank | SciTech |  |  |  | 0%
3.8.5 | Purchase gas components | SciTech |  |  |  | 0%
3.9 | Preliminary Design Review |  |  |  |  | 0%
3.9.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
3.9.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
3.9.3 | ME detail slides | ME |  |  |  | 0%
3.9.4 | EE detail slides | EE |  |  |  | 0%
3.9.5 | SE detail slides | SE |  |  |  | 0%
3.9.6 | Updated Test Plans | ME, EE, SE, SciTech |  |  |  | 0%
3.1 | Purchase long lead items | ME, EE, SE, SciTech |  |  |  | 0%
0%
4 | Critical Design Update Drawings and Build
4.1 | Systems block diagram - update per Prelim review |  |  |  |  | 0%
4.2 | Purchase Components |  |  |  |  | 0%
4.2.1 | Valve(s) | ME, SciTech |  |  |  | 0%
4.2.2 | Computer | EE, SE |  |  |  | 0%
4.2.3 | Commuincations | EE, SE |  |  |  | 0%
4.2.4 | Components still TBD for assembly and test | ME, EE, SE, SciTech |  |  |  | 0%
4.2.5 | Materials for build, assembly and test | ME, EE, SE, SciTech |  |  |  | 0%
4.3 | Revise system documents per Prelim review |  |  |  |  | 0%
4.3.1 | Power budget calcs/spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
4.3.2 | System weight and balance spreadsheet | ME, EE, SE, SciTech |  |  |  | 0%
4.3.3 | Revised System Specifications | ME, EE, SE, SciTech |  |  |  | 0%
4.4 | Equilibrator / Extractor Build |  |  |  |  | 0%
4.4.1 | Equilibrator / Extractor Tube Build | ME, SciTech |  |  |  | 0%
4.4.2 | Intake Build | ME, SciTech |  |  |  | 0%
4.4.3 | Air Sampler Build | ME, SciTech |  |  |  | 0%
4.4.4 | Internal Flow Build | ME, SciTech |  |  |  | 0%
4.5 | Commnications Sub-system Design |  |  |  |  | 0%
4.5.1 | Communications Housing Build | ME |  |  |  | 0%
4.5.2 | Intrenal Electronics - Wiring Diagram Update | EE |  |  |  | 0%
4.5.3 | Internal Electrnoics Rack Build | ME, EE |  |  |  | 0%
4.5.4 | Communicaions Elex w. Antennea Test | EE, SE |  |  |  | 0%
4.5.5 | Wiring Harness Build | ME, EE |  |  |  | 0%
4.6 | Main Electronics Build |  |  |  |  | 0%
4.6.1 | Housing Build | ME |  |  |  | 0%
4.6.2 | Comonent rack Build | ME, EE |  |  |  | 0%
4.6.3 | Computer - Bench test | EE, SE |  |  |  | 0%
4.6.4 | Power Supply - Build or Buy | EE, SE(maybe) |  |  |  | 0%
4.6.4 | Wiring Harness Build | ME, EE |  |  |  | 0%
4.7 | Power System Build |  |  |  |  | 0%
4.7.1 | Battery Purchase (may be done if long lead) | ME, EE, SE |  |  |  | 0%
4.7.2 | Charging System - Build or Buy | ME, EE, SE |  |  |  | 0%
4.7.3 | Housing Build | ME |  |  |  | 0%
4.7.4 | Comonent rack build | ME, EE |  |  |  | 0%
4.7.5 | Computer - Bench test | EE, SE |  |  |  | 0%
4.7.6 | Power Management Board | EE, SE(maybe) |  |  |  | 0%
4.7.7 | Wiring Harness Build | ME, EE |  |  |  | 0%
4.8 | Callibration System |  |  |  |  | 0%
4.8.1 | Bench Test sub-system and environmental tests | Me, Sci Tech |  |  |  | 0%
4.8.2 | ResultsSe code and test (TBD) | ME, SciTech |  |  |  | 0%
4.8.3 | Assemble Gas system components | ME |  |  |  | 0%
4.8.4 | Bench Test of Calibration Gas system | SciTech |  |  |  | 0%
4.9 | Critical Design Review |  |  |  |  | 0%
4.9.1 | Science slides | Sci Tech w/ PI |  |  |  | 0%
4.9.2 | Integrated System design | ME, EE, SE, SciTech |  |  |  | 0%
4.9.3 | ME detail slides | ME |  |  |  | 0%
4.9.4 | EE detail slides | EE |  |  |  | 0%
4.9.5 | SE detail slides | SE |  |  |  | 0%
4.9.6 | Updated Test Plans | ME, EE, SE, SciTech |  |  |  | 0%
0%
5 | System Integration and Test
5.1 | Full System Integration | ME, EE, SE, SciTech |  |  |  | 0%
5.2 | Dry Lab Testing - verify operation and software | ME, EE, SE, SciTech |  |  |  | 0%
5.3 | Wet Testing - likely test in tank | ME, EE, SE, SciTech |  |  |  | 0%
5.4 | Small Boat Test - overboard in sea water | ME, EE, SE, SciTech |  |  |  | 0%
5.5 | System Integration to test Mooring |  |  |  |  | 0%
5.5.1 | Reconfigure for Mooring Space (TBD) | ME, EE, SE, SciTech |  |  |  | 0%
5.5.2 | Dry Test | ME, EE, SE, SciTech |  |  |  | 0%
5.5.3 | Wet Test - test tank or dock | ME, EE, SE, SciTech |  |  |  | 0%
5.5.4 | Load for deployment | ME, EE, SE, SciTech |  |  |  | 0%
5.5.5 | At sea deployment - duration ~ 6 mos. | ME, EE, SE, SciTech |  |  |  | 0%
0%
6 | Test Results Reporting
6.1. | System Technical Publication | ME, EE, SE, SciTech |  |  |  | 0%
6.2 | System Science Publication | ME, EE, SE, SciTech |  |  |  | 0%
0%
7 | Future Proposal - Wave Glider Deployment
7.1 | Proposal Abstract | ME, EE, SE, SciTech |  |  |  | 0%
7.2 | Full Proposal | ME, EE, SE, SciTech |  |  |  | 0%
0%