## Cruise Plan 24hr Ops
CANON 21 Spring cruise on Western Flyer
GMT is LOC+7; 10 nMi=18.348 km |  |  |  | Depart ML | 2021-06-21 16:00
Based on 8 kt steaming |  |  |  | END ML | 2021-06-25 18:10
Event | Start time | Station | End time | Latitude | Longitude | Approx | Remarks | nMi to | Station | Hrs steam | Cumulative
# | (local) | Name | (local) | (deg N) | (deg W) | Depth |  | next stat. | Hrs | to next | Time Used
[6 empty] | (m) |  |  |  | Sta (15kt) | (hours)
Event | Start Time | Station | End time | Latitude | Longitude | Depth | Remarks | nMi_to | Hours | Steam_Time | Cumulative
1 | 2021-06-21 16:00 | ML |  | 36.8 | -121.75 |  | Begin Cruise | 4.806 |  | 0.60075 | 0
2 | 2021-06-21 16:36 | C1 | 2021-06-21 17:36 | 36.796 | -121.85 | 200 | CTD | 9.2517 | 1 | 1.1565 | 0.60075 | Day 1
3 | 2021-06-21 18:45 | M1 | 2021-06-21 19:45 | 36.762 | -122.038 | 1000 | CTD | 16.7795 | 1 | 2.0974 | 2.7572
4 | 2021-06-21 21:51 | M2 | 2021-06-21 22:51 | 36.697 | -122.378 | >1000 | CTD | 23.8897 | 1 | 2.9862 | 5.8547
5 | 2021-06-22 01:50 | 67-60 | 2021-06-22 02:50 | 36.459 | -122.777 | >1000 | CTD | 39.6293 | 1 | 4.9537 | 9.8409 | Day 2
6 | 2021-06-22 07:48 | 67-70 | 2021-06-22 08:48 | 36.126 | -123.49 | >1000 | CTD | 39.505 | 1 | 4.9381 | 15.7945
7 | 2021-06-22 13:44 | 67-80 | 2021-06-22 16:44 | 35.793 | -124.2 | >1000 | CTD | 39.4113 | 1 | 4.9264 | 21.7327
8 | 2021-06-22 19:40 | 67-90 | 2021-06-22 23:40 | 35.459 | -124.907 | >1000 | CTD | 167.2325 | 48 | 20.9041 | 27.6591 | Day 3-4
9 | 2021-06-25 16:34 | C1 | 2021-06-25 17:34 | 36.796 | -121.85 | >1000 | CTD | 4.806 | 1 | 0.60075 | 96.5631
16 | 2021-06-25 18:10 | ML |  | 36.8 | -121.75 |  | End Cruise | 0 | 1 | 0 | 98.1639
Overall sums | [7 empty] | 345.3111 | 56 | 43.1639 | 4.1318
Formulas:
Start time = [Start time, row above]+(SUM([Station, row above]:[Hrs steam, row above])/24)
End time = [Start time]+([Station])/24