## Sheet1
Serial Number | Base test | Full test | Location / Status
MFET unlabelled | pass | pass | In housing, heading for Lizard Island Oct 2019 deployment
MFET031 | pass |  | Thomz Desk - development unit until mfet040 is fixed
MFET032 | pass |  | Yui Lab
MFET033 | pass |  | Yui Lab
MFET034 | pass |  | Yui Lab
MFET035 | pass |  | Yui Lab
MFET036 | pass |  | Yui Lab
MFET037 | pass |  | Yui Lab
MFET038 | pass |  | Yui Lab
MFET039 | pass |  | Yui Lab
MFET040 | pass->failed |  | Transformer broke, fell out of bag when loading box (gave to Jose to fix - this will be Thoms dev board)
MFET041 | pass |  | Yui Lab
MFETxxx | failed |  | hi current draw, thomz box
MFETxxx | failed |  | wont run - hangs turning on hibernate clock domain, maybe osc prob, Scott box
MFETxxx | failed |  | wont wakeup - wakes by TP1, hangs turning on hibernate module clock, osc prob? Scott box
MFETxxx | failed |  | 32K osc prob per Jim, loc?
MFETxxx | failed |  | 32K osc prob per Jim, loc?
MFETxxx | failed |  | 32K osc prob per Jim, loc?
Base Test
Load program
Run program
uSD store/retrieve
Config test
Deploy test
Sleep test
Power consumption as expected
Verify battery voltage measurement
Full Test
Connect isFET
Connect thermistor
Verify data correctness